Department of Resources Recycling and Recovery

Notice to Prospective Proposers

REVISED 11/22/19 12/2/19

REVISED #2 12/7/19

November 15, 2019

You are invited to review and respond to this modified Request for Proposal (RFP) Primary, entitled “Tree Removal Management for the Camp Fire” DRR19055.  In submitting your proposal, you must comply with the instructions herein.

Note that all agreements entered into with the State of California will include by reference General Terms and Conditions, Special Terms and Conditions and Contractor Certification Clauses which are referenced in Section II of this package.  If you do not have internet access, a hard copy can be provided by contacting the person listed below.

In the opinion of the Department of Resources Recycling and Recovery (CalRecycle) this RFP is complete and without need of explanation.  However, if you have questions, or should you need any clarifying information, the contact person for this RFP is:

Michael VanBaaren

contracts@calrecycle.ca.gov

Phone: 916.341.6303

Fax: 916.319.7345

Please note that no verbal information given will be binding upon the State unless such information is issued in writing as an official addendum.

Michael VanBaaren

Contract Administrator

Table of Contents

Section 1	Overview	1

General Information	1

CalRecycle Contact Information	1

Service Needed	1

Contract Budget	1

Payment Withhold	2

Contract Term	2

Process Type	2

Process Schedule	2

Section II	Rules and Conditions	3

Introduction	3

Commitment	3

Antitrust Claims	3

Contractor’s Cost	4

Information	4

Written Questions	4

Addenda	5

Modification of Submittals	5

Errors in Submittals	5

Unreliable List	5

Suspension and Debarment	5

Electronic Waste Recycling	6

Use Tax	6

Subcontractors	6

Recycled-Content Certification	6

Payments to the Contractor	6

Section III	Proposal Submittal Requirements	7

Introduction	7

Deadline	7

Addressing	7

Number of Copies	7

Document Printing	7

Cover Letter	7

Table of Contents	8

Summary	8

Methodology	8

Organization	10

Qualifications and Resources	10

References	11

Samples of Written Work	11

Contractor Eligibility	11

Licenses	12

Small Business (SB) Preference	12

Disabled Veterans Business Enterprise (DVBE) Incentive	13

Maximum Combined Preferences and Rules for Award	15

Section IV	Cost Proposal Submittal	16

Overview	16

Cost Breakdown	16

Section V	Evaluation and Selection	17

Introduction	17

Selection Process	17

Grounds for Rejection	17

Award of Agreement	17

Notice of Intent to Award	18

Rejection of Award	18

Protest of Award	18

Section VI	Description of Work	20

Work to be Performed	20

Overall Tasks to be Performed	25

Roles	29

Weather Delays	41

Location of Services	41

Control of Work	41

Section VII	Definition and Terms	43

Attachments	45

Cost Proposal Sheet	46

Proposal Scoring Sheet	50

Bidder Declaration	52

Small Business (SB) and Disabled Veteran Business Enterprise (DVBE) Subcontractor Payment Certification	54

Darfur Contracting Act	55

Iran Contracting Act	56

California Civil Rights Laws Certification	57

Contractor Status Form	58

Client References	59

DRAFT Standard Agreement (STD 213)	60

Proposal Completion Checklist	102

# Section 1	Overview

## General Information

The Department of Resources Recycling and Recovery (CalRecycle) has been tasked by the California Governor’s Office of Emergency Services (Cal OES) to manage a coordinated hazard tree removal project for trees damaged by the Camp Fire.  CalRecycle intends to perform this work in an expedited manner in full compliance with Cal OES and Federal Emergency Management Agency (FEMA) project requirements as outlined in this Request for Proposals (RFP), while protecting public health and safety and the environment.

Please note that CalRecycle is soliciting this contract under the authority of the Governor’s Proclamation of a State of Emergency (11-8-2018) and many sections and requirements may differ from typical RFP documents.  Please Note: Time periods are shorter than typical RFPs in order to respond appropriately in the current emergency situation.

## CalRecycle Contact Information

Department of Resources Recycling and Recovery

Physical Address: 	1001 I Street,

Sacramento, CA 95814

Attn: Contracts Unit, MS-19A

Mailing Address:   	PO Box 4025,

Sacramento, CA 95812-4025

Attn: Contracts Unit, MS-19A

Phone:  (916) 341-6303

FAX:  (916) 319-7345

EMAIL:  contracts@calrecycle.ca.gov

Any documents delivered in person must be received in the Visitor’s and Environmental Service Center located in the lobby of the CalEPA Headquarters Building at 1001 I Street, Sacramento, CA 95814.

## Service Needed

This Contract requires the Contractor to provide professional hazard tree removal management services related to the tree removal in Butte County as well as assist CalRecycle in the coordination, documentation, and related efforts necessary to coordinate with county, state, and possibly federal agencies and document tree marking, removal, processing, and disposal.  Services may include support services in other Northern California counties.

## Contract Budget

Subject to the availability of funds and approval by CalRecycle, there is an anticipated maximum budget of approximately $67,500,000 (sixty seven million five hundred thousand dollars and zero cents).  CalRecycle reserves the right to amend the budget for this Agreement as needs arise.

## Payment Withhold

The provisions for payment under this contract will be subject to a ten percent (10%) withholding per task. The withheld payment amount will be included in the final payment to the Contractor and will only be released when all required work has been completed to the satisfaction of CalRecycle. The Contractor agrees to comply with the requirements of Public Contract Code (PCC) section 10346.

## Contract Term

The term of this Agreement will span approximately one year and the anticipated start date is January 2, 2020.  The bulk of the field work is anticipated to take approximately 270 days to complete, with residual field work lasting another 90 days, and office support until the end of the Agreement term.  CalRecycle reserves the right to amend the term of this Agreement as needs arise.

## Process Type

Modified Request for Proposal (RFP) (Primary Method).

## Process Schedule

This process will be conducted according to the following tentative schedule where all times are Pacific Time.

| Advertisement Date | November 15, 2019 |
| --- | --- |
| Written Questions Due by 11:00 a.m. | November 21, 2019 |
| Submittals Due by 2:00 pm | December 11 16, 2019 |
| Cost Proposal Opening at 10:00 a.m. | December 17 20, 2019 |
| Post Notice of Intent to Award Anticipated Start Date | December 17 20, 2019 January 2, 2020 |

# Section II	Rules and Conditions

## Introduction

There are conditions that this RFP, submitting Proposers, proposals and the resulting Agreements are subject to, and/or with which they must comply.

## Commitment

Upon submittal of a Proposal, the Contractor has committed to comply with the following requirements:

- All items noted in RFP documents

- Special Terms and Conditions, which are included in the attached sample contract.

- General Terms and Conditions (GTCs) and Contractor Certification Clauses (CCCs) are both available for viewing at

https://www.dgs.ca.gov/OLS/Resources/Page-Content/Office-of-Legal-Services-Resources-LIst-Folder/Standard-Contract-Language

- FEMA Public Assistance Program Clauses, which are included in the sample Agreement attachment.

The above terms, conditions, and/or requirements are not subject to negotiation.  Any Proposer that reserves a right to negotiate or expresses any exception to the above terms, conditions, and/or requirements will be disqualified.

If the Proposer fails to meet any of the requirements or comply with CalRecycle requests, CalRecycle can reject, disqualify, or remove the firm from the process. CalRecycle is not committed to award an Agreement resulting from this RFP.

## Antitrust Claims

In submitting a Proposal Package to a public purchasing body, the Proposer offers and agrees that if the Proposal Package is accepted, it will assign to the purchasing body all rights, title, and interest in and to all causes of action it may have under Section 4 of the Clayton Act (15 U.S.C. Sec. 15) or under the Cartwright Act (Chapter 2 [commencing with Section 16700] of Part 2 of Division 7 of the Business and Professions Code), arising from purchases of goods, materials, or services by the Proposer for sale to the purchasing body pursuant to the Proposal Package.  Such assignment shall be made and become effective at the time the purchasing body tenders final payment to the Proposer.  (See Government Code Section 4552.)

If an awarding body or public purchasing body receives, either through judgment or settlement, a monetary recovery for a cause of action assigned under this chapter, the assignor shall be entitled to receive reimbursement for actual legal costs incurred and may, upon demand, recover from the public body any portion of the recovery, including treble damages, attributable to overcharges that were paid by the assignor but were not paid by the public body as part of the Proposal Package price, less the expenses incurred in obtaining that portion of the recovery.  (See Government Code Section 4553.)

Upon demand in writing by the assignor, the assignee shall, within one year from such demand, reassign the cause of action assigned under this part if the assignor has been or may have been injured by the violation of law for which the cause of action arose and (a) the assignee has not been injured thereby, or (b) the assignee declines to file a court action for the cause of action.  (See Government Code Section 4554.)

## Contractor’s Cost

All costs resulting from the Contractor’s participation in the RFP process are at the firm’s expense. No costs incurred by the Contractor participating in the RFP process will be reimbursed by CalRecycle.

## Information

All materials submitted in response to this RFP will become the property of CalRecycle and, as such, are subject to the Public Records Act (Government Code sections 6250 et seq.). CalRecycle will disregard any language purporting to render all or portions of any bid package confidential.

All information obtained or produced during the course of the Agreement will be made available to CalRecycle.

Any information obtained or produced during the course of the Agreement that qualifies as confidential or a trade secret(s) under the Public Records Act (PRA) or the Public Contract Code (PCC) and is thus exempt from disclosure under those statutes must so be marked by the proposer prior to submission to CalRecycle. Any claims of confidentiality or trade secret(s) except as to information that qualifies as such under the PRA or PCC may result in disqualification.

CalRecycle will hold information obtained or produced during the course of the Agreement deemed confidential or trade secret(s) by the proposer to the extent allowable by the California Public Records Act and the Public Contract Code.

## Written Questions

Proposers needing clarification of the requirements of this solicitation may submit questions to CalRecycle’s Contracts Unit.  All inquiries must be received no later than 11:00 a.m. on November 21, 2019 regardless of postmark. If the inquiries are faxed, then the time and date on the fax must not be later than the due date and time.

Questions, suggestions or objections regarding the content of this solicitation, including but not limited to the purpose, scope of work, etc., not submitted by the deadline for questions shall be deemed waived and may not be raised at a later time.

Oral communications with CalRecycle officers and employees shall be non-binding on the State and shall in no way excuse the Proposer of any obligations as set forth in this package.

All questions or inquiries regarding this solicitation shall be submitted using the contact information provided in Section I.

E-mails and/or faxes should be clearly marked “Questions Relating to SOLICITATION DRR19055”.

The questions and answers will be published in an Addendum to the RFP (see below, Addenda).

## Addenda

CalRecycle reserves the right to amend, alter, or change the rules and conditions of this RFP.

Any ambiguity, conflict, discrepancy, omission, or other error discovered in the RFP should immediately be reported to CalRecycle.

## Modification of Submittals

A Proposal submitted prior to the submittal deadline, can be withdrawn or modified by the submitting proposer.  The proposer must:

- Provide a written request

- Identify the requesting individual and their association to the proposer

A Proposal cannot be withdrawn for modification after the submittal deadline has passed.

## Errors in Submittals

An error in a Proposal package may be cause for rejection of that Proposal.

CalRecycle may make certain corrections, if the Proposer’s intent is clearly established based on review of the complete proposal.

## Unreliable List

Any contractor or subcontractor currently on CalRecycle’s Unreliable list, is ineligible to apply for or participate in this contract.

## Suspension and Debarment

This contract is a covered transaction for purposes of 2 C.F.R. pt. 180 and 2 C.F.R. pt. 3000. As such the contractor is required to verify that none of the contractor, its principals (defined at 2 C.F.R. § 180.995), or its affiliates (defined at 2 C.F.R. § 180.905) are excluded (defined at 2 C.F.R. § 180.940) or disqualified (defined at 2 C.F.R. § 180.935).

The contractor must comply with 2 C.F.R. pt. 180, subpart C and 2 C.F.R. pt. 3000, subpart C and must include a requirement to comply with these regulations in any lower tier covered transaction it enters into.

This certification is a material representation of fact relied upon by CalRecycle. If it is later determined that the contractor did not comply with 2 C.F.R. pt. 180, subpart C and 2 C.F.R. pt. 3000, subpart C, in addition to remedies available to the State of California or CalRecycle, the Federal Government may pursue available remedies, including but not limited to suspension and/or debarment.

The bidder or proposer agrees to comply with the requirements of 2 C.F.R. pt. 180, subpart C and 2 C.F.R. pt. 3000, subpart C while this offer is valid and throughout the period of any contract that may arise from this offer. The bidder or proposer further agrees to include a provision requiring such compliance in its lower tier covered transactions.

## Electronic Waste Recycling

If the Contractor or any subcontractors participate in activities that result in the disposition of electronic components, they will comply with the provisions of PRC Chapter 8.5.

## Use Tax

If, during the course of the agreement, the Contractor will be involved in the re-sale of goods to the State, they must comply with the requirements of Section 6452.1, 6487, 6487.3, 7101, and 18510 of the Revenue and Taxation Code, in addition to Section 10295.1 of the Public Contract Code.

## Subcontractors

All subcontractors identified in the proposal, must be experts in their respective disciplines and capable of performing the tasks for which they are hired.

If awarded the Agreement, the Contractor must use all of the SB and DVBE firms identified on the Bidder Declaration (Attachment C) form.

Contractor understands and agrees that should award of this contract be based in part on their commitment to use the Disabled Veteran Business Enterprise (DVBE) subcontractor(s) identified in their proposal, per Military and Veterans Code 999.5 (e), a DVBE subcontractor may only be replaced by another DVBE subcontractor and must be approved by the Department of General Services (DGS). Changes to the scope of work that impact the DVBE subcontractor(s) identified in the proposal and approved DVBE substitutions will be documented by contract amendment.

Failure of Contractor to seek substitution and adhere to the DVBE participation level identified in the proposal may be cause for contract termination, recovery of damages under rights and remedies due to the State, and penalties as outlined in M&VC § 999.9; Public Contract Code (PCC) § 10115.10, or PCC § 4110 (applies to public works only).

CalRecycle reserves the right to approve substitutions of subcontractors, as long as, certified business participation levels remain unchanged.

## Recycled-Content Certification

The Proposer receiving award of this Contract will be required to report all State Agency Buy Recycled Campaign (SABRC) reportable purchases and the recycled content of those purchases.  The sample Agreement, Attachment H, contains this form (CalRecycle 74C) and is required to be submitted with each invoice or annually as determined by the CalRecycle Contract Manager.

## Payments to the Contractor

Payments to the Contractor by CalRecycle will be made in arrears.  Services rendered by the Contractors must be identified on an invoice, to be billed monthly in arrears.

# Section III	Proposal Submittal Requirements

## Introduction

Failure to follow the instructions contained in this document may be grounds for rejection of a Proposal.

CalRecycle may reject any Proposal if it is conditional, incomplete or contains irregularities.

CalRecycle may waive an immaterial deviation in a Proposal, if deemed in the best interest of CalRecycle.

## Deadline

The Proposal Package must be received by CalRecycle, at the address listed in Section I, Overview by 2:00 p.m. on December 11 16, 2019.

Proposals received after the deadline will be considered late and returned to the Proposer unopened.

## Addressing

The proposal package must clearly state that it is in response to this RFP and note the RFP number listed with the direction of “Mailroom – do not open.”

## Number of Copies

The Proposer is required to submit all required documents in the following format:

- One original, non-bound hard copy marked “Original” (Do not include Cost Proposal Sheet in this set)

- One original signed Cost Proposal Sheet in a separate sealed envelope marked “Proposal Cost-Do Not Open”

- Three (3) bound hard copy marked “Copy” (Do not include Cost Proposal Sheet in this set)

- One electronic copy on USB flash drive viewable by Adobe Acrobat Reader.  Entire proposal, including any attachments, must be saved as a single document. (Do not include Cost Proposal Sheet in the electronic copy)

It is the submitting Proposer’s responsibility to ensure that the electronic copy is formatted in Adobe Acrobat Reader and viewable by CalRecycle.

## Document Printing

All documents must be submitted double-sided on paper with a minimum of 100% post-consumer recycled content fiber.

## Cover Letter

The cover letter shall be signed by an individual who is authorized to bind the Proposer and shall indicate that person's title or position.  The cover letter must be on the Proposer's company letterhead and contain the following information:

- Name and address of the Proposer submitting qualifications;

- Proposer’s Headquarters for purposes of this agreement, if awarded;

- Name, telephone number, and e-mail address of a person who can be contacted if further information is required;

- Name, title, address, telephone number, and e-mail address of individual(s) with authority to execute a binding Agreement on behalf of the Proposer;

- Statement that the Proposer will have qualified personnel available to meet the service;

- Statement attesting to the fact of the percentage of post-consumer recycled content fiber paper used in the compilation of the proposal package;

- Statement stating that the Contractor and any Subcontractors to be used during the performance of the contract are eligible to contract with the State of California, pursuant to PCC 10286;

- Statement verifying that none of the Contractor, its principals, or its affiliates are excluded or disqualified (per the Suspension and Debarment clause of Exhibit G); and

- List of Contractor’s and any subcontractor(s’) business names, identification of certified SB status, if applicable, and corresponding OSDS Reference number(s) issued to the certified SB by the DGS.

## Table of Contents

The information must be organized as presented with corresponding page references.

## Summary

The Proposer must include a brief overview of the project and summarize the Proposer’s approach to the work.

## Methodology

The proposal must include a Staffing Work Plan describing the methods to be employed to accomplish the contract activities in Section VI Description of Work.  The methodology must be described in sufficient detail to allow CalRecycle staff to evaluate the methods and must address all tasks and items in the Scope of Work. The description must include not only what work will be performed, but how it will be performed, and how it will be managed in a way that meets Federal Emergency Management Agency (FEMA) debris removal standards and Timber Harvest Plan and/or Waiver requirements.

The personnel described in the Scope of Work outlines the anticipated roles and responsibilities of each of the required staff necessary for completing the task requirements.

Each proposal, at a minimum, shall include the following:

- A written narrative describing the method or manner in which the Proposer intends

to satisfy the requirements of the Scope of Work.

- A description of the Proposer’s experience in providing tree removal management and monitoring services as outlined in the Scope of Work including specific experience with California Governor’s Office of Emergency Services (Cal OES) and/or Federal Emergency Management Agency (FEMA) compliance on Cal OES and/or FEMA reimbursable Hazard Tree Removal projects. The description should also include experience with the National Incident Management System (NIMS) and specific Incident Command System (ICS) experience. The Proposer may also include specific experience in providing similar services for other state and/or local agencies.

- An organizational chart to show the project positions and corresponding ICS personnel and subject matter experts (SMEs) that shall be responsible for providing the services.

- Professional resumes for key project personnel, including one Project Manager, one Incident Commander, two Operations Chiefs, two Deputy Operations Chiefs, two Planning Chiefs, two Deputy Planning Chiefs, one Logistics Chiefs, two Finance Chiefs, three Environmental Branch Directors, two Branch Directors, one Health and Safety Officer, ten four Registered Professional Foresters (RPFs), and at least twenty professional International Society of Arboriculture (ISA) Certified Arborists that are Tree Risk Assessment Qualified (TRAQ) (Arborists).  Professional resumes for four branch directors, division supervisors and other project personnel are desired to demonstrate the experience of the Proposer’s resources but are not required.

- Response Plan – given the critical nature of this work and the importance of an immediate response, the Proposer must provide a plan to indicate the initial steps that will be taken to fulfill the management, staffing and debris monitoring needs of the Project.  The response plan shall demonstrate that, within two (2) days of the Contractor’s notice to proceed, four (4) RPFs and up to fifteen (15) registered Arborists will be trained and then deployed to begin a windshield survey and report of the number and sizing of hazard trees, damaged by fire (as defined by CalFire) and located on private properties that could fall on public rights of way.  This survey and supporting report, will be a follow on to a CalFire Tree Inventory Sampling Plan, dated October 18, 2019.  The Contractor’s report shall delineate the total number of trees found, by species, and their size (diameter and height) as listed below:

| Size Category Tree | Diameter at 4.5 Feet above ground level* |
| --- | --- |
| R1 | 6" - 10" |
| R2 | 10" - 24" |
| R3 | 24" - 40" |
| R4 | >40" |

*If the tree trunk forks below 4.5 feet above the ground, please note that this tree should be tracked/paid as a single tree.  A reasonable diameter measurement for such a tree would be a measurement taken below the fork of the tree.

This report shall be completed within four (4) weeks of that notice to proceed.

The response plan shall also describe how the Contractor intends to conduct the windshield survey and complete it within the four-week period.  Finally, the response plan shall also indicate A plan for how the Team of RPFs plan on shall prepare preparing appropriate Timber Harvest Plan(s)/Conversion Exemptions to meet the CalFire and National Environmental Policy Act (NEPA) requirements for tree removal.  The plan shall also demonstrate how and how quickly the initial 20 paired teams of Arborists with task force leaders (TFLs) will be trained by the RPFs on project specific hazard tree marking methodology, how to assess and determine eligible hazard trees for this program, what environmental conditions to look for at each property and then how to enter all of the necessary information using the Survey 123 data collection software questionnaire developed by CALFIRE.  Then, these teams will be sent out to mark and document hazard trees from properties for which right of entry forms (ROEs) have been accepted into the program.

Hazard Trees - are trees that meet the FEMA description, namely: “if its condition was caused by the disaster; it is an immediate threat to lives, public health and safety, or improved property; it has a diameter at 4.5 feet above ground level of six inches or greater; and one or more of the following criteria: it has more than 50% of its crown damaged or destroyed, or it is a split trunk, broken branches or exposed heartwood, or it is leaning at an angle greater than 30 degrees.” Or as more precisely described in the CalFire Tree Notes No. 33 for, “Survival of Fire-Injured Conifers in California”, Owen, Cluck, Smith, (April, 2015).

The Operations Chief, Planning Chief, Logistics Chief, and Financial Chief shall be deployed within one (1) week of the Contractor’s notice to proceed.  The other listed staff shall be deployed and phased in within a 2-3 week period of the Contractor beginning work.  All Proposer field staff shall be Occupational Safety and Health Administration (OSHA) certified.

## Organization

Provide a brief description of the organization’s services and activities, including:

- Date of establishment

- History

- Location

- Any known conflicts of interest

## Qualifications and Resources

As demonstrated by resumes and references, the Proposer and any subcontractors must have the experience, qualifications, and resources to perform the required tasks of the project.

As demonstrated by resumes and references, the Proposer must be highly knowledgeable in providing ICS management services related to the tree cleanup project tasks including:

- Hazard Tree Windshield Survey;

- Hazard Tree assessments, for properties for which the IMT has Right of Entry (ROEs);

- Hazard Tree Removal planning;

- Logistic operations;

- Finance/administration qualifications and;

- State and Federal Environmental permitting and oversight of Best Management Practices (BMP) installation prior to and after tree removal (by Tree Removal Contractor)

As demonstrated by resumes and references, the Proposer must be able to provide management of tree removal activities and assist CalRecycle in the coordination, documentation and other necessary efforts required to coordinate with local, state, and federal agencies (if and where necessary) that are represented as part of the disaster hazard tree removal effort.  It is highly recommended that the majority of the Proposer’s key staff have a minimum of three (3) years of experience supporting, overseeing, and monitoring hazard tree removal and/or remediation site cleanup management support service (ideally, FEMA hazard tree removal, debris cleanup, and/or ICS related experience).

This service requires experience with the management of post-disaster hazard tree removal environmental support and monitoring management, and it is expected that between 250-300 employees (Arborists, Biologists, Archaeologists, Task Force Leaders, and IMT members) and 20-30 Administrative staff will be needed in order to complete this task.

Each Proposal must include a description of the resources to be used on the project while demonstrating an individual or team members’ abilities to perform the work.  The Proposer shall include resumes for the Project Manager, Incident Commander, four RPFs, Registered Certified Arborists who are Tree Risk Assessment Qualified (TRAQ) (minimum of 20), key Biologists, key Archaeologists, Personnel, and Subcontractors, that include:

  - Experience

  - Knowledge

  - Educational Background

  - Appropriate licensing

## References

The Proposer’s team must provide a minimum of three (3) verifiable references and/or experience that support the above qualifications.

CalRecycle reserves the right to seek references in addition to the client references provided by the Proposer, as it deems necessary.

If a reference or project experience is unable to be verified, it may be disregarded.  Because of the extremely short period for proposal evaluation, CalRecycle reserves the right not to disqualify a proposal if some references cannot be verified in the time scheduled.

## Samples of Written Work

The Proposal must include a copy of a final report from a project that is similar in nature to the proposed project.

## Contractor Eligibility

The Proposer must include a written declaration, stating that the Contractor and any Subcontractors to be used during the performance of the contract are eligible to contract with the State of California, pursuant to PCC section 10286.1.  Statement may be included in the cover letter.

## Licenses

The Proposer and any Subcontractors shall be individuals or firms qualified to do business in California.  The Proposal must include the following required documentation:

- A copy of the Proposer’s (and any Subcontractors’) professional registrations with the California Secretary of State.

- Registered Professional Forester, per the 2019 California Forest Practice Rules and pursuant to Article 3, Chapter 2, Division 1 of the Public Resources Code.

- Registered Certified Arborists (i.e. International Society of Arboriculture (ISA), America Society of Consulting Arborist (ASCA), or certified or a degreed Forester) who are also Tree Risk Assessment Qualified (TRAQ).

- Registered safety professional (CIH or CSP).

- The Proposer (prime Contractor only) must provide their OSHA lost time injury/illness incidence, OSHA recordable injury/illness incidence, and their Workers Compensation Insurance Experience Modification Rate (EMR) for the last 3 years.

## Small Business (SB) Preference

The following information shall apply to both SBs and Micro Businesses (MB).

Any Proposer competing in this process as a California Certified Small Business (SB) or Micro Business (MB), or as a non-SB certifying to subcontract a minimum of 25% of the total contract services to a California Certified SB or MB, will receive a five percent (5%) preference. Certification must be provided by the Department of General Services (DGS), Procurement Division (PD), Office of Small Business and DVBE Services (OSDS). CalRecycle will apply the preference per State law and as described on the DGS website at http://www.dgs.ca.gov/pd/Programs/OSDS.aspx .

A five percent (5%) preference is available to a non-small business claiming twenty-five percent (25%) California certified small business subcontractor participation. If claiming the non-small business subcontractor preference, the Proposal response must include a list of the small business(es) with which you commit to subcontract in an amount of at least twenty-five percent (25%) of the net Proposal price with one of more California certified small businesses. Each listed certified small business must perform a "commercially useful function" in the performance of the contract as defined in Government Code Section 14837(d)(4).

The required list of California certified small business subcontracts must be attached to the Proposal response and must include the following: 1) subcontractor name, 2) address, 3) phone number, 4) a description of the work to be performed and/or products supplied, 5) and the dollar amount or percentage of the net Proposal price (as specified in the solicitation) per subcontractor.  Use the Bidder Declaration form to report this information.

Proposers claiming the five percent (5%) preference must commit to subcontract at least twenty-five percent (25%) of the net Proposal price with one or more California certified small businesses. Completed certification applications and required support documents must submitted to the office of Small Business and DVBE Certification (OSDC) no later than 5:00 p.m. on the Proposal due date, and the OSDC must be able to approve the application as- submitted. Questions regarding certification should be directed to the OSDC at (916) 375-4940. In no event shall the SB preference or non-SB subcontracting preference exceed $50,000 in any single Proposal. In order to apply the preference and calculate the maximum preference amount, the bidder’s Total Daily Cost will be multiplied by an estimated 50 days of work.

The preference is applied during the evaluation process and is only applied for responsive Proposals from responsible Proposers proposing the percentage of SB participation for the incentive specified above. The SB preference will be applied when a responsible Proposer that is not a CA certified SB or a non-SB claiming 25% CA certified SB subcontractor participation submits the lowest responsive Proposal.

For award based on low price, the preference is applied by reducing the Proposal price by the amount of incentive as computed from the lowest responsive and responsible Proposal price.  The computation is for evaluation purposes only.  Application of the incentive shall not displace an award to a small business with a non-small business.

A copy of the Proposer’s SB certification should be included with the Proposal Package.

If the Proposer makes a commitment to achieve small business participation, then the Proposer, if awarded this contract, must within 60 days of receiving final payment (or within such other time period as may be specified elsewhere in this Contract) report to the awarding department the actual percentage of small business participation that was achieved (Govt. Code § 14841).  Refer to Attachment D to fulfill this requirement.

## Disabled Veterans Business Enterprise (DVBE) Incentive

Any Proposer competing in this process as a California Certified Disabled Veterans Business Enterprise, or as a non-DVBE certifying to subcontract a minimum of 3% of the total contract services to a California Certified DVBE will receive an incentive as shown below:

- Five (5%) and above participation level = Proposal will receive five percent (5%) 
incentive.

- Four (4%) participation level = Proposal will receive two percent (2%) incentive.

- Three (3%) participation level = Proposal will receive one percent (1%) incentive.

Certification must be provided by the Department of General Services (DGS), Procurement Division (PD), Office of Small Business and DVBE Services (OSDS).

A five percent (3-5%) Proposal incentive is available to a non-DVBE claiming a minimum of three percent (3%) California certified DVBE subcontractor participation. If claiming the non-DVBE subcontractor incentive, the Proposal response must include a list of the DVBE(s) with which you commit to subcontract in an amount of at least three percent (3%) of the net Proposal price with one of more California certified DVBEs. Each listed certified DVBE must perform a "commercially useful function" in the performance of the contract as defined in Government Code Section 14837(d)(4).

The required list of California certified DVBE subcontracts must be attached to the Proposal response and must include the following: 1) subcontractor name, 2) address, 3) phone number, 4) a description of the work to be performed and/or products supplied, 5) and the dollar amount or percentage of the net Proposal price (as specified in the solicitation) per subcontractor.  Use Attachment B to report this information.

Proposers claiming incentive must commit to subcontract at least three percent (3%) of the net Proposal price with one or more California certified DVBEs. Completed certification applications and required support documents must submitted to the office of Small Business and DVBE Certification (OSDC) no later than 5:00 p.m. on the Proposal due date, and the OSDC must be able to approve the application as- submitted. Questions regarding certification should be directed to the OSDC at (916) 375-4940.

The incentive is applied during the evaluation process and is only applied for responsive Proposals from responsible Proposers proposing the percentage(s) of DVBE participation for the incentive(s) specified above.

For award based on low price, the incentive is applied by reducing the Proposal price by the amount of incentive as computed from the lowest responsive and responsible Proposal price.  The computation is for evaluation purposes only.  Application of the incentive shall not displace an award to a small business with a non-small business.

A copy of the Proposer’s DVBE certification should be included with the Proposal Package.

For information on locating DVBE resources please go to the following website http://www.dgs.ca.gov/pd/Programs/OSDS.aspx

A copy of the Proposer’s DVBE certification should be included with the Proposal Package.

If awarded, the Proposer who has made a commitment to achieve disabled veteran business enterprise (DVBE) participation, must within 60 days of receiving final payment under this agreement (or within such other time period as may be specified elsewhere in this agreement) certify in a report to the awarding department: (1) the total amount the prime contractor received under the contract; (2) the name and address of the DVBE(s) that participated in the performance of the contract; (3) the amount each DVBE received from the prime contractor; (4) that all payments under the contract have been made to the DVBE(s); and (5) the actual percentage of DVBE participation that was achieved. A person or entity that knowingly provides false information shall be subject to a civil penalty for each violation (Military & Veterans Code (M&VC) § 999.5(d)).  Refer to Attachment D to fulfill this requirement.

## Maximum Combined Preferences and Rules for Award

In combination with any other preferences (SB or DVBE participation) the maximum limit of the combined preferences is 15% of the bid amount and, in no case, more than $100,000.00 per solicitation. In order to apply the preference and calculate the maximum preference amount, the bidder’s Total Daily Cost will be multiplied by an estimated 250 days of work.

Preference programs for the non-SB subcontracting preference cannot displace a direct award to a certified SB. In the event of a tie between a SB and a firm that is SB and DVBE, the award shall be made to the firm that is SB and DVBE.

# Section IV	Cost Proposal Submittal

## Overview

The Cost Proposal Sheet must be submitted in a separate, sealed envelope by the due date identified in the Schedule of Section I.

The envelope must read “Proposal Cost-Do Not Open”.

## Cost Breakdown

The Cost Proposal must specify the total cost and include detailed project costs, as required in the Cost Proposal Sheet. The winning proposer’s invoices must be itemized as shown in the submitted cost sheet.

The costs identified, should take into consideration the length of the contract, rise in salaries and administrative overhead costs.

The Cost Proposal Sheet is a self-contained document for purposes of evaluating whether all information required by the RFP has been submitted and determining lowest cost. Therefore, all information must be included on the Cost Proposal Sheet. Reference by incorporation to the proposal is not acceptable.

The rates identified on the Cost Proposal Sheet may not be changed and will remain in effect for the life of the Agreement.

The rates on the Cost Proposal Sheet represent the rate the Contractor will be paid for each hour of work.  The proposed hourly prices must be inclusive of all items reasonably required to perform the work, including labor, cameras, computers, cell phones, navigation devices, vehicle, overhead, and profit for each hour of work, including overtime, pre-planned shutdowns, non-working days and holidays, and any other items reasonably required to perform the work. These items cannot be invoiced separately.

The hourly labor costs do not include lodging costs. There is a possibility that the Contractor’s staff will be lodged (housing only) in a base camp, provided by the Contractor or by others. If separate lodging is required because base camps have not been established or because no base camp is provided, the Contractor may invoice at the Cost Proposal Sheet rates for on-site Contractor employees with a premium of $10 per hour during the period where the Contractor is required to provide separate lodging.  No other compensation for lodging will be allowed. If the Contractor is asked to provide a base camp, those costs will be covered in a Change Order in the Contract.

The Cost Proposal Sheets will be compared on the basis of Total Daily Cost to determine the lowest cost proposal among all proposals receiving passing scores.

# Section V	Evaluation and Selection

## Introduction

CalRecycle will perform a Pre-Qualification Evaluation process to ensure that the Proposer has included all required documentation in the Proposal submittal.

If a proposal package does not meet all of the requirements set forth in this RFP, it will be considered non-responsive and rejected from further competition.

Those Proposer’s submittals that pass this review will be forwarded to the Selection Committee for Evaluation.

## Selection Process

The Selection Committee will evaluate and score all proposals, passing the Pre-Qualification Evaluation, utilizing the Scoring Criteria identified in this RFP. Only those that receive a score of at least the minimum requirement identified on the Scoring Sheet will advance to the cost opening and be eligible to be awarded a contract. The qualified cost proposals (sealed) will be opened publicly at the CalEPA building at 1001 I Street, Sacramento, CA at the time set in Section I Overview, Process Schedule.

## Grounds for Rejection

All proposals may be rejected whenever the determination is made that the proposals received are not really competitive, when the cost is not reasonable, or when the cost exceeds the amount expected.

Additionally, a proposal may be rejected if:

- It is received after the due date and time for submittal

- The cost submittal is unsigned

- Duplicative staff from other current fire debris removal projects are proposed for primary staff positions within the Proposer’s team

- The proposal cost is not prepared as required by the RFP

- The Proposer has been prohibited from contracting with the State by the Department of Fair Employment and Housing

- The Proposer has received a substantive negative contract performance from the State

- Any items required by the RFP are not included with the submittal

No proposal may be rejected arbitrarily or without reasonable cause.

## Award of Agreement

The award of this Agreement will be to the lowest responsive responsible Proposer meeting all of the RFP requirements.

In the event of a tie, CalRecycle will utilize a tie breaker to determine the winning Proposer.  The tie breaker will be determined based on which proposer has the most SB and DVBE participation identified in Attachment C.

CalRecycle reserves the right to not award an Agreement.

## Notice of Intent to Award

CalRecycle will post a Notice of Intent to Award this Contract as soon as possible after the Cost Proposal opening.  This notice will be posted for five (5) working days, but because of the emergency situation CalRecycle may move forward with contract award during the 5-day period, subject to the protest procedure discussed below.

Notice of the intent to Award will be posted on CalRecycle’s website at www.CalRecycle.ca.gov/contracts and at the headquarters building noted in Section I.  It is the Proposer’s responsibility to check one of these locations for a copy of the Notice of Intent to Award.

## Rejection of Award

If the Proposer fails to enter into a satisfactory Agreement within a reasonable timeframe after the award is made, CalRecycle may deem that the Proposer has rejected the award.

CalRecycle reserves the right to disqualify the awardee and award the Agreement to the next highest ranked Proposer.

CalRecycle will notify the rejected highest ranked Proposer at least one (1) day prior to the award being made, of the decision not to award the agreement.

## Protest of Award

A Bidder may protest the proposed award by filing a protest with CalRecycle’s Hearing Officer.  The protest must be filed within five (5) working days of the notice of intent to award the contract.  The Bidder must submit a detailed written statement with information that supports that the Bidder would have been awarded the contract and the grounds for that position.

Because of the necessity to begin fire-damaged tree removal immediately, the Agreement may be awarded prior to a decision on the filed protest.  In the event that the Hearing Officer finds that the contract was awarded incorrectly, the contract may be terminated and awarded to the protestant, terminated and resolicited by CalRecycle, or simply terminated, at the sole discretion of CalRecycle.

In considering the protest, the Hearing Officer may request and consider written statements of the protestant, the apparent awardee, and CalRecycle, along with all RFP and proposal documents.

The protest documents should be sent via registered mail to the following parties:

Department of Resources Recycling and Recovery

Attn: Hearing Officer

1001 I Street, MS-25A

Sacramento, CA  95814

Fax (916) 319-7498

Department of Resources Recycling and Recovery

Attn: Contracts Unit

1001 I Street, MS-19A

Sacramento, CA  95814

Fax (916) 319-7345

Email contracts@calrecycle.ca.gov

# Section VI	Description of Work

## Work to be Performed

The Contractor shall perform all tree removal management services and reporting as required to manage the tree removal services in support of the Incident Commander (IC) including providing Planning, Logistics, Operations, and Finance/Administrative services, as directed by the CalRecycle Contract Manager.  Through Work Orders, CalRecycle will direct the Contractor when and where these services are necessary.  Typical tasks to be performed under this Agreement shall include, but are not limited to:

- Provide up to two Planning Chiefs (PC), per the Incident Command System (ICS) model as directed by the IC, who shall work cooperatively in support of the IC and the incident requirements as defined by the IC, California Governor’s Office of Emergency Services (Cal OES), and the CalRecycle Contract Manager. CalRecycle may use the Contractor’s PC as support to CalRecycle’s own PC but requires the Contractor’s PC to be fully qualified to assist and even take over the role on an as-needed basis. The Planning Team shall perform (but not be limited to) the following tasks:

- Work with the IC, and the Operations and Logistics Chiefs, to support CalRecycle and the RPFs in preparing the Timber Harvest Plans/Conversion Exemptions, if and as necessary.  The implementation of that plan will be conducted as the individual properties become available, based on the Town and/or County’s approval of Rights of Entry (ROEs), and as directed by the CalRecycle Planning Chief. The CalRecycle Planning Chief will control the work under this Agreement, and Work Orders will be issued as properties become available.

- Assist CalRecycle Planning Chief in assigning Contractor Registered Professional Foresters (RPFs) and their Certified Arborists/Arborist Technicians to properties for delineating and documenting trees that are deemed hazardous.

- Provide necessary support staff, including at least one full-time Geographic Information Systems (GIS) experienced and proficient professional who shall incorporate all necessary property data necessary to track the cleanup of each participating property.

- Provide up to two Operations Chiefs (OC), per the ICS model, as directed by the IC. These OCs shall work cooperatively in support of the IC and the incident requirements, as defined by the IC, State OC, and the CalRecycle Contract Manager. The OC shall head up an Operations Team that shall provide all necessary support staff including Division Supervisors and Task Force Leaders to oversee the actual cleanup activities by the Tree Removal Contractor(s) (under separate Agreement to CalRecycle). CalRecycle will likely use the Contractor’s OC as support to CalRecycle’s own OC but requires the Contractor’s OC to be fully qualified to assist and even take over the role on an as-needed basis. The Operations Team shall perform (but not be limited to) the following services:

- Tree Removal oversight, including but not limited to, documenting the cutting and removal of RPF designated hazard trees, located on properties that are eligible for tree removal as determined by the IMT and private properties that could fall on public rights of way or public facilities, as determined by the RPF and addressed in the Timber Harvest Plan/Conversion Exemptions. Cut trees, processed slash and limbs, and chipped trees shall be handled separately. Cut trees, processed slash and limbs, and chipped trees shall be tracked separately (material quantities and costs) all the way to the Logging Decks. Logging Decks are where trees will be processed, prior to taking them to the Materials Receiving Facilities. The processed tree waste will also be tracked to the Materials Receiving Facilities (i.e., lumber mills, biomass burning facilities, etc.) to meet the overall objectives of this project and to track costs. The Contractor shall develop the form and format of the daily reports to the satisfaction of CalRecycle, to be consistent with Federal Emergency Management Agency (FEMA) standards and style for electronic monitoring reports, with input from CalRecycle staff.

- Assist the Tree Removal Contractor(s) in arranging for efficient coordination of trucks designated for the removal of trees and processed vegetative materials. Assist the Tree Removal Contractor(s) in arranging for efficient coordination of water trucks for dust control.

- Provide Hazard Tree Evaluation Teams to conduct Initial Site Reconnaissance, as directed by the IMT’s State Forester and the State’s OC. Also conduct hazard tree evaluations of each property in the program. These teams shall also be responsible for any post-tree cutting and removal confirmation and site condition evaluations.

- Be responsible for the preparation of an ICS Team and Tree Removal Operation Health and Safety Plan (HSP), signed by a certified health and safety professional. The HSP shall designate a project Health and Safety Officer for the Contractor’s employees and/or Subcontractors. The Contractor shall submit a draft copy of the health and safety plan to CalRecycle’s designated agent upon execution of this Agreement for review and comment. The Contractor shall designate, in writing, the individuals responsible for initiating, maintaining, and supervising all safety precautions and programs in connection with the work to be performed for the duration of this Agreement. The Contractor shall be responsible for the health and safety of its workforce and shall comply with all State and Federal Occupational Safety and Health Administration (OSHA) requirements. CalRecycle may handle this task with in-house resources and will coordinate as to who performs this task.

- Provide one Logistics Chiefs (LC), per the ICS model, as directed by the IC. The LC shall work in support of the IC and the incident requirements as defined by the IC, Cal OES and the CalRecycle Contract Manager. CalRecycle will likely use the Contractor’s LC as support to CalRecycle’s own LC but requires the Contractor’s LC to be fully qualified to assist and even take over the role on an as-needed basis. The LC and the Logistics Team shall provide (but not be limited to) the following services:

- Provide coordination with the tree disposal site owners and/or operators.

- Provide and/or coordinate with the Tree Removal Contractor(s) the means of communication among field crews, Operations Team members, Planning Team members, and the IC, as required.

- Provide coordination with the Tree Removal Contractor for a workspace and support services for the Tree Removal Operations Center (TROC).

- Coordinate with IC, OC, PC, Finance Chief, the Health and Safety Officer, and the Tree Removal Contractor to provide support services to the other Teams to be able to complete their defined tasks.

- The LC shall coordinate closely with the Tree Removal Contractor in providing these sustaining goods and services efficiently and effectively to both sets of staff.

- Provide at least one Finance/Administration Chief (FC), per the ICS model as directed by the IC. The FC will work cooperatively in support of the IC and the incident requirements as defined by the IC, Cal OES and the CalRecycle Contract Manager. CalRecycle will likely use the Contractor’s FC as support to CalRecycle’s own FC but requires the Contractor’s FC to be fully qualified to assist and even take over the role on as as-needed basis. The Finance/Administrative Team may be required to provide (but not be limited to) the following services:

- Prepare or support CalRecycle staff in the solicitation of the Tree Removal Contractor(s) Agreement.

- Support CalRecycle staff in the oversight and implementation of the Tree Removal Contractor(s) Agreement.

- Assist CalRecycle staff in setting up the Tree Removal Contractor(s) and their subcontractor’s invoice requirements to provide ease of invoice review and cost tracking of tree removal operations conducted per site cleaned up as part of the Government Hazard Tree Removal Program, to best meet the needs of CalRecycle and Cal OES for ease of state and/or Federal (if applicable) reimbursement.

- Assist CalRecycle staff in the review and processing of invoices for payment.  This support may take place in the TROC office in the field, or at CalRecycle’s offices in Sacramento.

- Assist CalRecycle in assembling and assessing Agreement correspondence.  This includes assistance in responding to the contractor’s requests for information, notices of potential claims, and claims review, assessment, and recommendations.

- Provide necessary administrative support for the ICS Team in the field.  This support may include staffing of the TROC or support staff to these positions.

- Provide up to four (4) RPFs as Subject Matter Experts, including one Lead and a minimum of three support RPFs, to prepare or direct the preparation of Timber Harvest Plans/Conversion Exemption Permit Applications, one for each of the three (3) sub areas designated by the IMT, as overseen by the State’s RPF Subject Matter Expert (SME).  The three sub-areas are the same as determined for the Government Hazard Tree Removal Program shall be determined by the IMT. The Contractor’s RPFs will also oversee the Tree Removal Contractor (a Licensed Timber Operator (LTO)) or the Tree Removal Contractor’s subcontractor LTO(s) to ensure that the Timber Harvest Plans/Conversion Exemptions are carried out as written and approved by CalFire’s Regional State Forester.

- The Lead RPF shall conduct and/or direct an initial Hazard Tree Windshield Survey along all County and Town Roadways within the Fire Burn Area.

Hazard Tree Windshield Survey (HTWS) - shall consist of evaluating all the hazard trees, sitting on private properties that can fall on public rights-of-way or public structures (buildings, trails, bike paths, schools, etc).  This HTWS will be conducted in the Town of Paradise and within Butte County along public roadways within the Camp fire burn scar footprint. This survey will be conducted from the road or road shoulder. The assessors shall not enter onto private properties to conduct this survey. The surveyors will estimate the number of hazard trees, and provide an estimated diameter, height, and species for each hazard tree included.

Hazard Trees - are trees that meet the FEMA description, namely: “if its condition was caused by the disaster; it is an immediate threat to lives, public health and safety, or improved property; it has a diameter at 4.5 feet above ground level of six inches or greater; and one or more of the following criteria: it has more than 50% of its crown damaged or destroyed, or it is a split trunk, broken branches or exposed heartwood, or it is leaning at an angle greater than 30 degrees.” Or as more precisely described in the CalFire Tree Notes No. 33 for, “Survival of Fire-Injured Conifers in California”, Owen, Cluck, Smith, (April, 2015).

- This HTWS shall be conducted/directed by the Contractor’s Lead RPF, support RPFs and/or an RPF trained TRAQ Arborist. This survey shall be conducted as quickly and accurately as possible (as soon as possible after receiving the notice to proceed) to provide contract information to be included in the Invitation for Bid (IFB) for a Tree Removal Contractor. This survey will include an overall estimated number of hazard trees as well as their diameter, height and type. This survey will include hazard trees that can fall onto the Town or County rights of way (and may include private road rights of way at the discretion of CalRecycle). A tally of the number of trees, by estimated tree diameter (delineations of diameter shall be determined by the RPF), height and species, along each mile of roadway will be tallied and recorded, also to be supplied as part of the IFB. This task shall be completed within four (4) weeks of the contract notice to proceed and submitted to the State RPF and the IMT’s PC and OC.

Timber Harvest Plans/Conversion Exemptions – are as defined in Chapter 4 (Forest Practices), Division 1.5 (Department of Forestry and Fire Protection), Title 14 (Natural Resources), California Code of Regulations.

Hazard Trees - are trees that meet the FEMA description, namely: “if its condition was caused by the disaster; it is an immediate threat to lives, public health and safety, or improved property; it has a diameter at 4.5 feet above ground level of six inches or greater; and one or more of the following criteria: it has more than 50% of its crown damaged or destroyed, or it is a split trunk, broken branches or exposed heartwood, or it is leaning at an angle greater than 30 degrees.” Or as more precisely described in the CalFire Tree Notes No. 33 for, “Survival of Fire-Injured Conifers in California”, Owen, Cluck, Smith, (April, 2015).

- All the RPFs will report to the CalRecycle Operations Chief and the IMT and work cooperatively with each of the sub-Area Deputy Operations Chiefs.

- These RPFs will oversee the timber being harvested within their Timber Harvest Plan/Conversion Exemption areas and make sure that they are properly delineated, marked, and documented, and that the Tree Removal Contractor’s LTO(s) properly and safely cut the previously marked trees, and that they are processed and transported to the disposal sites per the state regulations and per their specific Timber Harvest Plans/Conversion Exemptions.

- These RPFs will work with the Contractor’s Biologists and Archaeologists in preparing the environmental protection aspects of the Timber Harvest Plans/Conversion Exemptions. The RPFs, Biologists, and Archaeologists will also inspect and ensure that the Tree Removal Contractor’s LTO(s) are implementing the Best Management Practices delineated in the Timber Harvest Plans/Conversion Exemptions.

- Provide up to 75-100 40 Certified Arborists/Arborist Technicians, as determined and trained up by the State Forester and the OC, to evaluate trees to be harvested as part of this operation. The Arborist/arborist technician will have the following responsibilities, but are not limited to:

- They shall be trained by the State RPF and Contractor RPFs in delineating how to evaluate hazard trees. Each arborist/arborist technician will receive a training certificate from the State RPF indicating they have received such training and have indicated a clear understanding for evaluating the health and height of trees to be harvested and application of the Timber Harvest Plan/Conversion Exemptions.

- Under the direction of a State RPF, assess trees within the defined public right of way of each private property eligible for tree removal as determined by the IMT for which the State has an approved ROE and mark those trees, as prescribed by the State RPF, that meet the Timber Harvest Plan/Conversion Exemption requirements for selecting hazard trees.

- Arborist/Arborist Technicians shall be accompanied by Task Force Leaders who shall document all of the trees that are marked by the Arborist/Arborist Technicians electronically which must include the number of trees, each tree’s tree type and height (as determined by the Arborist/Arborist Technician), its diameter (at 4.5 feet above ground level), its GPS coordinates, and photographs of each tree. Maps of the trees shall also be prepared and placed in a database folder for each property by APN number and available to the IMT by “Box” or other similar, IMT approved database.

- Provide an adequate number of experienced biologists (including aviary and amphibian specialists) to assist the RPFs in preparing and overseeing the appropriate implementation of each of the Timber Harvest Plans/Conversion Exemptions with respect to the state California Environmental Quality Act (CEQA) and federal National Environmental Policy Act (NEPA) environmental protection requirements, for protection of endangered and impacted species and their habitats under emergency operations.

- Provide an adequate number of experienced archaeologists to assist the RPFs in preparing and overseeing the appropriate implementation of each of the Timber Harvest Plans/Conversion Exemptions with respect to the state California Environmental Quality Act (CEQA) and federal National Environmental Policy Act (NEPA) environmental protection requirements, for preservation of historic structures and artifacts under emergency operations.

- Provide an adequate number of experienced Environmental Unit Leaders and an Environmental Unit Supervisor, to assist the RPFs in preparing and overseeing the appropriate implementation of each of the Timber Harvest Plans/Conversion Exemptions with respect to the state California Environmental Quality Act (CEQA) and federal National Environmental Policy Act (NEPA) environmental protection requirements, for protection of endangered and impacted species and their habitats under emergency operations.

- Provide an Environmental Branch Director/Senior Environmentalist to assist the RPFs in preparing and overseeing the appropriate implementation of each of the Timber Harvest Plans/Conversion Exemptions with respect to the state California Environmental Quality Act (CEQA) and federal National Environmental Policy Act (NEPA) environmental protection requirements, for protection of endangered and impacted species and their habitats under emergency operations.

## Overall Tasks to be Performed

The Contractor shall provide ICS OC, PC, LC and FC staff to lead and/or support the established ICS Team in implementing the technical elements of the Timber Harvest Plan/Conversion Exemptions.  The following is a summary description of the tasks the Contractor shall perform in implementing the Timber Harvest Plan/Conversion Exemptions.  Actual interpretation in implementing the Timber Harvest Plan/Conversion Exemptions is at the discretion of the IMT.

- Prepare a Safe Work Plan for Contractor staff to follow for the services to be provided.

- Contractor Project Manager and IC shall ensure that all Contractor staff are trained by State RPF, CalRecycle OC, CalRecycle H&S professional, and State Environmental SME prior to being sent out for any field work.

- Conduct HTWS (as described previously), under the direction of the State and Contractor RPFs and the IMT, to provide necessary information to the Hazard Tree Removal Contractor’s Invitation for Bid solicitation.

Conduct initial visual survey of roadways and infrastructure along those roads that could potentially be impacted by the debris cleanup operations.  Evaluate pre-operational conditions with video recording and notes collected during the evaluation.  These shall be compared to post-operational evaluation for potential local agency reimbursement by state or federal funding agency.

- Perform Individual Property Assessments for Trees requiring removal under this program:

- Under the direction of the RPF, Arborists/Arborist Technicians will delineate those trees that are determined to be hazardous, and will mark those trees appropriately, as prescribed by the RPF, on each property.

- One Task Force Leader shall be teamed-up with each Arborist/Arborist Technician on each property.

- The Task Force Leader (TFL) shall:

  - Review the Right of Entry (ROE) documentation for the property before any Contractor staff enter the property.  TFL shall communicate any hazards, unusual conditions, or other relevant information reported on the ROE to any other personnel entering the property.

  - Verify that each property, upon arrival, has an address sign installed.

  - If no address sign is installed, the Task Force Leader will install such a sign prior to proceeding onto the property.

  - Observe any overhead utilities and note them in the TFL’s documentation.

  - Identify and document any existing buildings, structures, fences, vehicles, septic tanks, water wells, stream beds, bridges, etc.

  - Identify and document other property-specific hazards (i.e. animals, swimming pools, steep hillsides, large vehicles).

  - Document all of the trees that are marked by the Arborist/Arborist Technician with a FEMA approved Automated Debris Management System (ADMS) device, electronically. Data collected will include:

    - unique identification numbers for all trees,

    - the number of trees (on this property) on a site assessment map,

    - each tree’s tree type (as determined by the Arborist/Arborist Technician),

    - its height,

    - its diameter (at 4.5 feet above ground level),

    - its GPS coordinates, and

    - a photograph of each tree before removal showing the identification number on the tree trunk and a photograph after removal showing the identification number on the remaining stump.

    - The TFL shall also prepare a survey map showing the location of the trees included on the property (The survey map shall include a tree represented as a circle tagged with a tree identification number).

  - Be prepared to mark property boundaries if access to hazard trees that are marked to be cut may require access across such a boundary or if the trees may fall across such boundaries after being cut. Mark this possibility on the site map.

  - Place all above listed information in a database folder for each property by APN number and available to the IMT by “Box” or other similar, IMT approved database.

  - Assist in overseeing the appropriate implementation of each of the Timber Harvest Plans with respect to the state California Environmental Quality Act (CEQA) and federal National Environmental Policy Act (NEPA) environmental protection requirements (BMPs), for protection of endangered and impacted species and their habitats under emergency operations.

  - Task Force Leader (Tower Monitor):

    - Track each truck and estimate the volume in cubic yards of vegetative debris entering and leaving the debris management site.

    - Track each truck and estimate the volume in cubic yards of vegetative debris entering final destination wood waste facilities.

- Conduct Air Monitoring and Surveillance during Tree Removal Operations:

1.	Develop an offsite (community) air monitoring plan for constituents of concern detected during the previous debris removal operation, to the satisfaction of CalRecycle.

2.	Conduct offsite (community) air monitoring consistent with the offsite (community) air monitoring plan, if and as determined by CalRecycle’s and the Contractor’s Health and Safety Officers.

- Health and Safety Considerations:

- Though this project is being conducted after the ash and debris removal operation has been completed, there still may be heavy metals impacted ash in the tree branches and bark. Therefore, dust control such as wetting the ground where the trees are intended to fall (with water from water trucks) prior to start of tree falling and removal and wetting down the trees prior to and during limb/slash chipping operations will be necessary to reduce dust and sawdust releases. The TFL shall be responsible to advise the Tree Removal Contractor about minimizing the release of dust and sawdust from their work areas.

- Protect Storm Water Best Management Practices During Tree Falling and Removal Operations:

- Observe and verify the protection of already installed on-property storm water best management practices (BMPs) such as waddles and compost socks installed to prevent off-site migration of waste into municipal system or nearby waters.

- Document the Tree Removal Contractor’s installation of new stormwater BMPs necessary to meet Timber Harvest Plan requirements and overall operationally required BMPs to minimize both soil erosion and generated sawdust from being carried down to local streambeds.

- Project Completion Documentation:

- Assist CalRecycle staff in completing financial summary information for each property that signed up for the Government Hazard Tree Removal Program in a manner and level of detail acceptable to CalRecycle to document complete project costs.

- Provide adequate management level and administrative staff as required to conduct after action meetings and prepare an after action report for work performed on this project. An after action incident report is critical. After action reports will ensure that lessons learned can be integrated into response operations at future hazard tree removal operations. This process includes: identifying the functions to assess and evaluate, conducting meetings with key personnel to discuss these functions, and developing an after action report or improvement plan to document the lessons learned.  These services are described in more detail as follows:

- Determine Hazard Tree Removal Functions

Using the concepts of the California Standardize Emergency Management System (SEMS) and Incident Command System (ICS), the Contractor shall coordinate with CalRecycle to determine the hazard tree removal-related functions to assess for the after action meeting.

- Conduct After Action Meeting

Once the list of functions is finalized, the Contractor shall conduct a half-day after action meeting with key personnel to discuss the successes and lessons learned from these fire tree removal operations. CalRecycle will coordinate the scheduling, invitations, and office location for the meeting. The Contractor shall facilitate the meeting and provide printed materials. The Contractor shall manage the agenda to ensure there is sufficient time to discuss each tree removal function. During the after action meeting, the Contractor shall use the Cal OES after action meeting template to document areas for improvement and potential improvement actions (i.e. planning, training, personnel, equipment, or facilities).

- Deliver After Action Report

The Contractor shall develop and deliver the after action report that documents the successes and lessons learned from these hazard tree removal operations. The report will provide recommendations to address gaps in the Tree removal-related functions and will include an improvement plan matrix for CalRecycle to track improvement actions.

The final report will include best management practices that have been instituted as a result of the operational standards set forth on this fire. The report shall include a comparison to historical tree removal operations by other state agencies to demonstrate how CalRecycle can improve upon the effectiveness and efficiencies of their tree removal operations.

The Contractor shall conduct meetings to review changes to the report. The Contractor shall make the changes and provide the final version electronically to CalRecycle.

- Prepare draft versions of CalRecycle project administration documents to implement the recommended changes on future hazard tree removal projects.  Example documents that may be amended include, but are not limited to: the Timber Harvest Plan and all of its technical appendices, site completion reports, reports generated by the planning function on the ICS team, project Agreement, project Agreement solicitation documents, and any and all field documentation required for the project administration.

## Roles

The following are CalRecycle’s requirements for the specific roles and responsibilities of the Contractor’s staff in the performance of this Agreement.  All staff conducting work in and around the tree removal cleanup and disposal operations shall be trained in industry specific safety training, prior to commencing work.

- PROJECT MANAGER

The Project Manager is responsible for overseeing the operations of the Contractor’s staff deployed as part of the ICS Team.  This position is not necessarily a full-time position but is dedicated to make sure that the operation has sufficient staff, equipment and materials to complete the work defined by the Incident Command’s IC, OC, PC, LC, FC and CalRecycle’s Contract Manager.

- INCIDENT COMMANDER

The Incident Commander shall be responsible for overseeing the on-site Contractor ICS staff and be full-time in the field.  The Contractor IC selection requires the approval of the CalRecycle FC/Contract Manager and the CalRecycle OC.

- HEALTH AND SAFETY OFFICER

The Health and Safety Officer shall prepare, have reviewed and signed by a Certified Safety Professional (CSP) or Certified Industrial Hygienist (CIH), and be responsible for implementing a program Safe Work Plan covering all Contractor Activities, listed in this scope of work, for the Contractor’s employees and/or the Contractor’s subcontractors, and CalRecycle staff (if requested) at all the hazard tree removal and processing sites. The Health and Safety officer shall also coordinate with the other Safety officers provided by CalRecycle and the Prime Tree Removal Contractor.

The Health and Safety Officer shall be a registered safety professional, CIH or CSP, and have appropriate experience to adequately oversee and/or perform the tasks outlined in the Scope of Services.

- REGISTERED PROFESSIONAL FORESTER

The Registered Professional Foresters (RPFs) shall include a lead RPF and a minimum of three (3) Sub-Area RPFs that together will oversee and help the State and the IMT manage the Tree Removal Contractor and subcontractors to ensure the proper implementation of the Timber Harvest Plans/Conversion Exemptions (THPs/CEs) for each sub-area. The RPFs duties include but are not limited to:

- Preparing and/or overseeing the preparation of the THPs for each subarea.

- Providing the THPs/CEs to the Tree Removal Contractor and/or to the Tree Removal Contractor’s LTO Subcontractor(s) for signature and submitting to the CalFire Regional Forester prior to implementing of the tree harvest operation.

- Once Rights of Entry have been submitted to and approved by the Town of Paradise and/or Butte County, and approved by the CalFire Regional Forester, the Contractor’s Forester and/or their designated Arborist shall assess and mark each property for hazard trees that could fall on public rights of way.

- The RPFs will oversee and direct the Arborists/Arborist Technicians (joined by the TFLs) to oversee that the LTOs prepare for the cutting, processing and removal of property marked hazard trees in such a manner as to protect any personal property and /or utilities in the process.

- OPERATIONS CHIEF

The Operations Chief (OC) is responsible for developing and implementing strategy and tactics to accomplish the incident objectives by directing and/or supervising soil/solids environmental cleanup and/or remediation operations. The OC duties include but are not limited to:

- Is responsible to the Incident Commander for the direct management of all incident-related operational activities.

- Works closely with and supports the IC, the PC, and the RPF in formulating and updating the Timber Harvest Plans that shall be prepared to direct the OC, the RPF, and the Operations Team as to their duties and their responsibilities. The OC is responsible for setting up staging areas from which the hazard tree removal teams shall muster.

- Establishes and directs all tactical objectives for each operational period.

- The OC organizes, assigns, and supervises all the tactical or response resources assigned to the incident. Responsible for setting up the required Divisions and/or Specialty Groups to properly, effectively, and efficiently carry out the hazard tree removal operations.

- Directs the Operations Team who together shall be responsible for all activities focused on reducing the immediate hazard, saving lives and property, establishing situational control, and restoring normal operations.

- The OC will also be responsible for recording and keeping track of all Damage Claims submitted to the IMT, the Town and County, the TFLs, and Contractor IMT. The Damage Claims forms, supplied by the IMT, will include a decision chain that will require signatures or acknowledgements by the TFL, Division Supervisor, Branch Director, Ops Chief, CalRecycle Ops Chief and the Incident Commander. The Contractor shall ensure that each and every Damage Claim form is filled out with the damage description, Ops Chief determination of action to be taken, concurrence by CalRecycle Ops chief and IC and notation that the property owner had been notified for the decision with a signature and date for each action.

- Additionally, if a Staging Area is established, the OC shall manage the Staging Area.

- DEPUTY OPERATIONS CHIEF

The responsibilities of the Deputy Operations Chief includes supporting the OC in collecting information, managing data, coordinating with property owners and local agencies in assisting in the preparation and carrying out of the overall tree removal preparation, operation, and de-mobilization.

- BRANCH DIRECTOR

The Branch Director (as approved by the OC) is responsible to supervise and support all Division Supervisors (responsible for both overseeing their Division Supervisors and supporting their tasks as well as coordinating with the Tree Removal Contractor to address field activities concerns/issues) and to report back to the OC and IC about status or issues/concerns with operations in their purview. The duties for this operation include:

- Fully understand and follow the requirements included in the Timber Harvest Plan that covers their logistical area, provided by the PC and the State Forester;

- Provide and/or verify that the Division Supervisors are properly trained to conduct the work assigned;

- Provide direct supervision of and direction to the Division Supervisors and the work they are conducting;

- Inform the OC of issues or suggestions on how to conduct the operation more efficiently and effectively;

- Provide the necessary health and safety equipment and materials required for the Division Supervisors for the work they are conducting;

- Provide the forms, tools, and communication equipment to keep in contact with the Division Supervisor at all times; and

- Report directly to the OC and be the line of contact between the OC and the Division Supervisors in fulfilling the responsibilities of the Branch as assigned by the OC.

- DIVISION SUPERVISOR

The Division Supervisor (as approved by the OC) is responsible to supervise and support all Task Force Leaders (both responsible for overseeing the Tree Removal Contractor’s Field Activities including recording the trees removed from each property within their logistical area of supervision and working with the Tree Removal Contractor’s Superintendents addressing operational issues) and reporting their status to the Branch Director. The duties for this operation include:

1.	Fully understand and follow the requirements included in the Timber Harvest Plan that covers their logistical area, provided by the PC and the State Forester;

2.	Provide and/or verify that the Task Force Leaders are properly trained to conduct the work assigned;

- Provide direct supervision of and direction to the Task Force Leaders and the work they are conducting;

- Inform the Branch Director of issues or suggestions on how to conduct the operation more efficiently and effectively;

- Provide the necessary health and safety equipment and materials required for the Task Force Leaders for the work they are conducting;

- Provide the forms, tools, and communication equipment to keep in contact with the Supervisor at all times; and

- Report directly to the Branch Director and be the line of contact between the Branch Director and the Task Force Leaders in fulfilling the responsibilities of the Division as assigned by the OC.

- TASK FORCE LEADER

Task Force Leaders shall be selected and assigned by the Contractor’s Project Manager and report directly to and work for the Division Supervisor, the Branch Director, and ultimately the OC.  The Task Force Leaders are responsible for working with the Arborist/Arborist Technician in directing and overseeing tree removal operations at one or more such sites and must be capable of directing and overseeing these operations. The Task Force Leader shall have either at least two (2) years of experience in the Task Force Leader role and/or directing or overseeing tree removal operations at one or more such operations, or an approved equivalent, such as at least three (3) years of experience in overseeing and/or inspecting environmental cleanup and/or remediation operations. The Task Force Leaders shall:

- Read and fully understand the Timber Harvest Plan for the area within which properties that the TFL will be monitoring, prior to monitoring any tree cutting and harvesting;

- The TFL will accompany the A/AT Arborist during their initial property hazard tree assessments. The TFL will document all of the trees that are marked by the A/AT Arborist for placement in a database. The A/AT Arborist will determine the trees in need of removal, tree number identifier (pre-approved by the IMT), its diameter (at 4.5 feet above ground level), its type, its GPS coordinates.  The TFL will then document all of the collected data, electronically, for each property including number, type and diameter of trees on each APN. The A/AT Arborist will prepare a Map of the trees, for each property that will be provided to the TFL so that the TFL can place it with the photos and other recorded information about each tree to be removed in a database folder for each property by APN number and available to the IMT by “Box” or other similar and IMT approved database;

- Bring to each property and fully read, understand, and follow the requirements included in the initial site plan and the ROE for that property from which trees will be cut and harvested;

- Attend daily Incident Operations Chief/Tree Removal Contractor initiated safety meetings to discuss possible personal and community hazards;

- Be responsible to carry out, under the direction of the OC, the Branch Director, and the Division Supervisor, the Timber Harvest Plan requirements for each individual property assigned, and to read and follow the Homeowner’s directions, listed on the signed and County approved Right of Entry (ROE) Forms;

- The Task Force Leaders shall be the Homeowner’s point of contact until the trees on their property have been removed and the property has been cleared by the County;

- Inspect each contractor’s truck supporting work on each property and ensure that they each have a safety check placard, issued by the Contractor’s DOT commercial truck inspector teams.

- Inspect, monitor, photographically track, and document the trees cut and removed from the property by type, size, and number marked on the tree by the Forester/Arborist from each assigned property;

- Provide documentation of trees removed by street, route, and date. This documentation shall be in an Excel format or other formats utilizing a FEMA approved Automated Tree Removal Management System (ATRMS) Survey 123 data collector software including providing their own tablets or other similar electronic type devices;

- Complete and submit to PC and/or any additional governmental agency all documentation that is required for CalRecycle to receive the maximum reimbursement for all covered trees removed and related costs;

- Watch and advise the tree removal crew’s activities if any health and safety or environmental controls and/or activities (i.e. controlling dust, water run-off of burn ash, etc.) should be addressed during the cleanup operation;

- If there are any existing stormwater BMPs (such as wattles, compost socks, hay bales, erosion control netting or other such BMP) on the property, ensuring that they are not disturbed by the tree removal operation;

- Per the Timber Harvest Plan, work with the arborist/arborist technician to be sure that any environmental and/or archaeological BMPs required are in place and noted to the Tree Removal Contractor prior to commencing tree removal operations. The Tree Removal Contractor will not be allowed to work on any property that is not appropriately protected per the THP;

- Fill out and submit daily activity logs per property documenting Contractor labor staff and hours, equipment used, trucks that hauled materials from the property, logging decks or timber end use locations where trees and any processed materials from that property were taken to directly;

- Inspect traffic control devices and procedures for compliance with the site-specific traffic control plan;

- Provide daily oral status reports to the Division Supervisor, the Branch Director, and the OC, or designee, at the end of each day;

- Obtain site clearance/approval from OC once all designated trees have been removed from the property to allow for a final walk through by the OC or designee;

- Coordinate and work cooperatively with the Tree Removal Contractor, the State Forester’s Site Inspection Team, the Operations Team’s and Tree Removal Contractor’s Health and Safety Officers, air sampling consultants (if required), and other Operations Team Members;

- Coordinate and communicate with OC and PC on a regular basis or as needed, including reporting any unresolved issues, concerns, or complications that may be occurring with the Tree Removal Contractor;

- Be present during any Tree cutting and removal activities, and related on-site management, which shall take place from Monday through Saturday, 11 hours per day if safe conditions allow unless otherwise stated by the OC;

- Perform other requests as directed by the OC and/or the PC;

- Task Force Leaders assigned to truck staging area(s), Logging Decks for timber processing, and/or Tree product Disposal Sites will be assigned to logging-in the trucks entering and leaving each Logging Deck and Disposal Site, verifying materials that are in the truck payloads, and verifying the quantity of materials delivered by each truck in a truck tracking system developed with the Division Supervisor, Branch Director, and OC/PC, monitoring the safety stickers and inspection stickers, transportation of the trees; and

- These Truck Staging Area and/or Log Deck TFLs shall also inspect each Contractor’s truck supporting work on each property and ensure that they each have a safety check placard, issued by the Contractor’s DOT commercial truck inspector teams.

- ARBORIST/ARBORIST TECHNICIAN

The Certified Arborists are environmental science trained and degreed professionals experienced and trained in assessing the health of fire-damaged trees and trained by a RPF to assess such trees.  Arborist Technicians are not necessarily degreed but are experienced and trained similarly to Arborists. The Arborist/Arborist Technicians (A/ATs) shall be overseen and directed by one of the RPFs. The responsibilities of the A/ATs Arborists include, but are not limited to the following:

- Each Arborist/Arborist Technician shall receive a training certificate from the RPF indicating they have received such training and have indicated a clear understanding for evaluating the health and height of trees to be harvested.

- Under the direction of an RPF, assess trees threatening the defined public right of way near each property that is eligible for tree removal as determined by the IMT private property for which the State has an approved ROE and mark those trees appropriately, as prescribed by the RPF, that meet the Timber harvest plan requirements for selecting hazard trees. This information will be logged into the Contractor database by the accompanying Task Force Leader and be accessible by the IMT by the next day.

- Arborists/Arborist Technicians shall be accompanied by task force leaders (who will document all of the trees that are marked by the A/AT Arborist for placement in a database). The A/AT Arborist shall determine the trees in need of removal, tree number identifier (pre-approved by the IMT), its diameter (at 4.5 feet above ground level), its type, its height, and its GPS coordinates.  The TFL shall then document all of the collected data, electronically, for each property including number, type and diameter of trees on each APN. The A/AT Arborist shall prepare a Map of the trees, for each property that will be provided to the TFL so that the TFL can place it with the photos and other recorded information about each tree to be removed in a database folder for each property by APN number and available to the IMT by “Box” or other similar and IMT approved database.

- Once the marked trees are cut and cleared off of each property, the A/ATs Arborists shall assess, document, and mark the tree stumps with their original markings (prior to cutting) and take a picture and GPS the stump location. This information shall be logged into the Contractor database by the accompanying Task Force Leader and be accessible by the IMT by the next day.

- Prepare Final Site Tree Removal Reports, one for each property, that summarizes the pre-tree removal and post-tree removal conditions, including; the initial and final assessments, a copy of site’s ROE, a summary of the trees removed from the property, the type of erosion control best management practices conducted on the property (post-tree removal operation, if deemed necessary by the RPF) and an indication of any unique or unexpected circumstances that occurred during the tree removal operations. Each report shall include pictures from both pre- and post-tree removal operations.

- BIOLOGISTS/ARCHAEOLOGISTS

The Senior Biologists and Senior Archaeologists shall help to prepare the Timber Harvest Plan environmental protection supporting documentation assessments as well as recommended environmental/historical best management practices (BMPs) to protect these areas from negative impacts for each Timber Harvest Plan.

Biologists and Archaeologists, trained by the Senior Biologist, Senior Archeologist, and Lead RPF will conduct required assessments and monitor the Tree Removal Contractor’s crews to make sure that they are implementing the THP’s required BMPs.

Some of the Biologists shall be required to have aviary and amphibian specialties to assist in necessary evaluation and protection of species (endangered and otherwise).

- ENVIRONMENTAL UNIT LEADER/AIR QUALITY

The Air Quality Environmental Unit Leader shall oversee the preparation and implementation of an air monitoring plan.  The plan shall include the collection of air monitoring samples assessing for airborne particulate matter and criteria pollutants that may cause health hazards from the previously released structural fire ash that may have been captured by the hazard trees during the fire and subsequent debris removal operations.  Criteria air contaminants are typically emitted from many sources.  The Air Quality teams will typically set up continuous operating monitoring stations at key community sites, that will be checked on throughout the day.  Additionally, the teams will set up 3 continuous air monitoring stations at up to one-third of the hazard tree removal task force teams, which could add up to approximately 33 task forces in need of air monitoring.  All of these air monitoring stations will also need to be checked on throughout the day.

- DATA/PACKET MANAGER

The Data Packet manager shall electronically manage and track all the site documentation including, but not limited to the following; the ROEs, all site documentation, daily activity documentation, trucking documentation, and site data reconciliation with the Tree Removal Contractor. The Data/Packet Manager shall compile documentation for cost tracking and reconciliation.

The Data//Packet Manager shall also make collected data available to the OC, PC, and FC and the entire IMT as requested to help improve the effectiveness and efficiency of the operation.

- PLANNING CHIEF

The Planning Chief (PC) shall oversee the collection, evaluation, and dissemination of operational information related to the incident.  It is the PC’s responsibility to prepare and assist the OC in implementing the THPs, as well as track the status of all incident resources and all the preparations for, data management from, and the final dispositions of each property that has entered into the tree removal program.

- PLANNING ASSISTANT

The responsibilities of the Planning Assistant include supporting the PC in collecting information, managing data, coordinating with property owners and local agencies in assisting in the preparation and carrying out of the overall tree removal preparation, operation, and de-mobilization.

- GIS PROFESSIONAL

The GIS professional shall be responsible for taking all local fire incident information, local agency information, mapping, and infrastructure information and building it into a cohesive database that can be used to assess, coordinate, and summarize all the tree removal activities that have taken place. The database shall be developed by the GIS professional to provide the PC, OC, and FC an easy way to access information that will assist them in performing their duties. This database shall include all daily activity logs, truck tickets, site tree assessments, and closure reports for each participating property, using a CalOES and CalRecycle specified data structure.  The Database shall be based on ESRI software and compatible with CalRecycle’s GIS systems.

- LOGISTICS CHIEF

The Logistics Chief (LC) shall be responsible for supporting the overall tree removal operation by finding and supplying the facilities, utilities, supporting materials, health and safety personal, and protective equipment and other expendables in support of the Operations staff. The LC shall also provide communications devices, computers, tablets, transportation, and anything else needed to support the tree removal efforts.

- FINANCE/ADMINISTRATION CHIEF

The Finance/Administration Chief (FC) is responsible for all of the financial and cost analysis and cost efficiency aspects of the tree removal operations. These include Tree Removal Agreement negotiation (if appropriate), recording or auditing personnel and equipment time, documenting and processing claims for accidents and injuries occurring at the incident, and keeping a running tally of the costs associated with the incident. The FC is also responsible for reviewing and auditing the Tree Removal Contractor’s monthly invoices to make sure that they are accurate, defendable, and reimbursable by the state and federal (if applicable) agencies supplying disaster relief funding.

- The FC shall validate and ensure the preparation of invoices adhere to the following provisions:

- Invoices comply with provisions of purchase orders, sub-purchase orders, contracts, leases, service agreements, grants, etc. This includes ensuring completed work orders, adherence to contract terms and invoicing, and that there is proper authorization and internal control of purchases and assets.

- Items or services invoiced have been received or provided, as evidenced by stock received reports or similar documents or employee verification and is fully documented for audit or other external review.

- Authority exists to obtain the goods or services.

- Payment has not previously been made.

- ACCOUNTING AND ADMINISTRATIVE STAFF RESPONSIBILITIES

Accounting and Administrative staff shall be selected by the Contractor’s Program/Project Manager and report directly to CalRecycle’s Incident Operations Planning Chiefs (PC) and/or Financial Chiefs (FC) supporting the tree cleanup activities. The services to be provided include:

- Early on, work with the Tree Removal Contractor and the CalRecycle FC and/or accounting staff in developing an acceptable method for accounting of billable activities and an agreed upon format for invoices to be submitted to the CalRecycle FC for review and payment;

- Work directly with the FC to track trees removed, hauled, and deposited at final destinations by managing daily work sheets prepared by the TFLs, and collecting and collating truck tickets and destination (landfill, recycle facility, etc.) tickets from each cleanup property on a daily basis;

- Work with the FC in accumulating and tabulating daily quantities removed from each site and in total for the Government Hazard Tree Removal Program;

- Receive, review, and compare contractor invoices with the daily logs and materials disposal tickets for costs expended;

- Evaluate invoices to verify that all costs have been charged per the Agreement approved unit rates;

- Report to the FC any discrepancies between the daily logs, other per lot documentation, and the invoices; and

- Other administrative requests made by either the PC or the FC.

- ENVIRONMENTAL UNIT LEADERS

The Environmental Unit Leaders and supervisors will be responsible for overseeing and supporting the field work conducted by the Biologists and Archaeologists in addressing the environmental requirements of the Timber Harvest Plans.

- ENVIRONMENTAL BRANCH DIRECTOR/SENIOR ENVIRONMENTALIST

Provide an Environmental Branch Director/Senior Environmentalist to assist the RPFs in preparing and overseeing the appropriate implementation of each of the Timber Harvest Plans/Conversion Exemptions with respect to the state California Environmental Quality Act (CEQA) and federal National Environmental Policy Act (NEPA) environmental protection requirements, for protection of endangered and impacted species and their habitats under emergency operations. The Environmental Branch Director/Senior Environmentalist will also be responsible for overseeing and supporting the Environmental Unit Leaders in addressing the environmental requirements of the Timber Harvest Plans.

- ENVIRONMENTAL UNIT LEADER/WATER QUALITY BMPS

Provide an Environmental Unit Leader to assist the RPFs in preparing and overseeing the appropriate implementation of each of the water quality BMPs required in the Timber Harvest Plans/Conversion Exemptions with respect to the state California Environmental Quality Act (CEQA) and federal National Environmental Policy Act (NEPA) environmental protection requirements, for protection of endangered and impacted species and their habitats under emergency operations.

- MISCELLANEOUS POSITIONS/SERVICES

- There may be Tribal Monitoring required on this project under a subcontract to this Agreement.  Tribal monitoring is typically provided by the regional tribe using tribal appointed monitors.  Rates established by the tribe(s) will be the basis for the rates paid to the tribal monitors and is outside of the control of the Contractor.  The Contractor is limited to a ten (10) percent markup on this subcontract.

- The Contractor shall hire independent third-party DOT commercial truck inspector two-person teams. The Contractor shall:

  - Provide certifications and resumes indicating their experience as truck inspectors to the IMT for approval. The inspectors shall have the necessary insurance, qualifications, and expertise to perform a level one inspection for all commercial trucks assigned to the incident. All inspection records, both pass and fail, shall be submitted to the IMT within 24 hours of the inspection.

  - Provide as many such 2-person crews as is determined by the IMT to be necessary to confirm that all trucks pass safety inspections as required by the State Highway Patrol and applicable state and local regulations. The Contractor will placard each and every truck that has been inspected with a unique placard number that can be scanned by TFLs at each property site, log deck processing site, and final disposal site.

  - Inspect all logging trucks, haul trucks, water tenders, tow trucks, street sweepers, low-beds, and other commercially licensed vehicles used on the project. Water trucks used specifically on-site lots are not subject to inspection provided they are not carrying water loads on a public road; these water trucks are considered construction vehicles.

  - Re-inspect 10 percent of all previously certified trucks every 30 days.

- GPS Tracking of Commercial Fleet

The Contractor shall be responsible for installing and monitoring Global Positioning System (GPS) tracking on all haul trucks, street sweepers, and community water tenders. The Contractor shall provide access to the tracking software to the IMT and Tree Removal Contractor.

- The Contractor is required to provide and install property signage, where necessary (signs may already exist), per the following:

  - Depending on the number of ROEs, up to approximately 16,000+ reflective aluminum address signs will be required. The sign dimension should be 6 inches in width and 18 inches in height or length. The edges shall be rounded and free of sharp edges. The background shall be a reflective green and all text shall be reflective white. Each sign shall be mounted on a 6-foot pre-drill, u-channel steel post or other post. The numbering for the address shall be 3 to 4 inches in height. The Contractor shall assemble and install each sign,

  - The Contractor shall post each sign and notify USA 811 before installing.

  - Address sign example (not to scale):

  - CalRecycle will reimburse the Contractor for signage per the proposal cost sheet.  The cost to provide signage shall be paid on a per sign basis and include all sign material, delivery, and installation.

- The Contractor shall hire a Licensed Professional Surveyor to resolve boundary disputes on affected properties.

- There may be a need for the Contractor to provide additional professional services in support of the Government Hazard Tree Removal Program, if requested by CalRecycle.  Any additional services must be approved by the Contract Manager in writing and in accordance with the “Work Authorization” clause of Exhibit D.  All rates must be approved in the Work Authorization document, and shall be reasonable, typical of the industry, and allocable.  If such additional services require subcontracting, the Contractor is limited to a ten (10) percent markup on subcontract costs.

- Change Orders: If the Contractor is directed to perform work outside the Scope of Work of this Agreement or encounters any other situation where it believes an adjustment of costs from the Cost Proposal Sheet is justified, the Contractor must immediately notify the Contract Manager and the IMT of the need for a Change Order. Failure to promptly notify the Contract Manager constitutes a waiver of any claim for additional compensation prior to actual notification to the Contract Manager.

The Contract Manager, in consultation with the IMT, shall notify the Contractor whether to perform or continue the affected work and issue a Change Order if adjustment to the Cost Proposal Sheet costs is necessary. The Contractor shall promptly provide all information requested by the Contract Manager in support of a Change Order. Upon completion, a Change Order shall be attached to this Agreement through the formal amendment process. A Change Order shall specify the effective date of the adjusted costs, but those costs cannot be invoiced at the adjusted rate prior the completion of the amendment. In order to be approved, the Change Order costs must be reasonable, allocable, and typical of the industry, and the Change Order work must be reasonable for the completion of the project scope.

## Weather Delays

In the event that a crew does not work as scheduled due to weather or other delays outside the control of the Contractor, the Contractor shall be compensated for the idle employees based on the hourly rates established on the Cost Proposal Sheet based on the chart below.

For the purposes of this chart, more than or equal to 30 minutes of work shall be considered a full hour of work.  Less than 30 minutes of work will not be considered.

| Hours Actually Worked | Hours to be Paid |
| --- | --- |
| 0 | 3 |
| 1 - 2 | 4 |
| 3 - 4 | 5 |
| 5 | 5.5 |
| 6 + | Actual Hours Worked |

## Location of Services

Services will be provided in Butte County.

## Control of Work

- The CalRecycle Contract Manager has the authority to determine the quality and acceptability of the following:

- Work to be performed;

- Rate and progress of the work;

- Fulfillment of the services provided by the Contractor; and

- Compensation for services provided by the Contractor.

- The Contractor will designate a Project Manager who holds the following authority:

  - Act as the Contractor’s Representative for work to be provided under this Agreement

  - Act as the Contractor’s Representative regarding contractual matters relating to this Agreement

If during the course of the Agreement, it is deemed necessary to replace the Project Manager, CalRecycle’s Contract Manager approval is required prior to the replacement being made.

# Section VII	Definition and Terms

General

Unless the context otherwise requires, wherever in this RFP or addenda, the following abbreviations and terms, or pronouns in place of them, are used, the intent and meaning shall be interpreted as provided in this Section.

Working titles having a masculine gender, such as “draftsman” and “journeyman” and the pronoun “he”, are utilized in these provisions for the sake of brevity and are intended to refer to persons of either sex.

Abbreviations

ADA	Americans with Disabilities Act

CAL EPA	California Environmental Protection Agency

CCR	California Code of Regulations

DVBE	Disabled Veteran Business Enterprise

EPA	Environmental Protection Agency (Federal Government)

GC	Government Code

PCC	Public Contract Code

RFP	Request for Proposals

SB	Small Business

SOW	Scope of Work

OSDS	The Department of General Services (DGS), Procurement Division (PD), Office of Small Business and DVBE Services (OSDS)

Agreement

The written agreement covering performance of the work and furnishing of labor, materials, tools, and equipment in providing the work.  The Agreement shall include the RFP, Proposal, general and specific terms and conditions, Work Orders, and supplemental agreements which may be required to complete the work in a substantial and acceptable manner.

Cal EPA

The California Environmental Protection Agency

CalRecycle Staff

Staff of the Department of Resources Recycling and Recovery involved in the implementation of this contract.

Contract

A legally binding agreement between the state & another entity, public or private, for the provision of goods or services

Contract Manager

A person designated by the responsible state agency or department to manage performance under a contract.

Contractor

A party contracting with the awarding agency.  Vendor is often used synonymously with contractor.

Cost Proposal Opening

A public meeting, where the costs bid by a proposer on an advertised project, are opened and a determination is made as to the apparent low bidder.

Director

The Executive Director of the Department of Resources Recycling and Recovery, or his/her designees.  Any references to Executive Officer shall mean the Executive Director and/or designated officer.

Disabled Veteran Business Enterprise (DVBE Certified)

A business that meets all of the following criteria:  (1) at least 51% of the business is owned by one or more disabled veterans or, in a business whose stock is publicly held, at least 51% or more of the stockholders are disabled veterans (2) the management and control of the business are exercised by one or more disabled veterans; (3) the business is domestically owned and its home office is in the United States; and (4) the business has been certified as a DVBE by the State of California, Department of General Services (DGS), Procurement Division (PD), Office of Small Business and DVBE Services (OSDS).

Legal Holiday

Those days designated as State holidays in the Government Code.

Project Manager

In addition to the responsibilities described in the Description of Work, the Project Manager is the Contractor’s representative for all work performed under this Agreement.  All official correspondence, reports, submittals, billings, and other work done under this Agreement shall be reviewed and signed by the Project Manager prior to submittal to CalRecycle.

Scope of Work

The description of work required of a contractor by the awarding agency.

Small Business (Certified)

A business that has been certified by the Department of General Services (DGS), Procurement Division (PD), Office of Small Business and DVBE Services (OSDS), as a small business as defined in GC 14837 and 2 CCR 1896.

State

The State of California.

State Contract Law

The Public Contract Code and other applicable laws that form and constitute a part of the provisions of this Agreement to the same extent as if set forth herein in full.

Subcontractor

A person or entity which contracts with the Contractor to perform all or a portion of the work as specified in the Scope of Work.

|  | # Attachments |  |
| --- | --- | --- |

## Cost Proposal Sheet

Debris Management for the Camp Fire Tree Removal

DRR19055

Complete this form and submit the original in accordance with the requirements of this RFP.

| Contractor/Company Name: |  |
| --- | --- |

Proposer shall submit hourly rates in the schedule below in a separate, sealed envelope. The hourly rate shall be inclusive of all pre-planned shutdowns, non-working days and holidays, straight time, overtime, and double time labor per day, H&S equipment, cameras, computers, cell phones, navigation devices, vehicle, air fare, per diem, travel, overhead,*** and profit for each hour of work, including overtime, indicating the proposed rates of reimbursement for the project.  Rates do not include lodging.

Note: One Division Supervisor is required for every 5 Task Force Leaders. Actual numbers of personnel will be determined by the IMT’s OC and PC and changed as circumstances require.  It is anticipated that the number of Operations Chiefs, Planning Chiefs, Logistics Chiefs, Division Supervisors, Task Force Leaders, H&S Officers, and other support positions required will be based on the requirement to adequately plan, supervise, and direct the work appropriately, as required by CalRecycle.

| Tree Removal Monitoring Project Management and Environmental oversight cost sheet |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Position Function* |  | Pay Rate per Hour (in dollars) | Quantity of Staff ** (Include all staff in this category) |  | Number of labor hours per day |  | Cost per Day (in dollars) |  |
| Project Manager |  |  | 1 |  | 4 |  | $ |  |
| Incident Commander |  |  | 1 |  | 10 |  | $ |  |
| Health and Safety Officer |  |  | 1 |  | 10 |  | $ |  |
| Operations Chief |  |  | 2 |  | 10 |  | $ |  |
| Deputy Operations Chief |  |  | 2 |  | 10 |  | $ |  |
| Registered Professional Forester |  |  | 4 10 |  | 10 |  | $ |  |
| Certified Arborist |  |  | 20 40 |  | 11 |  | $ |  |
| Arborist Technician |  |  | 55 |  | 11 |  | $ |  |
| Branch Director |  |  | 3 |  | 11 |  | $ |  |
| Division Supervisor |  |  | 15 |  | 11 |  | $ |  |
| Task Force Leader - Removal Sites |  |  | 75 |  | 11 |  | $ |  |
| Professional Land Surveyor |  |  | 2 |  | 4 |  | $ |  |
| Task Force Leader - Materials Receiving Facilities |  |  | 30 |  | 11 |  | $ |  |
| Environmental Unit Supervisor |  |  | 2 |  | 11 |  | $ |  |
| Environmental Unit Leader |  |  | 7 |  | 11 |  | $ |  |
| Environmental Unit Leader/Water Quality BMPs |  |  | 10 |  | 11 |  | $ |  |
| Environmental Unit Leader/Air Quality |  |  | 24 |  | 11 |  | $ |  |
| Environmental Branch Director/Senior Environmentalist |  |  | 1 |  | 11 |  | $ |  |
| Data/Packet Manager |  |  | 4 |  | 11 |  | $ |  |
| Planning Chief |  |  | 2 |  | 11 |  | $ |  |
| Planning Assistant |  |  | 2 |  | 11 |  | $ |  |
| GIS Professional |  |  | 2 |  | 11 |  | $ |  |
| Logistics Chief |  |  | 1 |  | 8 |  | $ |  |
| Financial/Administrative Chief |  |  | 3 |  | 11 |  | $ |  |
| Accounting and Administrative Staff - Field |  |  | 6 |  | 11 |  | $ |  |
| Accounting and Administrative Staff - Office |  |  | 4 |  | 8 |  | $ |  |
| Biologist |  |  | 10 |  | 11 |  | $ |  |
| Archaeologist |  |  | 10 |  | 11 |  | $ |  |
|  |  |  | Personnel Subtotal |  |  |  |  |  |
| Other Costs |  | Cost per Crew day (in dollars) | Quantity |  | Hours per day |  | Cost per Day (in dollars) |  |
| Truck Inspection Crews (DOT Level 1) |  |  | 4 |  | 10 |  | $ |  |
| Other Costs |  | Cost per Unit (in dollars) | Quantity of Units |  | Quantity of Days |  | Cost per Day (in dollars) |  |
| GPS Tracking of Commercial Fleet |  |  | 2,000 |  | 1 |  |  |  |
| Other Costs |  | Cost per Sign (in dollars) | Quantity |  | days |  | Cost per Day (in dollars) |  |
| Property Signage |  |  | 20 |  | 1 |  | $ |  |
| Other Costs |  | Cost per Day | Quantity of Equipment |  | days |  | Cost per Day (in dollars) |  |
|  |  | __ |  |  |  |  |  |
| Air Monitoring Equipment (including continuous monitoring dust trackers and portable electric generator sets and support materials) |  | $________/day | 15 |  | 1 | $ |  |  |
| TOTAL DAILY COST (Personnel and Other costs combined) |  |  |  |  |  | $ |  |  |

*Any other technical or support staff and/or equipment deemed necessary by the CalRecycle Contract Manager but not listed above shall be paid at a negotiated rate that is reasonable, typical of the industry, and allocable and with the written approval of the CalRecycle Contract Manager per the Work Authorization clause of Exhibit D.

**The number of staff placed in the table is for cost comparison purposes only and is not intended to define the staff required to be used as part of this project.

***Overhead includes administrative support, fringe benefits, and home office costs and does not include field costs to support the debris removal operations as directed by the IMT.

| Acknowledgement/Authorization |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| The undersigned acknowledges the submittal of this proposal constitutes an irrevocable offer for a ninety (90) day period for CalRecycle to award an Agreement. Additional acknowledgement is made of receipt of all competitive documents, including Addenda, relating to this Agreement. The undersigned acknowledges that the Proposer has read all of the requirements set forth in CalRecycle documents and will comply with said provisions. The undersigned hereby authorizes and requests any person, firm, agency, or corporation to furnish any information requested by CalRecycle in verification of the recitals comprising this Proposal and also hereby authorizes CalRecycle to contact such persons, firms, etc., in order to obtain information regarding the undersigned. The undersigned acknowledges that there are no potential conflicts of interest, as defined in Public Contract Code (PCC) sections 10410, 10411, and Government Code (GC) section 87100, by the submitting firm and/or any subcontractors listed in the Proposal. |  |  |  |  |  |
| I declare under penalty of perjury that the foregoing is true and correct. |  |  |  |  |  |
| Name & Title of Authorized Representative: |  |  |  |  | Contractor Name: |
| Address: |  |  |  |  | Telephone #: |
| City, State, Zip: |  |  |  |  | Email: |
| Signature of Authorized Representative: |  |  |  |  | Date Signed: |

## Proposal Scoring Sheet

Debris Management for the Camp Fire Tree Removal

DRR19055

| Contractor/Company Name: |  |
| --- | --- |

To advance to the cost opening, the Proposer MUST achieve the minimum score in each scoring category and an overall total score of 17.

- Methodology 				Max 9 points, Min 6 points to qualify

- Soundness of proposed methodology for conducting the Initial Windshield Survey. (0-3 points)

Demonstration of being able to provide the number of TRAQ qualified Certified Arborists, for the ultimate build up.  (0-3 points)

- Overall approach and understanding of problems, issues and required tasks related to the Timber Harvest Plans/Conversion Exemptions Permit Applications. (0-3 points)

- Soundness of proposed methodology of the Staffing Work Plan as described on page 8-9. (0-3 points)

Score: a) ________		b)________		c)________		total:_________

- Qualifications/Resources			Max 9 points, Min 6 points to qualify

- Assigned staff's senior and mid-level staff’s knowledge, educational background, and experience with hazard tree removal operations. (0-3 points)

- Assigned Registered Professional Foresters’, Biologists’, Archaeologists’, and other technical experts’ experience and background in similar projects. (0-3 points)

- Abilities of assigned staff to conduct the necessary research with proficiency and accuracy and without omission and/or proposed training to be conducted to enhance staff capabilities. (0-3 points)

Score: a) ________		b)________		c)________		total:_________

- Past Work References (may be consulted)	Max 6 points, Min 4 points to qualify

- Similarity between previous projects and the project contained in this RFP. (0-3 points)

- The success (including level of completion) of past projects and any related work record. (0-3 points)

Score: a) ________		b)________					total:_________

Overall Total Score (Sum of 1, 2, and 3)				Overall Total:_________

RFP Evaluation System and Rating Factors

- Narrative proposal evaluation/scoring

- Proposals that appear to meet the basic format requirements, initial qualification requirements and contain the required documentation, as evidenced by passing the Stage 1 review, will be submitted to an evaluation committee.  The evaluators will, individually and/or as a team, review, evaluate and numerically score proposals based on the proposal's adequacy, thoroughness, and the degree to which it complies with the RFP requirements.

- CalRecycle will use the following scoring system to assign points.  Following this chart is a list of the considerations that raters may take into account when assigning individual points to a technical proposal.

| Points | Interpretation | General basis for point assignment |
| --- | --- | --- |
| 0 | Inadequate | Proposal response (i.e., content and/or explanation offered) is inadequate or does not meet CalRecycle’s needs/requirements or expectations. The omission(s), flaw(s), or defect(s) are significant and unacceptable. |
| 1 | Barely Adequate | Proposal response (i.e., content and/or explanation offered) is barely adequate or barely meets CalRecycle’s needs/requirements or expectations. The omission(s), flaw(s), or defect(s), are inconsequential and acceptable. |
| 2 | Fully Adequate | Proposal response (i.e., content and/or explanation offered) is fully adequate or fully meets CalRecycle’s needs/requirements or expectations. The omission(s), flaw(s), or defect(s), if any, are inconsequential and acceptable. |
| 3 | Excellent or Outstanding | Proposal response (i.e., content and/or explanation offered) is above average or exceeds CalRecycle’s needs/requirements or expectations. Minimal weaknesses are acceptable. Proposer offers one or more enhancing feature, method, or approach that will enable performance to exceed our basic expectations. |

- In assigning points for individual rating factors, evaluators may consider issues including, but not limited to, the extent to which a proposal response:

- Is lacking information, lacking depth or breadth or lacking significant facts and/or details, and/or

- Is fully developed, comprehensive and has few if any weaknesses, defects or  deficiencies, and/or

- Demonstrates that the Proposer understands CalRecycle’s need's, the services sought, and/or the contractor's responsibilities, and/or

- Illustrates the Proposer's capability to perform all services and meet all scope of work requirements, and/or

- If implemented, will contribute to the achievement of CalRecycle’s goals and objectives, and/or

- Demonstrates the Proposer's capacity, capability and/or commitment to exceed regular service needs (i.e., enhanced features, approaches, or methods; creative or innovative business solutions).

|  |  | ## Bidder Declaration |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| State of California—Department of General Services, Procurement Division GSPD–05–105 (EST 8/09) |  |  |  |  |  | Solicitation Number DRR19055 |  |  |  |
|  |  | BIDDER DECLARATION |  |  |  |  |  |  |  |
| - Prime bidder information (Review attached Bidder Declaration Instructions prior to completion of this form): |  |  |  |  |  |  |  |  |  |
| - Identify current California certification(s) (MB, SB, NVSA, DVBE): or None |  |  |  |  |  |  |  |  |  |
| - Will subcontractors be used for this contract? Yes No (If yes, indicate the distinct element of work your firm will perform in this contract e.g., list the proposed products produced by your firm, state if your firm owns the transportation vehicles that will deliver the products to the State, identify which solicited services your firm will perform, etc.). Use additional sheets, as necessary. |  |  |  |  |  |  |  |  |  |
| - If you are a California certified DVBE: |  |  | (1) Are you a broker or agent? Yes No |  |  |  |  |  |  |
|  |  |  | (2) If the contract includes equipment rental, does your company own at least 51% of the equipment provided in this contract (quantity and value)? Yes No N/A |  |  |  |  |  |  |
| - If no subcontractors will be used, skip to certification below. Otherwise, list all subcontractors for this contract. (Attach additional pages if necessary): |  |  |  |  |  |  |  |  |  |
| Subcontractor Name, Contact Person, Phone Number & Fax Number | Subcontractor Address & Email Address |  |  | CA Certification (MB, SB, DVBE or None) | Work performed or goods provided for this contract |  | Corresponding % of bid price | Good Standing? | 51% Rental? |
| CERTIFICATION: By signing the bid response, I certify under penalty of perjury that the information provided is true and correct |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  | Page _____ of _____ |  |  |

| State of California—Department of General Services, Procurement |  |  |  |
| --- | --- | --- | --- |
| Division GSPD–05–105 (EST 8/09) Instructions | BIDDER DECLARATION Instructions |  |  |
| All prime bidders (the firm submitting the bid) must complete the Bidder Declaration. - Identify all current certifications issued by the State of California. If the prime bidder has no California certification(s), check the line labeled“None”and proceed to Item #2. If the prime bidder possesses one or more of the following certifications, enter the applicable certification(s) on the line: - Microbusiness (MB) - Small Business (SB) - Small Business Nonprofit Veteran Service Agency (SB/NVSA) - Disabled Veteran Business Enterprise (DVBE) - Mark either“Yes”or“No” to identify whether subcontractors will be used for the contract. If the response is “No”, proceed to Item #1.c. If“Yes”, enter on the line the distinct element of work contained in the contract to be performed or the goods to be provided by the prime bidder. Do not include goods or services to be provided by subcontractors. Bidders certified as MB, SB, SB/NVSA, and/or DVBE must provide a commercially useful function as defined in Military and Veterans Code Section 999(e)(2)(A) for DVBEs and Government Code Section 14837(d)(4)(A) for small/microbusinesses. For questions regarding commercially useful function determinations made in conjunction with certification approval, contact the Department of General Services, Procurement Division, Office of Small Business and DVBE Certification (OSDC), OSDC Certification and Compliance Unit via email at: osdchelp@dgs.ca.gov Bids must propose that certified bidders provide a commercially useful function for the resulting contract or the bid will be deemed non-responsive and rejected by the State. For questions regarding the solicitation, contact the procurement official identified in the solicitation. Note:A subcontractor is any person, firm, corporation, or organization contracting to perform part of the prime’s contract. - This item is only to be completed by businesses certified by California as a DVBE. - Declare whether the prime bidder is a broker or agent by marking either“Yes”or“No”. The Military and Veterans Code Section 999.2 (b) defines“broker”or“agent”as a certified DVBE contractor or subcontractor that does not have title, possession, control, and risk of loss of materials, supplies, services, or equipment provided to an awarding department, unless one or more of the disabled veteran owners has at least 51-percent ownership of the quantity and value of the materials, supplies, services, and of each piece of equipment provided under the contract. If bidding rental equipment, mark either“Yes” or“No”to identify if the prime bidder owns at least 51% of the equipment provided (quantity and value). If not bidding rental equipment, mark“N/A”for“not applicable.” __________________________________________________________________________________________ - If no subcontractors are proposed, do not complete the table. Read the certification at the bottom of the form and complete“Page of ”on the form. If subcontractors will be used, complete the table listing all subcontractors. If necessary, attach additional pages and complete the“Page of ”accordingly. |  | - (continued) Column Labels Subcontractor Name, Contact Person, Phone Number & Fax Number—List each element for all subcontractors. Subcontractor Address & Email Address—Enter the address and if available, an Email address. CA Certification (MB, SB, DVBE or None)—If the subcontractor possesses a current State of California certification(s), verify on the OSDC website (www.pd.dgs.ca.gov/smbus) that it is still valid and list all current certifications here. Otherwise, enter“None”. [Note: A SB/NVSA should not be participating as a subcontractor] Work performed or goods provided for this contract—Identify the distinct element of work contained in the contract to be performed or the goods to be provided by each subcontractor. Certified subcontractors must provide a commercially useful function for the contract. (See paragraph 1.b above for code citations regarding the definition of commercially useful function.) If a certified subcontractor is further subcontracting a greater portion of the work or goods provided for the resulting contract than would be expected by normal industry practices, attach a separate sheet of paper explaining the situation. Corresponding % of bid price—Enter the corresponding percentage of the total bid price for the goods and/or services to be provided by each subcontractor. Do not enter a dollar amount. Good Standing?—Provide a response for each subcontractor listed. Enter either“Yes”or“No”to indicate that the prime bidder has verified that the subcontractor(s) is in good standing for all of the following: - Possesses valid license(s) for any license(s) or permits required by the solicitation or by law - If a corporation, the company is qualified to do business in California and designated by the State of California Secretary of State to be in good standing - Possesses valid State of California certification(s) if claiming MB, SB, and/or DVBE status - Is not listed on the OSDC website as ineligible to transact business with the State 51% Rental?—This pertains to the applicability of rental equipment. Based on the following parameters, enter either“N/A” (not applicable),“Yes”or“No”for each subcontractor listed. Enter“N/A”if the: - Subcontractor is NOT a DVBE (regardless of whether or not rental equipment is provided by the subcontractor) or - Subcontractor is NOT providing rental equipment (regardless of whether or not subcontractor is a DVBE) Enter“Yes”if the subcontractor is a California certified DVBE providing rental equipment and the subcontractor owns at least 51% of the rental equipment (quantity and value) it will be providing for the contract. Enter“No”if the subcontractor is a California certified DVBE providing rental equipment but the subcontractor does NOT own at least 51% of the rental equipment (quantity and value) it will be providing. Read the certification at the bottom of the page and complete the “Page of ” accordingly. |  |

.

## Small Business (SB) and Disabled Veteran Business Enterprise (DVBE) Subcontractor Payment Certification

As Contractor of record for the Department of Resources Recycling and Recovery, Contract number ___________________, I certify, in accordance with Government Code 14841 and Military and Veteran Code § 999.5, that pursuant to the terms and conditions of the contract, all payments have been made to the SB or DVBE firm(s) listed below for commodities or services rendered as the SB or DVBE subcontractor(s) of record.   I understand certification must be made to the Department of Resources Recycling and Recovery within 60 days of receiving final payment under this Agreement.   I further understand and acknowledge that falsification of this Certification may result in the imposition of civil or criminal penalties for not less than $2,500 or more than $25,000 for each violation.

Please copy this form to include as many SB or DVBE firms as necessary.  Authorized signatures and information are required on each separately submitted form. Return to: Department of Resources Recycling and Recovery, Contracts Unit- MS 19-A, Attn: SB/DVBE Advocate, P.O. Box 4025, Sacramento, CA 95812-4025

SB/MB/DVBE SUBCONTRACTOR INFORMATION

| Contract Firm Name |  |  |  |
| --- | --- | --- | --- |
| Name of Firm Representative |  |  |  |
| Title |  |  |  |
|  | Phone: Fax: |  |  |
| Firm Address | Street: |  |  |
|  | City: State: Zip: |  |  |
| Contract Number |  |  |  |
| Total Amount Received Under this Contract |  |  | $ Date Final Payment Received: / / |

SB/DVBE SUBCONTRACTOR INFORMATION

| SB/DVBE Subcontractor |  |  | Street Address City State Zip |  |  |  | Amount Paid | Participation Achieved |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  |  |  | % |
|  |  |  |  |  |  |  |  | % |
|  |  |  |  |  |  |  |  | % |
|  |  |  |  |  |  |  |  | % |
| Printed Name |  |  |  | Signature: |  |  |  |  |
| Title: |  |  |  | Report Date: |  |  |  |  |

## Darfur Contracting Act

Pursuant to Public Contract Code section 10478, if a bidder or Proposer currently or within the previous three years has had business activities or other operations outside of the United States, it must certify that it is not a “scrutinized” company as defined in Public Contract Code section 10476.

Therefore, to be eligible to submit a bid or Proposal, please complete only one of the following three paragraphs (via initials for Paragraph # 1 or Paragraph # 2, or via initials and certification for Paragraph # 3):

| 1. |  | We do not currently have, or we have not had within the previous three years, |
| --- | --- | --- |
|  | Initials | business activities or other operations outside of the United States. |
|  |  | OR |
| 2. |  | We are a scrutinized company as defined in Public Contract Code section |
|  | Initials | 10476, but we have received written permission from the Department of General Services (DGS) to submit a bid or Proposal pursuant to Public Contract Code section 10477(b). A copy of the written permission from DGS is included with our bid or Proposal. |
|  |  | OR |
| 3. |  | We currently have, or we have had within the previous three years, business |
|  | Initials + Certification below | activities or other operations outside of the United States, but we certify below that we are not a scrutinized company as defined in Public Contract Code section 10476. |

CERTIFICATION For # 3.

I, the official named below, CERTIFY UNDER PENALTY OF PERJURY that I am duly authorized to legally bind the prospective Proposer/bidder to the clause listed above in # 3.  This certification is made under the laws of the State of California.

| Proposer/Bidder Firm Name (Printed) |  | Federal ID Number |  |
| --- | --- | --- | --- |
| By (Authorized Signature) |  |  |  |
| Printed Name and Title of Person Signing |  |  |  |
| Date Executed | Executed in the County and State of |  |

YOUR BID OR PROPOSAL WILL BE DISQUALIFIED UNLESS YOUR BID OR PROPOSAL INCLUDES THIS FORM WITH EITHER PARAGRAPH # 1 OR # 2 INITIALED OR PARAGRAPH # 3 INITIALED AND CERTIFIED.

## Iran Contracting Act

Public Contract Code Sections 2202-2208

Prior to bidding on, submitting a proposal or executing a contract or renewal for a State of California contract for goods or services of $1,000,000 or more, a vendor must either:  a) certify it is not on the current list of persons engaged in investment activities in Iran created by the California Department of General Services (“DGS”) pursuant to Public Contract Code section 2203(b) and is not a financial institution extending twenty million dollars ($20,000,000) or more in credit to another person, for 45 days or more, if that other person will use the credit to provide goods or services in the energy sector in Iran and is identified on the current list of persons engaged in investment activities in Iran created by DGS; or b) demonstrate it has been exempted from the certification requirement for that solicitation or contract pursuant to Public Contract Code section 2203(c) or (d).

To comply with this requirement, please insert your vendor or financial institution name and Federal ID Number (if available) and complete one of the options below. Please note: California law establishes penalties for providing false certifications, including civil penalties equal to the greater of $250,000 or twice the amount of the contract for which the false certification was made; contract termination; and three-year ineligibility to bid on contracts. (Public Contract Code section 2205.)

OPTION #1 – CERTIFICATION

I, the official named below, certify I am duly authorized to execute this certification on behalf of the vendor/financial institution identified below, and the vendor/financial institution identified below is not on the current list of persons engaged in investment activities in Iran created by DGS and is not a financial institution extending twenty million dollars ($20,000,000) or more in credit to another person/vendor, for 45 days or more, if that other person/vendor will use the credit to provide goods or services in the energy sector in Iran and is identified on the current list of persons engaged in investment activities in Iran created by DGS.

| Vendor Name/Financial Institution (Printed) |  | Federal ID Number (or n/a) |
| --- | --- | --- |
| By (Authorized Signature) |  |  |
| Printed Name and Title of Person Signing |  |  |
| Date Executed | Executed in |  |

OPTION #2 – EXEMPTION

Pursuant to Public Contract Code sections 2203(c) and (d), a public entity may permit a vendor/ financial institution engaged in investment activities in Iran, on a case-by-case basis, to be eligible for, or to bid on, submit a proposal for, or enters into or renews, a contract for goods and services.  If you have obtained an exemption from the certification requirement under the Iran Contracting Act, please fill out the information below, and attach documentation demonstrating the exemption approval.

| Vendor Name/Financial Institution (Printed) |  | Federal ID Number (or n/a) |
| --- | --- | --- |
| By (Authorized Signature) |  |  |
| Printed Name and Title of Person Signing | Date Executed |  |

## California Civil Rights Laws Certification

Pursuant to Public Contract Code section 2010, if a bidder or proposer executes or renews a contract over $100,000 on or after January 1, 2017, the bidder or proposer hereby certifies compliance with the following:

1.  CALIFORNIA CIVIL RIGHTS LAWS:  For contracts over $100,000 executed or renewed after January 1, 2017, the contractor certifies compliance with the Unruh Civil Rights Act (Section 51 of the Civil Code) and the Fair Employment and Housing Act (Section 12960 of the Government Code); and

2.  EMPLOYER DISCRIMINATORY POLICIES: For contracts over $100,000 executed or renewed after January 1, 2017, if a Contractor has an internal policy against a sovereign nation or peoples recognized by the United States government, the Contractor certifies that such policies are not used in violation of the Unruh Civil Rights Act (Section 51 of the Civil Code) or the Fair Employment and Housing Act (Section 12960 of the Government Code).

CERTIFICATION

| I, the official named below, certify under penalty of perjury under the laws of the State of California that the foregoing is true and correct. Proposer/Bidder Firm Name (Printed) |  | Federal ID Number |
| --- | --- | --- |
| By (Authorized Signature) |  |  |
| Printed Name and Title of Person Signing |  |  |
| Date Executed | Executed in the County and State of |  |

## Contractor Status Form

| Contractor’s Name: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | County: |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Address: |  |  |  |  |  |  |  |  |  |  |  | Phone Number: |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Fax Number: |  |  |  |  |  |  |  |  |  |  |  |
| Federal Employer Identification Number: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| STATUS OF CONTRACTOR PROPOSING TO DO BUSINESS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Individual Limited Partnership General Partnership Corporation Other |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| If Individual or sole proprietorship, state the true name of sole proprietor: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| If a Limited or General Partnership, list each partner and state their true name and interest in the partnership: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| If a Corporation, state place and date of incorporation: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| President: |  |  |  |  |  |  | Vice President: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Secretary: |  |  |  |  |  |  |  |  |  |  | Treasurer: |  |  |  |  |  |  |  |  |  |  |  |  |
| Other Officer: |  |  |  |  |  |  |  |  |  | Other Officer: |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Provide explanation if claiming Other: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| SMALL BUSINESS PREFERECE |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Are you claiming preference for small/micro business? |  |  |  |  |  | YES – Attach approval letter from Office of Small Business Certification and Resources NO |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Are you claiming preference for DVBE? |  |  |  |  |  | YES – Attach approval letter from Office of Small Business Certification and Resources NO |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| NOTE: THIS FORM MUST BE COMPLETED OR YOUR BID MAY BE REJECTED |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

## Client References

List at least three (3) client references that can attest to the Bidder’s qualifications to fulfill the requirements of the Scope of Work.  List the most recent first.  Client references must also be provided for any subcontractors identified in the Bidder’s response.  Duplicate and attach additional pages as necessary.

| BIDDER / SUBCONTRACTOR’S NAME: |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| REFERENCE 1 |  |  |  |  |  |
| Name of Firm |  |  |  |  |  |
| Street Address | City |  |  | State | Zip Code |
| Contact Person |  | Telephone Number |  |  |  |
| Dates of Service |  |  | Cost of Service |  |  |
| Brief Description of Service Provided |  |  |  |  |  |
| REFERENCE 2 |  |  |  |  |  |
| Name of Firm |  |  |  |  |  |
| Street Address | City |  |  | State | Zip Code |
| Contact Person |  | Telephone Number |  |  |  |
| Dates of Service |  |  | Cost of Service |  |  |
| Brief Description of Service Provided |  |  |  |  |  |
| REFERENCE 3 |  |  |  |  |  |
| Name of Firm |  |  |  |  |  |
| Street Address | City |  |  | State | Zip Code |
| Contact Person |  | Telephone Number |  |  |  |
| Dates of Service |  |  | Cost of Service |  |  |
| Brief Description of Service Provided |  |  |  |  |  |
| If three references cannot be provided, explain why: |  |  |  |  |  |

| STATE OF CALIFORNIA - DEPARTMENT OF GENERAL SERVICES |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| STANDARD AGREEMENT |  |  |  | AGREEMENT NUMBER |  |  | PURCHASING AUTHORITY NUMBER (If Applicable) |  |  |  |  |
| STD 213 (Rev. 03/2019) |  |  |  | DRR19055 |  |  |  |  |  |  |  |
| 1. This Agreement is entered into between the Contracting Agency and the Contractor named below: |  |  |  |  |  |  |  |  |  |  |  |
| CONTRACTING AGENCY NAME |  |  |  |  |  |  |  |  |  |  |  |
| Department of Resources Recycling and Recovery (CalRecycle) |  |  |  |  |  |  |  |  |  |  |  |
| CONTRACTOR NAME |  |  |  |  |  |  |  |  |  |  |  |
| TBD |  |  |  |  |  |  |  |  |  |  |  |
| 2. The term of this Agreement is: |  |  |  |  |  |  |  |  |  |  |  |
| START DATE |  |  |  |  |  |  |  |  |  |  |  |
| TBD |  |  |  |  |  |  |  |  |  |  |  |
| THROUGH END DATE |  |  |  |  |  |  |  |  |  |  |  |
| January 30, 2021 |  |  |  |  |  |  |  |  |  |  |  |
| 3. The maximum amount of this Agreement is: |  |  |  |  |  |  |  |  |  |  |  |
| ( dollars and zero cents) |  |  |  |  |  |  |  |  |  |  |  |
| 4. The parties agree to comply with the terms and conditions of the following exhibits, which are by this reference made a part of the Agreement. |  |  |  |  |  |  |  |  |  |  |  |
| EXHIBITS |  | TITLE |  |  |  |  |  |  | PAGES |  |  |
|  | Exhibit A | Scope of Work |  |  |  |  |  |  |  |  |  |
|  | Exhibit B | Budget Detail and Payment Provisions |  |  |  |  |  |  | 2 |  |  |
|  | Exhibit C* | General Terms and Conditions GTC 04/2017 |  |  |  |  |  |  |  |  |  |
| Exhibit D |  | Special Terms and Conditions |  |  |  |  |  |  | 5 |  |  |
|  |  | Attachment 1 Recycled Content Certification |  |  |  |  |  |  | 2 |  |  |
| Exhibit E** |  | Request for Proposal, DRR19055 |  |  |  |  |  |  |  |  |  |
| Exhibit F** |  | from company name in response to Request For Proposal, DRR19055 |  |  |  |  |  |  |  |  |  |
| Exhibit G |  | FEMA Public Assistance Program Contract Clauses |  |  |  |  |  |  | 6 |  |  |
|  |  | Items shown with double Asterisks (**) are hereby incorporated by reference and made part of this agreement as if attached hereto. |  |  |  |  |  |  |  |  |  |
| Items shown with an asterisk (*), are hereby incorporated by reference and made part of this agreement as if attached hereto. These documents can be viewed at https://www.dgs.ca.gov/OLS/Resources |  |  |  |  |  |  |  |  |  |  |  |
| IN WITNESS WHEREOF, THIS AGREEMENT HAS BEEN EXECUTED BY THE PARTIES HERETO. |  |  |  |  |  |  |  |  |  |  |  |
| CONTRACTOR |  |  |  |  |  |  |  |  |  |  |  |
| CONTRACTOR NAME (if other than an individual, state whether a corporation, partnership, etc.) |  |  |  |  |  |  |  |  |  |  |  |
| TBD |  |  |  |  |  |  |  |  |  |  |  |
| CONTRACTOR BUSINESS ADDRESS |  |  |  |  | CITY |  |  | STATE |  | ZIP |  |  |
| PRINTED NAME OF PERSON SIGNING |  |  |  |  | TITLE |  |  |  |  |  |  |  |
| CONTRACTOR AUTHORIZED SIGNATURE |  |  |  |  | DATE SIGNED |  |  |  |  |  |  |  |
| STATE OF CALIFORNIA |  |  |  |  |  |  |  |  |  |  |  |  |
| CONTRACTING AGENCY NAME |  |  |  |  |  |  |  |  |  |  |  |  |
| Department of Resources Recycling and Recovery |  |  |  |  |  |  |  |  |  |  |  |  |
| CONTRACTING AGENCY ADDRESS |  |  |  |  | CITY |  |  | STATE |  | ZIP |  |  |
| 1001 “I” Street |  |  |  |  | Sacramento |  |  | CA |  | 95814 |  |  |
| PRINTED NAME OF PERSON SIGNING |  |  |  |  | TITLE |  |  |  |  |  |  |  |
| Noah Valadez |  |  |  |  | Administrative Services Branch Chief |  |  |  |  |  |  |  |
| CONTRACTING AGENCY AUTHORIZED SIGNATURE |  |  |  |  | DATE SIGNED |  |  |  |  |  |  |  |

## DRAFT Standard Agreement (STD 213)

| STATE OF CALIFORNIA - DEPARTMENT OF GENERAL SERVICES |  |  |  |
| --- | --- | --- | --- |
| STANDARD AGREEMENT | AGREEMENT NUMBER |  | PURCHASING AUTHORITY NUMBER (If Applicable) |
| STD 213 (Rev. 03/2019) | DRR19055 |  |  |
| CALIFORNIA DEPARTMENT OF GENERAL SERVICES APPROVAL |  | EXEMPTION (If Applicable) |  |
|  |  | Governor’s Emerg. Proc. (dated 11-8-19) |  |

EXHIBIT A

SCOPE OF WORK

- TBD (Contractor) agrees to provide the Department of Resources Recycling and Recovery (CalRecycle), with emergency debris management services as described herein:

- The Project Coordinators during the term of this Agreement will be:

| CalRecycle Contract Manager |  |  | <<Contractor>> |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Name: |  | TBD |  |  | Name: |  |  | <<Contractor Project Manager>> |  |  |
| Phone: |  | (916) |  |  | Phone: |  |  | (XXX) XXX-XXXX |  |  |
| Fax: | (916) |  |  | Fax: |  |  | (916) XXX-XXXX |  |  |
| Email: |  | @calrecycle.ca.gov |  |  | Email: |  |  | <<Contact Name>>@<<Contractor>> |  |  |
| Direct all agreement inquiries to: |  |  |  |  |  |  |  |  |
| CalRecycle Contract Analyst |  |  | <<Contractor>> |  |  |  |  |  |
| Contracts Unit |  |  |  |  |  |  |  |  |
| Attention: |  | TBD | Attention: |  |  | <<Contractor Contact Name>> |  |  |
| Address: |  | 1001 I St., MS 19-A | Address: |  |  | <<Contractor Street Address |  |  |
|  |  | Sacramento, CA 95814 |  |  |  | <<Contractor City, ST, zip>> |  |  |
| Phone: |  | (916) 341- | Phone: |  |  | (XXX) XXX-XXXX |  |  |
| Fax: |  | (916) 319- | Fax: |  |  | (XXX) XXX-XXXX |  |  |
| Email: |  | @calrecycle.ca.gov | Email: |  |  | <<Contact Name>>@<<Contractor>> |  |  |

Background

The Camp Fire has impacted Butte County.  To date, it is estimated that over 300,000 trees were damaged in Butte County that require removal.  This Contract will provide administrative and technical support services for this project.  The anticipated duration of this project is approximately one year for hazard tree removal.

The Contractor shall provide professional hazard tree removal management services related to the tree removal in Butte County as well as assist CalRecycle in the coordination, documentation, and related efforts necessary to coordinate with county, state and possibly federal agencies and document tree marking, removal, processing and disposal.  Services may include support services in other Northern California counties.

- Work to be Performed

The Contractor shall perform all tree removal management services and reporting as required to manage the tree removal services in support of the Incident Commander (IC) including providing Planning, Logistics, Operations, and Finance/Administrative services, as directed by the CalRecycle Contract Manager.  Through Work Orders, CalRecycle will direct the Contractor when and where these services are necessary.  Typical tasks to be performed under this Agreement shall include, but are not limited to:

- Provide up to two Planning Chiefs (PC), per the Incident Command System (ICS) model as directed by the IC, who shall work cooperatively in support of the IC and the incident requirements as defined by the IC, California Governor’s Office of Emergency Services (Cal OES), and the CalRecycle Contract Manager. CalRecycle may use the Contractor’s PC as support to CalRecycle’s own PC but requires the Contractor’s PC to be fully qualified to assist and even take over the role on an as-needed basis. The Planning Team shall perform (but not be limited to) the following tasks:

- Work with the IC, and the Operations and Logistics Chiefs, to support CalRecycle and the RPFs in preparing the Timber Harvest Plans/Conversion Exemptions, if and as necessary.  The implementation of that plan will be conducted as the individual properties become available, based on the Town and/or County’s approval of Rights of Entry (ROEs), and as directed by the CalRecycle Planning Chief. The CalRecycle Planning Chief will control the work under this Agreement, and Work Orders will be issued as properties become available.

- Assist CalRecycle Planning Chief in assigning Contractor Registered Professional Foresters (RPFs) and their Certified Arborists/Arborist Technicians to properties for delineating and documenting trees that are deemed hazardous.

- Provide necessary support staff, including at least one full-time Geographic Information Systems (GIS) experienced and proficient professional who shall incorporate all necessary property data necessary to track the cleanup of each participating property.

- Provide up to two Operations Chiefs (OC), per the ICS model, as directed by the IC. These OCs shall work cooperatively in support of the IC and the incident requirements, as defined by the IC, State OC, and the CalRecycle Contract Manager. The OC shall head up an Operations Team that shall provide all necessary support staff including Division Supervisors and Task Force Leaders to oversee the actual cleanup activities by the Tree Removal Contractor(s) (under separate Agreement to CalRecycle). CalRecycle will likely use the Contractor’s OC as support to CalRecycle’s own OC but requires the Contractor’s OC to be fully qualified to assist and even take over the role on an as-needed basis. The Operations Team shall perform (but not be limited to) the following services:

- Tree Removal oversight, including but not limited to, documenting the cutting and removal of RPF designated hazard trees, located on properties that are eligible for tree removal as determined by the IMT and private properties that could fall on public rights of way or public facilities, as determined by the RPF and addressed in the Timber Harvest Plan/Conversion Exemptions. Cut trees, processed slash and limbs, and chipped trees shall be handled separately. Cut trees, processed slash and limbs, and chipped trees shall be tracked separately (material quantities and costs) all the way to the Logging Decks. Logging Decks are where trees will be processed, prior to taking them to the Materials Receiving Facilities. The processed tree waste will also be tracked to the Materials Receiving Facilities (i.e., lumber mills, biomass burning facilities, etc.) to meet the overall objectives of this project and to track costs. The Contractor shall develop the form and format of the daily reports to the satisfaction of CalRecycle, to be consistent with Federal Emergency Management Agency (FEMA) standards and style for electronic monitoring reports, with input from CalRecycle staff.

- Assist the Tree Removal Contractor(s) in arranging for efficient coordination of trucks designated for the removal of trees and processed vegetative materials. Assist the Tree Removal Contractor(s) in arranging for efficient coordination of water trucks for dust control.

- Provide Hazard Tree Evaluation Teams to conduct Initial Site Reconnaissance, as directed by the IMT’s State Forester and the State’s OC. Also conduct hazard tree evaluations of each property in the program. These teams shall also be responsible for any post-tree cutting and removal confirmation and site condition evaluations.

- Be responsible for the preparation of an ICS Team and Tree Removal Operation Health and Safety Plan (HSP), signed by a certified health and safety professional. The HSP shall designate a project Health and Safety Officer for the Contractor’s employees and/or subcontractors. The Contractor shall submit a draft copy of the health and safety plan to CalRecycle’s designated agent upon execution of this Agreement for review and comment. The Contractor shall designate, in writing, the individuals responsible for initiating, maintaining, and supervising all safety precautions and programs in connection with the work to be performed for the duration of this Agreement. The Contractor shall be responsible for the health and safety of its workforce and shall comply with all State and Federal Occupational Safety and Health Administration (OSHA) requirements. CalRecycle may handle this task with in-house resources and will coordinate as to who performs this task.

- Provide one Logistics Chiefs (LC), per the ICS model, as directed by the IC. The LC shall work in support of the IC and the incident requirements as defined by the IC, Cal OES and the CalRecycle Contract Manager. CalRecycle will likely use the Contractor’s LC as support to CalRecycle’s own LC but requires the Contractor’s LC to be fully qualified to assist and even take over the role on an as-needed basis. The LC and the Logistics Team shall provide (but not be limited to) the following services:

- Provide coordination with the tree disposal site owners and/or operators.

- Provide and/or coordinate with the Tree Removal Contractor(s) the means of communication among field crews, Operations Team members, Planning Team members, and the IC, as required.

- Provide coordination with the Tree Removal Contractor for a workspace and support services for the Tree Removal Operations Center (TROC).

- Coordinate with IC, OC, PC, Finance Chief, the Health and Safety Officer, and the Tree Removal Contractor to provide support services to the other Teams to be able to complete their defined tasks.

- The LC shall coordinate closely with the Tree Removal Contractor in providing these sustaining goods and services efficiently and effectively to both sets of staff.

- Provide at least one Finance/Administration Chief (FC), per the ICS model as directed by the IC. The FC will work cooperatively in support of the IC and the incident requirements as defined by the IC, Cal OES and the CalRecycle Contract Manager. CalRecycle will likely use the Contractor’s FC as support to CalRecycle’s own FC but requires the Contractor’s FC to be fully qualified to assist and even take over the role on as as-needed basis. The Finance/Administrative Team may be required to provide (but not be limited to) the following services:

- Prepare or support CalRecycle staff in the solicitation of the Tree Removal Contractor(s) Agreement.

- Support CalRecycle staff in the oversight and implementation of the Tree Removal Contractor(s) Agreement.

- Assist CalRecycle staff in setting up the Tree Removal Contractor(s) and their subcontractor’s invoice requirements to provide ease of invoice review and cost tracking of tree removal operations conducted per site cleaned up as part of the Government Hazard Tree Removal Program, to best meet the needs of CalRecycle and Cal OES for ease of state and/or Federal (if applicable) reimbursement.

- Assist CalRecycle staff in the review and processing of invoices for payment.  This support may take place in the TROC office in the field, or at CalRecycle’s offices in Sacramento.

- Assist CalRecycle in assembling and assessing Agreement correspondence.  This includes assistance in responding to the contractor’s requests for information, notices of potential claims, and claims review, assessment, and recommendations.

- Provide necessary administrative support for the ICS Team in the field.  This support may include staffing of the TROC or support staff to these positions.

- Provide up to four (4) RPFs as Subject Matter Experts, including one Lead and a minimum of three support RPFs, to prepare or direct the preparation of Timber Harvest Plans/Conversion Exemptions Permit Application(s), one for each of the three (3) sub areas designated by the IMT, as overseen by the State’s RPF Subject Matter Expert (SME).  The three sub-areas are the same as determined for the Government Hazard Tree Removal Program shall be determined by the IMT. The Contractor’s RPFs shall also oversee the Tree Removal Contractor (a Licensed Timber Operator (LTO)) or the Tree Removal Contractor’s subcontractor LTO(s) to ensure that the Timber Harvest Plans/Conversion Exemptions are carried out as written and approved by CalFire’s Regional State Forester.

- The Lead RPF shall conduct and/or direct an initial Hazard Tree Windshield Survey along all County and Town Roadways within the Fire Burn Area.

Hazard Tree Windshield Survey (HTWS) - shall consist of evaluating all the hazard trees, sitting on private properties that can fall on public rights-of-way or public structures (buildings, trails, bike paths, schools, etc.).  This HTWS will be conducted in the Town of Paradise and within Butte County along public roadways within the Camp fire burn scar footprint. This survey will be conducted from the road or road shoulder. The assessors shall not enter onto private properties to conduct this survey. The surveyors will estimate the number of hazard trees, and provide an estimated diameter, height, and species for each hazard tree included.

Hazard Trees - are trees that meet the FEMA description, namely: “if its condition was caused by the disaster; it is an immediate threat to lives, public health and safety, or improved property; it has a diameter at 4.5 feet above ground level of six inches or greater; and one or more of the following criteria: it has more than 50% of its crown damaged or destroyed, or it is a split trunk, broken branches or exposed heartwood, or it is leaning at an angle greater than 30 degrees.” Or as more precisely described in the CalFire Tree Notes No. 33 for, “Survival of Fire-Injured Conifers in California”, Owen, Cluck, Smith, (April, 2015).

- This HTWS shall be conducted/directed by the Contractor’s Lead RPF, support RPFs and/or an RPF trained TRAQ Arborist. This survey shall be conducted as quickly and accurately as possible (as soon as possible after receiving the notice to proceed) to provide contract information to be included in the Invitation for Bid (IFB) for a Tree Removal Contractor. This survey will include an overall estimated number of hazard trees as well as their diameter, height and type.  This survey will include hazard trees that can fall onto the Town or County rights of way (and may include private road rights of way at the discretion of CalRecycle). A tally of the number of trees, by estimated tree diameter (delineations of diameter shall be determined by the RPF), height and species, along each mile of roadway will be tallied and recorded, also to be supplied as part of the IFB. This task shall be completed within four (4) weeks of the contract notice to proceed and submitted to the State RPF and the IMT’s PC and OC.

Timber Harvest Plans/Conversion Exemptions – as are as defined in Chapter 4 (Forest Practices), Division 1.5 (Department of Forestry and Fire Protection), Title 14 (Natural Resources), California Code of Regulations.

Hazard Trees - are trees that meet the FEMA description, namely: “if its condition was caused by the disaster; it is an immediate threat to lives, public health and safety, or improved property; it has a diameter at 4.5 feet above ground level of six inches or greater; and one or more of the following criteria: it has more than 50% of its crown damaged or destroyed, or it is a split trunk, broken branches or exposed heartwood, or it is leaning at an angle greater than 30 degrees.” Or as more precisely described in the CalFire Tree Notes No. 33 for, “Survival of Fire-Injured Conifers in California”, Owen, Cluck, Smith, (April, 2015).

    - All the RPFs shall report to the CalRecycle Operations Chief and the IMT and work cooperatively with each of the sub-Area Deputy Operations Chiefs.

2.	These RPFs shall oversee the timber being harvested within their Timber Harvest Plan/Conversion Exemption areas and make sure that they are properly delineated, marked, and documented, and that the Tree Removal Contractor’s LTO(s) properly and safely cut the previously marked trees, and that they are processed and transported to the disposal sites per the state regulations and per their specific Timber Harvest Plans/Conversion Exemptions.

- These RPFs shall work with the Contractor’s Biologists and Archaeologists in preparing the environmental protection aspects of the Timber Harvest Plans/Conversion Exemptions. The RPFs, Biologists, and Archaeologists will also inspect and ensure that the Tree Removal Contractor’s LTO(s) are implementing the Best Management Practices delineated in the Timber Harvest Plans/Conversion Exemptions.

- Provide up to 75-100 40 Certified Arborists/Arborist Technicians, as determined and trained up by the State Forester and the OC, to evaluate trees to be harvested as part of this operation. The Arborist/Arborist Technician shall have the following responsibilities, but are not limited to:

- They shall be trained by the State RPF and Contractor RPFs in delineating how to evaluate hazard trees. Each Arborist/Arborist Technician will receive a training certificate from the State RPF indicating they have received such training and have indicated a clear understanding for evaluating the health and height of trees to be harvested and application of the Timber Harvest Plan/Conversion Exemptions.

- Under the direction of a State RPF, assess trees within the defined public right of way of each private property eligible for tree removal as determined by the IMT private property for which the State has an approved ROE and mark those trees, as prescribed by the State RPF, that meet the Timber Harvest Plan/Conversion Exemption requirements for selecting hazard trees.

- Arborist/arborist technicians shall be accompanied by Task Force Leaders who shall document all of the trees that are marked by the Arborist/Arborist Technicians electronically which shall include the number of trees, each tree’s tree type and height (as determined by the Arborist/Arborist Technician), its diameter (at 4.5 feet above ground level), its GPS coordinates, and photographs of each tree. Maps of the trees shall also be prepared and placed in a database folder for each property by APN number and available to the IMT by “Box” or other similar, IMT approved database.

- Provide an adequate number of experienced Biologists (including aviary and amphibian specialists) to assist the RPFs in preparing and overseeing the appropriate implementation of each of the Timber Harvest Plans/Conversion Exemptions with respect to the state California Environmental Quality Act (CEQA) and federal National Environmental Policy Act (NEPA) environmental protection requirements, for protection of endangered and impacted species and their habitats under emergency operations.

- Provide an adequate number of experienced Archaeologists to assist the RPFs in preparing and overseeing the appropriate implementation of each of the Timber Harvest Plans/Conversion Exemptions with respect to the state California Environmental Quality Act (CEQA) and federal National Environmental Policy Act (NEPA) environmental protection requirements, for preservation of historic structures and artifacts under emergency operations.

- Provide an adequate number of experienced Environmental Unit Leaders and an Environmental Unit Supervisor, to assist the RPFs in preparing and overseeing the appropriate implementation of each of the Timber Harvest Plans/Conversion Exemptions with respect to the state California Environmental Quality Act (CEQA) and federal National Environmental Policy Act (NEPA) environmental protection requirements, for protection of endangered and impacted species and their habitats under emergency operations.

- Provide an Environmental Branch Director/Senior Environmentalist to assist the RPFs in preparing and overseeing the appropriate implementation of each of the Timber Harvest Plans/Conversion Exemptions with respect to the state California Environmental Quality Act (CEQA) and federal National Environmental Policy Act (NEPA) environmental protection requirements, for protection of endangered and impacted species and their habitats under emergency operations.

Overall Tasks to be Performed

The Contractor shall provide ICS OC, PC, LC and FC staff to lead and/or support the established ICS Team in implementing the technical elements of the Timber Harvest Plan/Conversion Exemptions.  The following is a summary description of the tasks the Contractor shall perform in implementing the Timber Harvest Plan/Conversion Exemptions.  Actual interpretation in implementing the Timber Harvest Plan/Conversion Exemptions is at the discretion of the IMT.

- Prepare a Safe Work Plan for Contractor staff to follow for the services to be provided.

- Contractor Project Manager and IC shall ensure that all Contractor staff are  trained by State RPF, CalRecycle OC, CalRecycle H&S professional, and State Environmental SME prior to being sent out for any field work.

- Conduct HTWS (as described previously), under the direction of the State and Contractor Foresters and the IMT, to provide necessary information to the Hazard Tree Removal Contractor’s Invitation for Bid solicitation.

Conduct initial visual survey of roadways and infrastructure along these roads that could potentially be impacted by the debris cleanup operations.  Evaluate pre-operational conditions with video recording and notes collected during the evaluation.  These shall be compared to post-operational evaluation for potential local agency reimbursement by state or federal funding agency.

- Perform Individual Property Assessments for Trees requiring removal under this program:

- Under the direction of the RPF, Arborists/Arborist Technicians will delineate those trees that are determined to be hazardous, and will mark those trees appropriately, as prescribed by the RPF, on each property.

- One Task Force Leader shall be teamed-up with each Arborist/Arborist Technician on each property.

- The Task Force Leader (TFL) shall:

  - Review the Right of Entry (ROE) documentation for the property before any Contractor staff enter the property.  TFL shall communicate any hazards, unusual conditions, or other relevant information reported on the ROE to any other personnel entering the property.

  - Verify that each property, upon arrival, has an address sign installed.

  - If no address sign is installed, the Task Force Leader will install such a sign prior to proceeding onto the property.

  - Observe any overhead utilities and note them in the TFL’s documentation.

  - Identify and document any existing buildings, structures, fences, vehicles, septic tanks, water wells, stream beds, bridges, etc.

  - Identify and document other property-specific hazards (i.e. animals, swimming pools, steep hillsides, large vehicles).

  - Document all of the trees that are marked by the Arborist/Arborist Technician with a FEMA approved Automated Debris Management System (ADMS) device, electronically. Data collected will include:

    - unique identification numbers for all trees,

    - the number of trees (on this property) on a site assessment map,

    - each tree’s tree type (as determined by the arborist/arborist technician),

    - its height,

    - its diameter (at 4.5 feet above ground level),

    - its GPS coordinates, and

    - a photograph of each tree before removal showing the identification number on the tree trunk and a photograph after removal showing the identification number on the remaining stump.

    - The TFL shall also prepare a survey map showing the location of the trees included on the property (The survey map shall include a tree represented as a circle tagged with a tree identification number).

  - Be prepared to mark property boundaries if access to hazard trees that are marked to be cut may require access across such a boundary or if the trees may fall across such boundaries after being cut. Mark this possibility on the site map.

  - Place all above listed information in a database folder for each property by APN number and available to the IMT by “Box” or other similar, IMT approved database.

  - Assist in overseeing the appropriate implementation of each of the Timber Harvest Plans with respect to the state California Environmental Quality Act (CEQA) and federal National Environmental Policy Act (NEPA) environmental protection requirements (BMPs), for protection of endangered and impacted species and their habitats under emergency operations.

  - Task Force Leader (Tower Monitor):

    - Track each truck and estimate the volume in cubic yards of vegetative debris entering and leaving the debris management site.

    - Track each truck and estimate the volume in cubic yards of vegetative debris entering final destination wood waste facilities.

- Conduct Air Monitoring and Surveillance during Tree Removal Operations:

1.	Develop an offsite (community) air monitoring plan for constituents of concern detected during the previous debris removal operation, to the satisfaction of CalRecycle.

2.	Conduct offsite (community) air monitoring consistent with the offsite (community) air monitoring plan, if and as determined by CalRecycle’s and the Contractor’s Health and Safety Officers.

- Health and Safety Considerations:

- Though this project is being conducted after the ash and debris removal operation has been completed, there still may be heavy metals impacted ash in the tree branches and bark. Therefore, dust control such as wetting the ground where the trees are intended to fall (with water from water trucks) prior to start of tree falling and removal and wetting down the trees prior to and during limb/slash chipping operations will be necessary to reduce dust and sawdust releases. The TFL shall be responsible to advise the Tree Removal Contractor about minimizing the release of dust and sawdust from their work areas.

- Protect Storm Water Best Management Practices During Tree Falling and Removal Operations:

- Observe and verify the protection of already installed on-property storm water best management practices (BMPs) such as waddles and compost socks installed to prevent off-site migration of waste into municipal system or nearby waters.

- Document the Tree Removal Contractor’s installation of new stormwater BMPs necessary to meet Timber Harvest Plan requirements and overall operationally required BMPs to minimize both soil erosion and generated sawdust from being carried down to local streambeds.

- Project Completion Documentation:

- Assist CalRecycle staff in completing financial summary information for each property that signed up for the Government Hazard Tree Removal Program in a manner and level of detail acceptable to CalRecycle to document complete project costs.

- Provide adequate management level and administrative staff as required to conduct after action meetings and prepare an after action report for work performed on this project. An after action incident report is critical. After action reports will ensure that lessons learned can be integrated into response operations at future hazard tree removal operations. This process includes: identifying the functions to assess and evaluate, conducting meetings with key personnel to discuss these functions, and developing an after action report or improvement plan to document the lessons learned.  These services are described in more detail as follows:

- Determine Hazard Tree Removal Functions

Using the concepts of the California Standardize Emergency Management System (SEMS) and Incident Command System (ICS), the Contractor shall coordinate with CalRecycle to determine the hazard tree removal-related functions to assess for the after action meeting.

- Conduct After Action Meeting

Once the list of functions is finalized, the Contractor shall conduct a half-day after action meeting with key personnel to discuss the successes and lessons learned from these fire tree removal operations. CalRecycle will coordinate the scheduling, invitations, and office location for the meeting. The Contractor shall facilitate the meeting and provide printed materials. The Contractor shall manage the agenda to ensure there is sufficient time to discuss each tree removal function. During the after action meeting, the Contractor shall use the Cal OES after action meeting template to document areas for improvement and potential improvement actions (i.e. planning, training, personnel, equipment, or facilities).

- Deliver After Action Report

The Contractor shall develop and deliver the after action report that documents the successes and lessons learned from these hazard tree removal operations. The report will provide recommendations to address gaps in the Tree removal-related functions and will include an improvement plan matrix for CalRecycle to track improvement actions.

The final report will include best management practices that have been instituted as a result of the operational standards set forth on this fire. The report will include a comparison to historical tree removal operations by other state agencies to demonstrate how CalRecycle can improve upon the effectiveness and efficiencies of their tree removal operations.

The Contractor shall conduct meetings to review changes to the report. The Contractor shall make the changes and provide the final version electronically to CalRecycle.

- Prepare draft versions of CalRecycle project administration documents to implement the recommended changes on future hazard tree removal projects.  Example documents that may be amended include, but are not limited to: the Timber Harvest Plan and all of its technical appendices, site completion reports, reports generated by the planning function on the ICS team, project Agreement, project Agreement solicitation documents, and any and all field documentation required for the project administration.

Roles

The following are CalRecycle’s requirements for the specific roles and responsibilities of the Contractor’s staff in the performance of this Agreement.  All staff conducting work in and around the tree removal cleanup and disposal operations shall be trained in industry specific safety training, prior to commencing work.

- PROJECT MANAGER

The Project Manager is responsible for overseeing the operations of the Contractor’s staff deployed as part of the ICS Team.  This position is not necessarily a full-time position but is dedicated to make sure that the operation has sufficient staff, equipment and materials to complete the work defined by the Incident Command’s IC, OC, PC, LC, FC and CalRecycle’s Contract Manager.

- INCIDENT COMMANDER

The Incident Commander shall be responsible for overseeing the on-site Contractor ICS staff and be full-time in the field.  The Contractor IC selection requires the approval of the CalRecycle FC/Contract Manager and the CalRecycle OC.

- HEALTH AND SAFETY OFFICER

The Health and Safety Officer shall prepare, have reviewed and signed by a Certified Safety Professional (CSP) or Certified Industrial Hygienist (CIH), and be responsible for implementing a program Safe Work Plan covering all Contractor Activities, listed in this scope of work, for the Contractor’s employees and/or the Contractor’s subcontractors, and CalRecycle staff (if requested) at all the hazard tree removal and processing sites. The Health and Safety officer shall also coordinate with the other Safety officers provided by CalRecycle and the Prime Tree Removal Contractor.

The Health and Safety Officer shall be a registered safety professional, CIH or CSP, certified and have appropriate experience to adequately oversee and/or perform the tasks outlined in the Scope of Services.

- REGISTERED PROFESSIONAL FORESTER

The Registered Professional Foresters (RPFs) shall include a lead RPF and a minimum of three (3) Sub-Area Foresters that together will oversee and help the State and the IMT manage the Tree Removal Contractor and subcontractors to ensure the proper implementation of the Timber Harvest Plans/Conversion Exemptions (THPs/CEs) for each sub-area. The RPFs duties include but are not limited to:

- Preparing and/or overseeing the preparation of the THPs for each subarea.

- Providing the THPs/CEs to the Tree Removal Contractor and/or to the Tree Removal Contractor’s LTO Subcontractor(s) for signature and submitting to the CalFire Regional Forester prior to implementing of the tree harvest operation.

- Once Rights of Entry have been submitted to and approved by the Town of Paradise and/or Butte County, and approved by the CalFire Regional Forester, the Contractor’s Forester and/or their designated Arborist shall assess and mark each property for hazard trees that could fall on public rights of way.

- The RPFs shall oversee and direct the Arborists/Arborist Technicians (joined by the TFLs) to oversee that the LTOs prepare for the cutting, processing and removal of property marked hazard trees in such a manner as to protect any personal property and /or utilities in the process.

- OPERATIONS CHIEF

The Operations Chief (OC) is responsible for developing and implementing strategy and tactics to accomplish the incident objectives by directing and/or supervising soil/solids environmental cleanup and/or remediation operations. The OC duties include but are not limited to:

- Is responsible to the Incident Commander for the direct management of all incident-related operational activities.

- Works closely with and supports the IC, the PC, and the RPF in formulating and updating the Timber Harvest Plans that shall be prepared to direct the OC, the RPF, and the Operations Team as to their duties and their responsibilities. The OC is responsible for setting up staging areas from which the hazard tree removal teams shall muster.

- Establishes and directs all tactical objectives for each operational period.

- The OC organizes, assigns, and supervises all the tactical or response resources assigned to the incident. Responsible for setting up the required Divisions and/or Specialty Groups to properly, effectively, and efficiently carry out the hazard tree removal operations.

- Directs the Operations Team who together shall be responsible for all activities focused on reducing the immediate hazard, saving lives and property, establishing situational control, and restoring normal operations.

- The OC will also be responsible for recording and keeping track of all Damage Claims submitted to the IMT, the Town and County, the TFLs, and Contractor IMT. The Damage Claims forms, supplied by the IMT, will include a decision chain that will require signatures or acknowledgements by the TFL, Division Supervisor, Branch Director, Ops Chief, CalRecycle Ops Chief and the Incident Commander. The Contractor shall ensure that each and every Damage Claim form is filled out with the damage description, Ops Chief determination of action to be taken, concurrence by CalRecycle Ops chief and IC and notation that the property owner had been notified for the decision with a signature and date for each action.

- Additionally, if a Staging Area is established, the OC shall manage the Staging Area.

- DEPUTY OPERATIONS CHIEF

The responsibilities of the Deputy Operations Chief includes supporting the OC in collecting information, managing data, coordinating with property owners and local agencies in assisting in the preparation and carrying out of the overall tree removal preparation, operation, and de-mobilization.

- BRANCH DIRECTOR

The Branch Director (as approved by the OC) is responsible to supervise and support all Division Supervisors (responsible for both overseeing their Division Supervisors and supporting their tasks as well as coordinating with the Tree Removal Contractor to address field activities concerns/issues) and to report back to the OC and IC about status or issues/concerns with operations in their purview. The duties for this operation include:

- Fully understand and follow the requirements included in the Timber Harvest Plan that covers their logistical area, provided by the PC and the State Forester;

- Provide and/or verify that the Division Supervisors are properly trained to conduct the work assigned;

- Provide direct supervision of and direction to the Division Supervisors and the work they are conducting;

- Inform the OC of issues or suggestions on how to conduct the operation more efficiently and effectively;

- Provide the necessary health and safety equipment and materials required for the Division Supervisors for the work they are conducting;

- Provide the forms, tools, and communication equipment to keep in contact with the Division Supervisor at all times; and

- Report directly to the OC and be the line of contact between the OC and the Division Supervisors in fulfilling the responsibilities of the Branch as assigned by the OC.

- DIVISION SUPERVISOR

The Division Supervisor (as approved by the OC) is responsible to supervise and support all Task Force Leaders (both responsible for overseeing the Tree Removal Contractor’s Field Activities including recording the trees removed from each property within their logistical area of supervision and working with the Tree Removal Contractor’s Superintendents addressing operational issues) and reporting their status to the Branch Director. The duties for this operation include:

1.	Fully understand and follow the requirements included in the Timber Harvest Plan that covers their logistical area, provided by the PC and the State Forester;

2.	Provide and/or verify that the Task Force Leaders are properly trained to conduct the work assigned;

- Provide direct supervision of and direction to the Task Force Leaders and the work they are conducting;

- Inform the Branch Director of issues or suggestions on how to conduct the operation more efficiently and effectively;

- Provide the necessary health and safety equipment and materials required for the Task Force Leaders for the work they are conducting;

- Provide the forms, tools, and communication equipment to keep in contact with the Supervisor at all times; and

- Report directly to the Branch Director and be the line of contact between the Branch Director and the Task Force Leaders in fulfilling the responsibilities of the Division as assigned by the OC.

- TASK FORCE LEADER

Task Force Leaders shall be selected and assigned by the Contractor’s Project Manager and report directly to and work for the Division Supervisor, the Branch Director, and ultimately the OC.  The Task Force Leaders are responsible for working with the Arborist/Arborist Technician in directing and overseeing tree removal operations at one or more such sites and must be capable of directing and overseeing these operations. The Task Force Leader shall have either at least two (2) years of experience in the Task Force Leader role and/or directing or overseeing tree removal operations at one or more such operations, or an approved equivalent, such as at least three (3) years of experience in overseeing and/or inspecting environmental cleanup and/or remediation operations. The Task Force Leaders shall:

- Read and fully understand the Timber Harvest Plan for the area within which properties that the TFL will be monitoring, prior to monitoring any tree cutting and harvesting;

- The TFL will accompany the A/AT Arborist during their initial property hazard tree assessments. The TFL will document all of the trees that are marked by the A/AT Arborist for placement in a database. The A/AT Arborist will determine the trees in need of removal, tree number identifier (pre-approved by the IMT), its diameter (at 4.5 feet above ground level), its type, its GPS coordinates.  The TFL will then document all of the collected data, electronically, for each property including number, type and diameter of trees on each APN. The A/AT Arborist will prepare a Map of the trees, for each property that will be provided to the TFL so that the TFL can place it with the photos and other recorded information about each tree to be removed in a database folder for each property by APN number and available to the IMT by “Box” or other similar and IMT approved database;

- Bring to each property and fully read, understand, and follow the requirements included in the initial site plan and the ROE for that property from which trees will be cut and harvested;

- Attend daily Incident Operations Chief/Tree Removal Contractor initiated safety meetings to discuss possible personal and community hazards;

- Be responsible to carry out, under the direction of the OC, the Branch Director, and the Division Supervisor, the Timber Harvest Plan requirements for each individual property assigned, and to read and follow the Homeowner’s directions, listed on the signed and County approved Right of Entry (ROE) Forms;

- The Task Force Leaders shall be the Homeowner’s point of contact until the trees on their property have been removed and the property has been cleared by the County;

- Inspect each Contractor’s truck supporting work on each property and ensure that they each have a safety check placard, issued by the Contractor’s DOT commercial truck inspector teams;

- Inspect, monitor, photographically track, and document the trees cut and removed from the property by type, size, and number marked on the tree by the Forester/Arborist from each assigned property;

- Provide documentation of trees removed by street, route, and date. This documentation shall be in an Excel format or other formats utilizing a FEMA approved Automated Tree Removal Management System (ATRMS) Survey 123 data collector software including providing their own tablets or other similar electronic type devices;

- Complete and submit to PC and/or any additional governmental agency all documentation that is required for CalRecycle to receive the maximum reimbursement for all covered trees removed and related costs;

- Watch and advise the tree removal crew’s activities if any health and safety or environmental controls and/or activities (i.e. controlling dust, water run-off of burn ash, etc.) should be addressed during the cleanup operation;

- If there are any existing stormwater BMPs (such as wattles, compost socks, hay bales, erosion control netting or other such BMP) on the property, ensuring that they are not disturbed by the tree removal operation;

- Per the Timber Harvest Plan, work with the arborist/arborist technician to be sure that any environmental and/or archaeological BMPs required are in place and noted to the Tree Removal Contractor prior to commencing tree removal operations. The Tree Removal Contractor will not be allowed to work on any property that is not appropriately protected per the THP;

- Fill out and submit daily activity logs per property documenting Contractor labor staff and hours, equipment used, trucks that hauled materials from the property, logging decks or timber end use locations where trees and any processed materials from that property were taken to directly;

- Inspect traffic control devices and procedures for compliance with the site-specific traffic control plan;

- Provide daily oral status reports to the Division Supervisor, the Branch Director, and the OC, or designee, at the end of each day;

- Obtain site clearance/approval from OC once all designated trees have been removed from the property to allow for a final walk through by the OC or designee;

- Coordinate and work cooperatively with the Tree Removal Contractor, the State Forester’s Site Inspection Team, the Operations Team’s and Tree Removal Contractor’s Health and Safety Officers, air sampling consultants (if required), and other Operations Team Members;

- Coordinate and communicate with OC and PC on a regular basis or as needed, including reporting any unresolved issues, concerns, or complications that may be occurring with the Tree Removal Contractor;

- Be present during any Tree cutting and removal activities, and related on-site management, which shall take place from Monday through Saturday, 11 hours per day if safe conditions allow unless otherwise stated by the OC;

- Perform other requests as directed by the OC and/or the PC;

- Task Force Leaders assigned to truck staging area(s), Logging Decks for timber processing, and/or Tree product Disposal Sites will be assigned to logging-in the trucks entering and leaving each Logging Deck and Disposal Site, verifying materials that are in the truck payloads, and verifying the quantity of materials delivered by each truck in a truck tracking system developed with the Division Supervisor, Branch Director, and OC/PC, monitoring the safety stickers and inspection stickers, transportation of the trees; and

- These Truck Staging Area and/or Log Deck TFLs shall also inspect each Contractor’s truck supporting work on each property and ensure that they each have a safety check placard, issued by the Contractor’s DOT commercial truck inspector teams.

- ARBORIST/ARBORIST TECHNICIAN

The Certified Arborists are environmental science trained and degreed professionals experienced and trained in assessing the health of fire-damaged trees and trained by an RPF to assess such trees.  Arborist Technicians are not necessarily degreed but are experienced and trained as Arborists. The Arborist/Arborist Technician (A/ATs) shall be overseen and directed by one of the RPFs. The responsibilities of the A/ATs Arborists include, but are not limited to the following:

- Each Arborist/Arborist Technician shall receive a training certificate from the RPF indicating they have received such training and have indicated a clear understanding for evaluating the health and height of trees to be harvested.

- Under the direction of an RPF, assess trees threatening the defined public right of way near each property that is eligible for tree removal as determined by the IMT private property for which the State has an approved ROE and mark those trees appropriately, as prescribed by the RPF, that meet the Timber harvest plan requirements for selecting hazard trees. This information will be logged into the Contractor database by the accompanying Task Force Leader and be accessible by the IMT by the next day.

- Arborists/Arborist Technicians shall be accompanied by task force leaders (who will document all of the trees that are marked by the A/AT Arborist for placement in a database). The A/AT Arborist shall determine the trees in need of removal, tree number identifier (pre-approved by the IMT), its diameter (at 4.5 feet above ground level), its type, its height and its GPS coordinates.  The TFL shall then document all of the collected data, electronically, for each property including number, type and diameter of trees on each APN. The A/AT Arborist shall prepare a Map of the trees, for each property that will be provided to the TFL so that the TFL can place it with the photos and other recorded information about each tree to be removed in a database folder for each property by APN number and available to the IMT by “Box” or other similar and IMT approved database.

- Once the marked trees are cut and cleared off of each property, the A/ATs Arborists shall assess, document, and mark the tree stumps with their original markings (prior to cutting) and take a picture and GPS the stump location. This information shall be logged into the Contractor database by the accompanying Task Force Leader and be accessible by the IMT by the next day.

- Prepare Final Site Tree Removal Reports, one for each property, that summarizes the pre-tree removal and post-tree removal conditions, including; the initial and final assessments, a copy of site’s ROE, a summary of the trees removed from the property, the type of erosion control best management practices conducted on the property (post-tree removal operation, if deemed necessary by the RPF) and an indication of any unique or unexpected circumstances that occurred during the tree removal operations. Each report shall include pictures from both pre- and post-tree removal operations.

- BIOLOGISTS/ARCHAEOLOGISTS

The Senior Biologists and Senior Archaeologists shall help to prepare the Timber Harvest Plan environmental protection supporting documentation assessments as well as recommended environmental/historical best management practices (BMPs) to protect these areas from negative impacts for each Timber Harvest Plan.

Biologists and Archaeologists, trained by the Senior Biologist, Senior Archeologist, and Lead RPF will conduct required assessments and monitor the Tree Removal Contractor’s crews to make sure that they are implementing the THP’s required BMPs.

Some of the Biologists shall be required to have aviary and amphibian specialties to assist in necessary evaluation and protection of species (endangered and otherwise).

- ENVIRONMENTAL UNIT LEADER/AIR QUALITY

The Air Quality Environmental Unit Leader shall oversee the preparation and implementation of an air monitoring plan.  The plan shall include the collection of air monitoring samples assessing for airborne particulate matter and criteria pollutants that may cause health hazards from the previously released structural fire ash that may have been captured by the hazard trees during the fire and subsequent debris removal operations.  Criteria air contaminants are typically emitted from many sources.  The Air Quality teams will typically set up continuous operating monitoring stations at key community sites, that will be checked on throughout the day.  Additionally, the teams will set up 3 continuous air monitoring stations at up to one-third of the hazard tree removal task force teams, which could add up to approximately 33 task forces in need of air monitoring.  All of these air monitoring stations will also need to be checked on throughout the day.

- DATA/PACKET MANAGER

The Data Packet manager shall electronically manage and track all the site documentation including, but not limited to the following; the ROEs, all site documentation, daily activity documentation, trucking documentation, and site data reconciliation with the Tree Removal Contractor. The Data/Packet Manager shall compile documentation for cost tracking and reconciliation.

The Data//Packet Manager shall also make collected data available to the OC, PC, and FC and the entire IMT as requested to help improve the effectiveness and efficiency of the operation.

- PLANNING CHIEF

The Planning Chief (PC) shall oversee the collection, evaluation, and dissemination of operational information related to the incident.  It is the PC’s responsibility to prepare and assist the OC in implementing the THPs, as well as track the status of all incident resources and all the preparations for, data management from, and the final dispositions of each property that has entered into the tree removal program.

- PLANNING ASSISTANT

The responsibilities of the Planning Assistant include supporting the PC in collecting information, managing data, coordinating with property owners and local agencies in assisting in the preparation and carrying out of the overall tree removal preparation, operation, and de-mobilization.

- GIS PROFESSIONAL

The GIS professional shall be responsible for taking all local fire incident information, local agency information, mapping, and infrastructure information and building it into a cohesive database that can be used to assess, coordinate, and summarize all the tree removal activities that have taken place. The database shall be developed by the GIS professional to provide the PC, OC, and FC an easy way to access information that will assist them in performing their duties. This database shall include all daily activity logs, truck tickets, site tree assessments, and closure reports for each participating property, using a CalOES and CalRecycle specified data structure.  The Database shall be based on ESRI software and compatible with CalRecycle’s GIS systems.

- LOGISTICS CHIEF

The Logistics Chief (LC) shall be responsible for supporting the overall tree removal operation by finding and supplying the facilities, utilities, supporting materials, health and safety personal, and protective equipment and other expendables in support of the Operations staff. The LC shall also provide communications devices, computers, tablets, transportation, and anything else needed to support the tree removal efforts.

- FINANCE/ADMINISTRATION CHIEF

The Finance/Administration Chief (FC) is responsible for all of the financial and cost analysis and cost efficiency aspects of the tree removal operations. These include Tree Removal Agreement negotiation (if appropriate), recording or auditing personnel and equipment time, documenting and processing claims for accidents and injuries occurring at the incident, and keeping a running tally of the costs associated with the incident. The FC is also responsible for reviewing and auditing the Tree Removal Contractor’s monthly invoices to make sure that they are accurate, defendable, and reimbursable by the state and federal (if applicable) agencies supplying disaster relief funding.

- The FC shall validate and ensure the preparation of invoices adhere to the following provisions:

- Invoices comply with provisions of purchase orders, sub-purchase orders, contracts, leases, service agreements, grants, etc. This includes ensuring completed work orders, adherence to contract terms and invoicing, and that there is proper authorization and internal control of purchases and assets.

- Items or services invoiced have been received or provided, as evidenced by stock received reports or similar documents or employee verification and is fully documented for audit or other external review.

- Authority exists to obtain the goods or services.

- Payment has not previously been made.

- ACCOUNTING AND ADMINISTRATIVE STAFF RESPONSIBILITIES

Accounting and Administrative staff shall be selected by the Contractor’s Program/Project Manager and report directly to CalRecycle’s Incident Operations Planning Chiefs (PC) and/or Financial Chiefs (FC) supporting the tree cleanup activities. The services to be provided include:

- Early on, work with the Tree Removal Contractor and the CalRecycle FC and/or accounting staff in developing an acceptable method for accounting of billable activities and an agreed upon format for invoices to be submitted to the CalRecycle FC for review and payment.

- Work directly with the FC to track trees removed, hauled, and deposited at final destinations by managing daily work sheets prepared by the TFLs, and collecting and collating truck tickets and destination (landfill, recycle facility, etc.) tickets from each cleanup property on a daily basis;

- Work with the FC in accumulating and tabulating daily quantities removed from each site and in total for the Government Hazard Tree Removal Program;

- Receive, review, and compare Contractor invoices with the daily logs and materials disposal tickets for costs expended;

- Evaluate invoices to verify that all costs have been charged per the Agreement approved unit rates;

- Report to the FC any discrepancies between the daily logs, other per lot documentation, and the invoices; and

- Other administrative requests made by either the PC or the FC.

- ENVIRONMENTAL UNIT LEADERS

The Environmental Unit Leaders and supervisors shall be responsible for overseeing and supporting the field work conducted by the Biologists and Archaeologists in addressing the environmental requirements of the Timber Harvest Plans.

- ENVIRONMENTAL BRANCH DIRECTOR/SENIOR ENVIRONMENTALIST

Provide an Environmental Branch Director/Senior Environmentalist to assist the RPFs in preparing and overseeing the appropriate implementation of each of the Timber Harvest Plans/Conversion Exemptions with respect to the state California Environmental Quality Act (CEQA) and federal National Environmental Policy Act (NEPA) environmental protection requirements, for protection of endangered and impacted species and their habitats under emergency operations. The Environmental Branch Director/Senior Environmentalist will also be responsible for overseeing and supporting the Environmental Unit Leaders in addressing the environmental requirements of the Timber Harvest Plans.

- ENVIRONMENTAL UNIT LEADER/WATER QUALITY BMPS

Provide an Environmental Unit Leader to assist the RPFs in preparing and overseeing the appropriate implementation of each of the water quality BMPs required in the Timber Harvest Plans/Conversion Exemptions with respect to the state California Environmental Quality Act (CEQA) and federal National Environmental Policy Act (NEPA) environmental protection requirements, for protection of endangered and impacted species and their habitats under emergency operations.

- MISCELLANEOUS POSITIONS/SERVICES

- There may be Tribal Monitoring required on this project under a subcontract to this Agreement.  Tribal monitoring is typically provided by the regional tribe using tribal appointed monitors.  Rates established by the tribe(s) will be the basis for the rates paid to the tribal monitors and is outside of the control of the Contractor.  The Contractor is limited to a ten (10) percent markup on this subcontract.

- The Contractor shall hire independent third-party DOT commercial truck inspector two-person teams. The Contractor shall:

- Provide certifications and resumes indicating their experience as truck inspectors to the IMT for approval. The inspectors shall have the necessary insurance, qualifications, and expertise to perform a level one inspection for all commercial trucks assigned to the incident. All inspection records, both pass and fail, shall be submitted to the IMT within 24 hours of the inspection.

- Provide as many such 2-person crews as is determined by the IMT to be necessary to confirm that all trucks pass safety inspections as required by the State Highway Patrol and applicable state and local regulations. The Contractor will placard each and every truck that has been inspected with a unique placard number that can be scanned by TFLs at each property site, log deck processing site, and final disposal site.

- Inspect all logging trucks, haul trucks, water tenders, tow trucks, street sweepers, low-beds, and other commercially licensed vehicles used on the project. Water trucks used specifically on-site lots are not subject to inspection provided they are not carrying water loads on a public road; these water trucks are considered construction vehicles.

- Re-inspect 10% of all previously certified trucks every 30 days.

- GPS Tracking of Commercial Fleet

The Contractor shall be responsible for installing and monitoring Global Positioning System (GPS) tracking on all haul trucks, street sweepers, and community water tenders. The Contractor shall provide access to the tracking software to the IMT and Tree Removal Contractor.

- The Contractor is required to provide and install property signage, where necessary (signs may already exist), per the following:

  - Depending on the number of ROEs, up to approximately 16,000+ reflective aluminum address signs will be required. The sign dimension should be 6 inches in width and 18 inches in height or length. The edges shall be rounded and free of sharp edges. The background shall be a reflective green and all text shall be reflective white. Each sign shall be mounted on a 6-foot pre-drill, u-channel steel post or other post. The numbering for the address shall be 3 to 4 inches in height. The Contractor shall assemble and install each sign,

  - The Contractor shall post each sign and notify USA 811 before installing.

  - Address sign example (not to scale):

  - CalRecycle will reimburse the Contractor for signage per the proposal cost sheet.  The cost to provide signage shall be paid on a per sign basis and include all sign material, delivery, and installation.

- The Contractor shall hire a Licensed Professional Surveyor to resolve boundary disputes on affected properties.

- There may be a need for the Contractor to provide additional professional services in support of the Government Hazard Tree Removal Program, if requested by CalRecycle.  Any additional services must be approved by the Contract Manager in writing and in accordance with the “Work Authorization” clause of Exhibit D.  All rates must be approved in the Work Authorization document, and shall be reasonable, typical of the industry, and allocable.  If such additional services require subcontracting, the Contractor is limited to a ten (10) percent markup on subcontract costs.

- Change Orders: If the Contractor is directed to perform work outside the Scope of Work of this Agreement or encounters any other situation where it believes an adjustment of costs from the Cost Proposal Sheet is justified, the Contractor must immediately notify the Contract Manager and the IMT of the need for a Change Order. Failure to promptly notify the Contract Manager constitutes a waiver of any claim for additional compensation prior to actual notification to the Contract Manager.

The Contract Manager, in consultation with the IMT, shall notify the Contractor whether to perform or continue the affected work and issue a Change Order if adjustment to the Cost Proposal Sheet costs is necessary. The Contractor shall promptly provide all information requested by the Contract Manager in support of a Change Order. Upon completion, a Change Order shall be attached to this Agreement through the formal amendment process. A Change Order shall specify the effective date of the adjusted costs, but those costs cannot be invoiced at the adjusted rate prior the completion of the amendment. In order to be approved, the Change Order costs must be reasonable, allocable, and typical of the industry, and the Change Order work must be reasonable for the completion of the project scope.

Weather Delays

In the event that a crew does not work as scheduled due to weather or other delays outside the control of the Contractor, the Contractor shall be compensated for the idle employees based on the hourly rates established on the Cost Proposal Sheet based on the chart below.

For the purposes of this chart, more than or equal to 30 minutes of work shall be considered a full hour of work.  Less than 30 minutes of work will not be considered.

| Hours Actually Worked | Hours to be Paid |
| --- | --- |
| 0 | 3 |
| 1 - 2 | 4 |
| 3 - 4 | 5 |
| 5 | 5.5 |
| 6 + | Actual Hours Worked |

Location of Services

Services will be provided in Butte County.

Control of Work

- The CalRecycle Contract Manager has the authority to determine the quality and acceptability of the following:

- Work to be performed;

- Rate and progress of the work;

- Fulfillment of the services provided by the Contractor; and

- Compensation for services provided by the Contractor.

- The Contractor will designate a Project Manager who holds the following authority:

  - Act as the Contractor’s Representative for work to be provided under this Agreement

  - Act as the Contractor’s Representative regarding contractual matters relating to this Agreement

If during the course of the Agreement, it is deemed necessary to replace the Project Manager, CalRecycle’s Contract Manager approval is required prior to the replacement being made.

EXHIBIT B

BUDGET DETAIL AND PAYMENT PROVISIONS

- INVOICING AND PAYMENT:

- For services satisfactorily rendered and upon receipt and approval of the invoices, the State agrees to compensate the Contractor for services performed in accordance with the rates specified herein.

- Itemized invoices shall be submitted in triplicate, with two sets of supporting documentation (i.e., receipts, timesheets, etc.), not more frequently than monthly in arrears to:

Accounts Payable

Department of Resources Recycling and Recovery

Fiscal Services Branch

U.S. Postal Correspondence:

P.O. Box 4025, MS-19A

Sacramento, CA 95812-4025

Federal Express Correspondence:

1001 I Street, MS-19A

Sacramento, CA 95814

- Each invoice submitted to CalRecycle must include the following information:

  - Invoice Number

  - Contract Number

  - Description of Rendered Activities/Services

  - Submitting Contractor’s Address

  - Invoice Period

- BUDGET CONTINGENCY CLAUSE:

- It is mutually agreed that if the Budget Act of the current year and/or any subsequent years covered under this Agreement does not appropriate sufficient funds for the program, this Agreement shall be of no further force and effect.  In this event, the State shall have no liability to pay any funds whatsoever to the Contractor or to furnish any other considerations under this Agreement and the Contractor shall not be obligated to perform any provisions of this Agreement.

- If funding for any fiscal year is reduced or deleted by the Budget Act for purposes of this program, the State shall have the option to either: cancel this Agreement with no liability occurring to the State, or offer an Agreement Amendment to the Contractor to reflect the reduced amount.

- PROMPT PAYMENT CLAUSE: Payment will be made in accordance with and within the time specified in Government Code, Chapter 4.5 (commencing with Section 927).

- TAXES:  The State of California is exempt from Federal Excise Taxes, and no payment will be made for any taxes levied on employees' wages.  The State will pay for any applicable State of California or local sales or use taxes on the services rendered or equipment or parts supplied pursuant to this Agreement.  California may pay any applicable sales or use tax imposed by another state.

- COST BREAKDOWN:

Insert the final pricing from the winning proposer.

- PROGRESS PAYMENT AND PAYMENT WITHHOLD:  Progress Payments are permitted under this agreement.  Ten percent of the invoiced amount shall be withheld pending completion of the contract.  The Contractor agrees to comply with the requirements of Public Contract Code (PCC), section 10346. Ten percent of the invoiced amount shall be withheld pending completion of each separate and distinct task.  Any funds withheld with regard to a particular task may be released upon completion of that task to the satisfaction of CalRecycle.  For assessment and monitoring of tree removal, the individual lots constitute separate and distinct tasks, and completion constitutes the lots being cleared of Program RPF/Arborist marked hazard trees, and taken through the installation of erosion control measures required per the IFB, THP, and EPP, and acceptance as complete by CalRecycle OC or OC designee.  Regardless of lot completion, CalRecycle shall retain an amount equal to the estimate costs to generate the final report through the duration of the Contract.  The Contractor agrees to comply with the requirements of Public Contract Code (PCC), Section 10346.

EXHIBIT D

SPECIAL TERMS AND CONDITIONS

    - AGENCY LIABILITY: The Contractor warrants by execution of this Agreement, that no person or selling agency has been employed or retained to solicit or secure this Agreement upon agreement or understanding for a commission, percentage, brokerage, or contingent fee, excepting bona fide employees or bona fide established commercial or selling agencies maintained by the Contractor for the purpose of securing business. For breach or violation of this warranty, CalRecycle shall, in addition to other remedies provided by law, have the right to annul this Agreement without liability, paying only for the value of the work actually performed, or otherwise recover the full amount of such commission, percentage, brokerage, or contingent fee.

    - AMENDMENT: No amendment or variation of the terms of this Agreement shall be valid unless made in writing, signed by the parties and approved as required.  No oral understanding or agreement not incorporated in this Agreement is binding on any of the parties.  CalRecycle reserves the right to amend this Agreement through a formal written amendment signed by both parties, for additional time and/or funding.

    - CALIFORNIA WASTE TIRES: Unless otherwise provided for in this contract, in the event the Contractor and/or Subcontractor(s) purchases waste tires or waste-tire derived products for the performance of this Agreement, only California waste tires and California waste tire-derived products shall be used. As a condition of payment under this Agreement, the Contractor must provide documentation substantiating the source of the tire materials used during the performance of this Agreement to the Contract Manager.

All formal notices required by this Agreement must be given in writing and sent by prepaid certified mail, fax, personal delivery or telex.

    - CONTRACT MANAGEMENT: The Contractor and the agents and employees of the Contractor, in the performance of this Agreement, shall act in an independent capacity and not as officers or employees or agents of the State of California. The Contractor may change the designated Project Director, but CalRecycle reserves the right to approve any substitution of the Project Director. Contractor’s key personnel may not be substituted without CalRecycle’s Contract Manager’s prior written approval. CalRecycle may change the Contract Manager by notice given to the Contractor at any time. CalRecycle staff will be permitted to work side by side with the Contractor’s staff to the extent and under conditions that may be directed by the Contract Manager. In this connection, CalRecycle’s staff will be given access to all required data, working papers, etc. The Contractor will not be permitted to utilize the CalRecycle’s staff for the performance of services, which are the responsibility of the Contractor unless the Contract Manager previously agreed to such utilization in writing, and any appropriate adjustment in price is made. No charge will be made to the Contractor for the services of CalRecycle’s staff for coordination or monitoring functions.

    - CONTRACTOR EVALUATIONS: If this Agreement is for consulting services, CalRecycle will evaluate the Contractor’s performance within sixty days of the completion of this Agreement and shall remain on file by CalRecycle for a period of thirty-six months. If the Contractor does not satisfactorily perform the work or service specified in this Agreement, CalRecycle will submit a copy of the negative evaluation to the Department of General Services (DGS), Office of Legal Services, within five (5) working days of the completion of the evaluation. Upon filing an unsatisfactory evaluation with the DGS, CalRecycle shall notify and send a copy of the evaluation to the Contractor within fifteen days. The Contractor shall have thirty days to prepare and send a written response to CalRecycle and the DGS. CalRecycle and the DGS shall file the Contractor's statement with the evaluation. (PCC §10369).

    - CONFIDENTIALITY/PUBLIC RECORDS: The Contractor and CalRecycle understand that each party may come into possession of information and/or data, which may be deemed confidential or proprietary by the person or organization furnishing the information or data. Such information or data may be subject to disclosure under the California Public Records Act, commencing with GC § 6250, or the PCC. CalRecycle agrees not to disclose such information or data furnished by Contractor and to maintain such information or data as confidential when so designated by Contractor in writing at the time it is furnished to CalRecycle, only to the extent that such information or data is exempt from disclosure under the California Public Records Act and the PCC.

    - CONFLICT-FUTURE BIDDING LIMITATION: Pursuant to Public Contracts Code Section 10365.5:

      - No person, firm, or subsidiary therefore who has been awarded a consulting services contract may submit a bid for, nor be awarded a contract for, the provision of services, procurement of goods or supplies, or any other related action that is required, suggested, or otherwise deemed appropriate in the end product of the consulting services contract.

      - Subdivision (a) does not apply to any person, firm, or subsidiary thereof who is awarded a subcontract of a consulting services contract that amounts to no more than ten (10) percent of the total monetary value of the consulting services contract.

      - Subdivisions (a) and (b) do not apply to consulting services contracts subject to Chapter 10 (commencing with Section 4525) of Division 5 of Title 1 of the Government Code.

    - CONSULTING SERVICES: If this Agreement is for consulting services, the Contractor is hereby advised of its duties, obligations and rights under PCC §§10335 through 10381.

    - COPYRIGHTS AND TRADEMARKS: The Contractor shall assign to CalRecycle any and all rights, title and interests to any copyrightable material or trademarkable material created or developed in whole or in any part as a result of this Agreement, including the right to register for copyright or trademark of such materials. The Contractor shall require that its subcontractors agree that all such materials shall be the property of CalRecycle. Such title will include exclusive copyrights and trademarks in the name of CalRecycle.

For contracts of $5,000 or more, any document or written report prepared for or under the direction of CalRecycle, shall include a notation on the inside cover as follows:

"Prepared as part of CalRecycle contract number DRR19055, Total Contract Amount ${Insert Amount}, pursuant to Government Code Section 7550."

    - DELIVERABLES: All documents and/or reports drafted for publication by or for CalRecycle in accordance with this contract shall adhere to CalRecycle’s Contractor Publications Guide at www.calrecycle.ca.gov/Publications/PubGuide/ and shall be reviewed by CalRecycle’s Contract Manager in consultation with CalRecycle editor.

    - ENTIRE AGREEMENT: This Agreement supersedes all prior agreements, oral or written, made with respect to the subject hereof and, together with the Attachments and/or Exhibits hereto, contains the entire Agreement of the parties.

    - ENVIRONMENTAL JUSTICE: In the performance of this Agreement, the Contractor shall conduct its programs, policies, and activities that substantially affect human health or the environment in a manner that ensures the fair treatment of people of all races, cultures, and income levels, including minority populations and low income populations of the State. (Government Code Section 65040.12(e)).

    - FORCE MAJEURE: Neither CalRecycle nor the Contractor, including the Contractor's subcontractor(s), if any, will be responsible hereunder for any delay, default or nonperformance of this Agreement, to the extent that such delay, default or nonperformance is caused by an act of God, weather, accident, labor strike, fire, explosion, riot, war, rebellion, sabotage, or flood, or any other cause beyond the reasonable control of such party.

    - GRATUITIES: CalRecycle may terminate this Agreement if gratuities were offered or given by the Contractor, or any agent or representative of the Contractor, to any employee of CalRecycle, with a view toward securing a contract or securing favorable treatment with respect to awarding or amending or making a determination with respect to performance of this Agreement.

    - IMPRACTICABILITY OF PERFORMANCE: This Agreement may be suspended or cancelled, without notice at the option of the Contractor, if the Contractor’s or CalRecycle premises or equipment is destroyed by fire or other catastrophe, or so substantially damaged that it is impractical to continue service or in the event the Contractor is unable to render service as a result of any action by any governmental authority.

    - INSURANCE: When required, the Contractor must provide: 1) a Certificate of Insurance insuring CalRecycle, and/or 2) verification of Worker’s Compensation insurance. The Contractor must provide said Certificate of Insurance and/or verification to CalRecycle within ten (10) days after notification of CalRecycle’s intent to award the Agreement. The Agreement will not be executed nor can work begin unless said Certificate of Insurance and/or verification is provided to CalRecycle.

The Certificate of Insurance must be in effect and shall include the following terms and conditions:

      - CalRecycle, its officers, agents, employees, and servants shall be included as additional insured.

      - The dates of inception and expiration of coverage shall be specified.

      - A minimum liability coverage of not less than $1,000,000 per occurrence for bodily injury and property damage liability combined shall be specified. The coverage shall not include a deductible feature.

      - The insurer will not cancel the insured’s coverage without thirty days prior written notice to CalRecycle.

      - CalRecycle is not liable for the payment of premiums or assessments on said policy.

      - The insurance coverage shall be on an occurrence basis only.

In the event the Certificate of Insurance should expire or be cancelled during the term of this Agreement, the Contractor agrees to provide, at least thirty days prior to said expiration or cancellation, a new Certificate of Insurance evidencing coverage, as provided for herein, for not less than one (1) year or for the remainder of the contractual agreement, whichever is greater. In the event the Contractor fails to keep in effect at all times insurance coverage as herein provided, CalRecycle may, in addition to any other remedies it may have, terminate this Agreement upon occurrence of such event.

    - LIABILITY FOR NONCONFORMING WORK: The Contractor will be fully responsible for ensuring the completed work conforms to the agreed upon terms. If nonconformity is discovered prior to the Contractor’s deadline, the Contractor will be given a reasonable opportunity to cure the nonconformity. If the nonconformity is discovered after the deadline for the completion of the project, CalRecycle, in its sole discretion, may use any reasonable means to cure the nonconformity. The Contractor shall be responsible for reimbursing CalRecycle for any additional expenses incurred to cure such defects. CalRecycle may pursue any sanctions allowed by law.

    - LICENSE OR PERMITS: The Contractor shall be an individual or firm licensed to do business in California and shall obtain at his/her expense all license(s) and permit(s) required by law for accomplishing any work required in connection with this Agreement.

In the event the Contractor fails to keep in effect at all times all required license(s) and permit(s), CalRecycle may, in addition to other remedies it may have, terminate this Agreement upon occurrence of such event.

    - OWNERSHIP OF DRAWINGS, PLANS AND SPECIFICATIONS: CalRecycle will have separate and independent ownership of all drawings, design plans, specifications, notebooks, tracings, photographs, negatives, reports, findings, recommendations, data and memoranda of every description or any part thereof, prepared under this Agreement. The originals and all copies thereof will be delivered to CalRecycle upon request. CalRecycle will have the full right to use said originals and copies in any manner when and where it may determine without any claim on the part of the Contractor, its vendors or subcontractors to additional compensation.

    - PATENTS: The Contractor assigns to CalRecycle all rights, title, and interest in and to each invention or discovery that may be capable of being patented, that is conceived of or first actually reduced to practice in the course of or under this Agreement.

    - PUBLICITY AND ACKNOWLEDGEMENT: The Contractor agrees that it will acknowledge CalRecycle’s support whenever projects funded, in whole or in part, by this Agreement are publicized in any news media, brochures, or other type of promotional material.

    - RECYCLED-CONTENT PRODUCT PURCHASING: In the performance of this Agreement, the Contractor shall purchase used and/or recycled-content products as set forth on the back of the Recycled-Content Certification Form (Exhibit D,  Attachment 1). For assistance in locating recycled-content products, please search the recycled-content product database available at: www.calrecycle.ca.gov/rcpm. If after searching the database, contractors are unable to find the recycled-content products they are looking for, please notify CalRecycle’s Contract Manager. All recycled content products purchased or charged/billed to CalRecycle that are printed upon such as promotional items, publications, written materials, and other educational brochures shall have both the total recycled content (TRC) and the post-consumer (PC) content clearly printed on them.

In addition, any written documents such as, publications, letters, brochures, and/or reports shall be printed double-sided on 100% post-consumer (PC) paper. Specific pages containing full-color photographs or other ink-intensive graphics may be printed on photographic paper. The paper should identify the post-consumer recycled content of the paper (i.e., “printed on 100% post-consumer paper”). When applicable, the Contractor shall provide the Contract Manager with an electronic copy of the document and/or report for CalRecycle’s uses. When appropriate, only an electronic copy of the document and/or report shall be submitted and no hard copy shall be provided.

    - REMEDIES: Unless otherwise expressly provided herein, the rights and remedies hereunder are in addition to, and not in limitation of, other rights and remedies under the Agreement, at law or in equity, and exercise of one right or remedy will not be deemed a waiver of any other right or remedy.

    - SETTLEMENT OF DISPUTES: In the event of a dispute, the Contractor shall file a “Notice of Dispute” with CalRecycle’s Director or his/her designee with ten (10) days of discovery of the problem. Within ten (10) days, the Director or his/her designee shall meet with the Contractor and CalRecycle Contract Manager for the purpose of solving the dispute.

    - STOP WORK NOTICE: Immediately, upon receiving a written notice to stop work, the Contractor shall cease all work under this Agreement.

    - SUBCONTRACTORS: All Subcontractors previously identified in the bid/proposal submitted are considered to be acceptable to CalRecycle. Any change or addition of Subcontractors will be subject to the prior written approval of the Contract Manager or the Director or his/her designee. Upon termination of any Subcontract, the Contractor shall notify the Contract Manager or the Executive Director immediately. If CalRecycle or the Contractor determines that the level of expertise or the services required are beyond that provided by the Contractor or its routine Subcontractors, The Contractor will be required to employ additional Subcontractors. Nothing contained in this Agreement or otherwise, shall create any contractual relation between CalRecycle and any Subcontractors, and no Subcontract shall relieve the Contractor of its responsibilities and obligations hereunder. The Contractor agrees to be as fully responsible to CalRecycle for the acts and omissions of its Subcontractors and of persons either directly or indirectly employed by any of them as it is for the acts and omissions of persons directly employed by the Contractor. The Contractor's obligation to pay its Subcontractors is an independent obligation from CalRecycle obligation to make payments to the Contractor. As a result, CalRecycle shall have no obligation to pay or to enforce the payment of any moneys to any Subcontractor.

    - SUCCESSORS: The provisions of this Agreement will be binding upon and inure to the benefit of CalRecycle, the Contractor, and their respective successors.

    - TERMINATION: CalRecycle shall have the right to terminate this Agreement at its sole discretion at any time upon thirty days written notice given to the Contractor. In the case of early termination, a final payment will be made to the Contractor upon approval by the Contract Manager of a financial report, invoices for costs incurred to date of termination and a written report describing all work performed by the Contractor to date of termination.

    - UNRELIABLE LIST: Prior to authorizing a Subcontractor(s) to commence work under this Agreement, the Contractor shall submit to CalRecycle a declaration from the Subcontractor(s), signed under penalty of perjury, stating that within the preceding three years, none of the events listed in Section 17050 of Title 14, California Code of Regulations, Natural Resources, Division 7, have occurred with respect to the subcontractor(s).

Placement of Contractor on CalRecycle Unreliable List anytime after award of this Agreement may be grounds for termination of Agreement. If a Subcontractor is placed on CalRecycle Unreliable List after award of this Agreement, the Contractor may be required to terminate the Subcontract.

    - WASTE REDUCTION: In the performance of this Agreement, the Contractor shall take all reasonable steps to ensure that materials purchased or consumed in the course of the project are utilized both effectively and efficiently to minimize the generation of waste. The steps should include, but not necessarily be limited to, the use of reusable products, the use of recyclable and compostable products, discretion in the amount of materials used, the provision of alternatives to disposal for materials consumed, and the practice of other waste reduction measures where feasible and appropriate.

    - WORK AUTHORIZATION: If this Agreement is for services as needed, or has clearly specified sub-categories a work authorization will be required before work can begin pursuant to this Agreement. The Contract Manger will make this determination, when work authorizations are required, the Contract Manager will prepare a work authorization for each item of work. Each work authorization, as appropriate, will consist of a detailed statement of the purpose, objectives or goals to be undertaken by the Contractor, identification of the Contractor/subcontractor team, all significant material to be developed and delivered by the Contractor, all materials to be furnished by CalRecycle to the Contractor, the Contractor’s estimated time schedule and person hours, billing rates and total cost of the work authorization.

      - All work authorizations will be in writing, negotiated and approved by the Contract Manager and the Contractor's Project Director prior to beginning work. However, in situations where expedience is of the utmost importance, the Contract Manager may verbally authorize the Contractor to begin work following up with written authorization.

      - The level of effort required for each work authorization will vary for each proposed project. Therefore, the Contract Manager will establish the time lines for completion of duties to be performed at the time of assignment.

      - CalRecycle reserves the right to require the Contractor to stop or suspend work on any work authorization. The Contract Manager will provide, in writing to Contractor's Project Director, notice of the date work is to be halted or suspended. Approved costs incurred to that date shall be reimbursed in accordance with this Agreement’s provision.

      - Each work authorization will be numbered sequentially.

      - The actual costs of a completed, approved work authorization will not exceed the authorized amount, except if, in the performance of the work, the Contractor determines that the actual cost will exceed the estimated costs; the Contractor will immediately notify the Contract Manager. Upon such notification, the Contract Manager may:

- Alter the scope of the work authorization to accomplish the work within the estimated costs; or

  - Augment the work authorization budget; or

  - Authorize the Contractor to complete the work for the actual costs; or

  - Terminate the work authorization.

EXHIBIT G

Required Contract Clauses for FEMA Public Assistance Program Contracts

The following clauses apply to this contract to the extent allowed by California law.

- Equal Employment Opportunity (Reference: 41 CFR Part 60-1.4(b)): During the performance of this contract, the contractor agrees as follows:

      - The contractor will not discriminate against any employee or applicant for employment because of race, color, religion, sex, sexual orientation, gender identity, or national origin. The contractor will take affirmative action to ensure that applicants are employed, and that employees are treated during employment without regard to their race, color, religion, sex, sexual orientation, gender identity, or national origin. Such action shall include, but not be limited to the following : Employment, upgrading, demotion, or transfer; recruitment or recruitment advertising; layoff or termination; rates of pay or other forms of compensation; and selection for training, including apprenticeship. The contractor agrees to post in conspicuous places, available to employees and applicants for employment, notices to be provided setting forth the provisions of this nondiscrimination clause.

      - The contractor will, in all solicitations or advertisements for employees placed by or on behalf of the contractor, state that all qualified applicants will receive consideration for employment without regard to race, color, religion, sex, sexual orientation, gender identity, or national origin.

      - The contractor will not discharge or in any other manner discriminate against any employee or applicant for employment because such employee or applicant has inquired about, discussed, or disclosed the compensation of the employee or applicant or another employee or applicant. This provision shall not apply to instances in which an employee who has access to the compensation information of other employees or applicants as a part of such employee's essential job functions discloses the compensation of such other employees or applicants to individuals who do not otherwise have access to such information, unless such disclosure is in response to a formal complaint or charge, in furtherance of an investigation, proceeding, hearing, or action, including an investigation conducted by the employer, or is consistent with the contractor's legal duty to furnish information.

      - The contractor will send to each labor union or representative of workers with which he has a collective bargaining agreement or other contract or understanding, a notice to be provided advising the said labor union or workers' representatives of the contractor's commitments under this section, and shall post copies of the notice in conspicuous places available to employees and applicants for employment.

      - The contractor will comply with all provisions of Executive Order 11246 of September 24, 1965, and of the rules, regulations, and relevant orders of the Secretary of Labor.

      - The contractor will furnish all information and reports required by Executive Order 11246 of September 24, 1965, and by rules, regulations, and orders of the Secretary of Labor, or pursuant thereto, and will permit access to his books, records, and accounts by the administering agency and the Secretary of Labor for purposes of investigation to ascertain compliance with such rules, regulations, and orders.

      - In the event of the contractor's noncompliance with the nondiscrimination clauses of this contract or with any of the said rules, regulations, or orders, this contract may be canceled, terminated, or suspended in whole or in part and the contractor may be declared ineligible for further Government contracts or federally assisted construction contracts in accordance with procedures authorized in Executive Order 11246 of September 24, 1965, and such other sanctions may be imposed and remedies invoked as provided in Executive Order 11246 of September 24, 1965, or by rule, regulation, or order of the Secretary of Labor, or as otherwise provided by law.

      - The contractor will include the portion of the sentence immediately preceding paragraph (1) and the provisions of paragraphs (1) through (8) in every subcontract or purchase order unless exempted by rules, regulations, or orders of the Secretary of Labor issued pursuant to section 204 of Executive Order 11246 of September 24, 1965, so that such provisions will be binding upon each subcontractor or vendor. The contractor will take such action with respect to any subcontract or purchase order as the administering agency may direct as a means of enforcing such provisions, including sanctions for noncompliance: Provided, however, that in the event a contractor becomes involved in, or is threatened with, litigation with a subcontractor or vendor as a result of such direction by the administering agency, the contractor may request the United States to enter into such litigation to protect the interests of the United States.

- Contract Work Hours and Safety Standards Act (Reference: 29 CFR 5.5(b)):  Compliance with the Contract Work Hours and Safety Standards Act.

      - Overtime requirements. No contractor or subcontractor contracting for any part of the contract work which may require or involve the employment of laborers or mechanics shall require or permit any such laborer or mechanic in any workweek in which he or she is employed on such work to work in excess of forty hours in such workweek unless such laborer or mechanic receives compensation at a rate not less than one and one-half times the basic rate of pay for all hours worked in excess of forty hours in such workweek.

      - Violation; liability for unpaid wages; liquidated damages. In the event of any violation of the clause set forth in paragraph (b)(1) of this section the contractor and any subcontractor responsible therefor shall be liable for the unpaid wages. In addition, such contractor and subcontractor shall be liable to the United States (in the case of work done under contract for the District of Columbia or a territory, to such District or to such territory), for liquidated damages. Such liquidated damages shall be computed with respect to each individual laborer or mechanic, including watchmen and guards, employed in violation of the clause set forth in paragraph (b)(1) of this section, in the sum of $27 for each calendar day on which such individual was required or permitted to work in excess of the standard workweek of forty hours without payment of the overtime wages required by the clause set forth in paragraph (b)(1) of this section.

      - Withholding for unpaid wages and liquidated damages. The State of California shall upon its own action or upon written request of an authorized representative of the Department of Labor withhold or cause to be withheld, from any moneys payable on account of work performed by the contractor or subcontractor under any such contract or any other Federal contract with the same prime contractor, or any other federally-assisted contract subject to the Contract Work Hours and Safety Standards Act, which is held by the same prime contractor, such sums as may be determined to be necessary to satisfy any liabilities of such contractor or subcontractor for unpaid wages and liquidated damages as provided in the clause set forth in paragraph (b)(2) of this section.

      - Subcontracts. The contractor or subcontractor shall insert in any subcontracts the clauses set forth in paragraph (b)(1) through (4) of this section and also a clause requiring the subcontractors to include these clauses in any lower tier subcontracts. The prime contractor shall be responsible for compliance by any subcontractor or lower tier subcontractor with the clauses set forth in paragraphs (b)(1) through (4) of this section.

- Clean Air Act and Federal Water Pollution Control Act:

D.1-Clean Air Act

- The contractor agrees to comply with all applicable standards, orders, or regulations issued pursuant to the Clean Air Act, as amended, 42 U.S.C. Section 7401 et seq.

- The contractor agrees to report each violation to the California Air Resources Board and understands and agrees that the California Air Resources Board will, in turn, report each violation as required to assure notification to the Department of Resources Recycling and Recovery, the California Governor’s Office of Emergency Services, Federal Emergency Management Agency (FEMA), and the appropriate Environmental Protection Agency Regional Office.

- The contractor agrees to include these requirements in each subcontract exceeding $150,000 financed in whole or in part with Federal assistance provided by FEMA.

D.2-Federal Water Pollution Control Act

- The contractor agrees to and the Federal Water Pollution Control Act, as amended, 33 U.S.C. Sections 1251 et seq.

- The contractor agrees to report each violation to the State Water Resources Control Board and understands and agrees that the State Water Resources Control Board will, in turn, report each violation as required to assure notification to the Department of Resources Recycling and Recovery, the California Governor’s Office of Emergency Services, Federal Emergency Management Agency (FEMA), and the appropriate Environmental Protection Agency Regional Office.

- The contractor agrees to include these requirements in each subcontract exceeding $150,000 financed in whole or in part with Federal assistance provided by FEMA.

- Suspension and Debarment

- This contract is a covered a transaction for the purposes of 2 C.F.R. pt. 180 and 2 C.F.R. pt. 3000.  As such the contractor is required to verify that none of the contractor, its principals (defined at 2 C.F.R. Section 180.995), or its affiliates (defined at 2 C.F.R. Section 180.905) are excluded (defined at 2 C.F.R. Section 180.940) or disqualified (defined at 2 C.F.R. Section 180.935).

- The contractor must comply with 2 C.F.R. pt. 180, subpart C and 2 C.F.R. pt. 3000, subpart C and must include a requirement to comply with these regulations in any lower tier covered transaction it enters into.

- This certification is a material representation of fact relied upon by the Department of Resources Recycling and Recovery.  If it is later determined that the contractor did not comply with 2 C.F.R. pt. 180, subpart C and 2 C.F.R. pt. 3000, subpart C, in addition to remedies available to the Department of Resources Recycling and Recovery, the Federal Government may pursue available remedies, including but not limited to suspension and/or debarment.

- The bidder or proposer agrees to comply with the requirements of 2 C.F.R. pt. 180, subpart C and 2 C.F.R. pt. 3000, subpart C while this offer is valid and throughout the period of any contract that may arise from this offer.  The bidder or proposer further agrees to include a provision requiring such compliance in its lower tier covered transactions.

- Byrd Anti-Lobbying Amendment, 31 U.S.C. Section 1352 (as amended)

Contractors who apply or bid for an award of $100,000 or more shall file the required certification.  Each tier certifies to the tier above that it will not and has not been used Federal appropriated funds to pay any person or organization for influencing or attempting to influence an officer or employee of a member of Congress in connection with obtaining any Federal contract, grant, or any other award covered by 31 U.S.C. Section 1352.  Each tier shall also disclose any lobbying with non-Federal funds that takes place in connection with obtaining any Federal award.  Such disclosures are forwarded from tier to tier up to the recipient who in turn will forward the certification(s) to the awarding agency.

Appendix A, 44 C.F.R. Part 18 – Certification Regarding Lobbying

Certification for Contracts, Grants, Loans, and Cooperative Agreements

The undersigned [Contractor] certifies, to the best of his or her knowledge, that:

(1) No Federal appropriated funds have been paid or will be paid to any person for influencing or attempting to influence an officer or employee of any agency, a Member of Congress, an officer or employee of Congress, or an employee of a Member of Congress on his or her behalf in connection with the awarding of any Federal contract, the making of any Federal grant, the making of any Federal loan, the entering into of any cooperative agreement, and the extension, continuation, renewal, amendment or modification of any Federal contract, grant, loan, or cooperative agreement.

(2) If any funds other than Federal appropriated funds (including profit or fee received under a covered Federal transaction) have been paid, or will be paid, to any person for influencing or attempting to influence an officer or employee of any agency, a Member of Congress, an officer or employee of Congress, or an employee of a Member of Congress on his or her behalf in connection with this Federal contract, grant, loan, or cooperative agreement , the undersigned shall complete and submit Standard Form-LLL, “Disclosure of Lobbying Activities”, in accordance with the instructions.

(3) The undersigned shall require that the language of this certification be included in the award documents for all subawards at all tiers (including subcontracts, subgrants, and contracts under grants, loans, and cooperative agreements) and that all subrecipients shall certify and disclose accordingly.

This certification is a material representation of fact upon which reliance is placed when this transaction was made or entered into.  Submission of this certification and disclosure is a prerequisite for making or entering into this contract imposed by 31, U.S.C. section 1352 (as amended by the Lobbying Disclosure Act of 1995).  Any who fails to file the required certification shall be subject to a civil penalty of not less than $10,000 and not more than $100,000 for each such failure.

The Contractor, _______________, certifies or affirms the truthfulness and accuracy of each statement of its certification and disclosure, if any.  In addition, the Contractor understands and agrees that the provisions of 31 U.S.C. Section 3801 et seq., apply to this certification and disclosure, if any.

_____________________________
Signature of Contractor’s Authorized Official

_____________________________
Name and Title of Contractor’s Authorized Official

_____________________________
Date

- Access to Records:  The following access to records requirements apply to this contract:

- The Contractor agrees to provide the Department of Resources Recycling and Recovery, the California Governor’s Office of Emergency Services, the FEMA Administrator, the Controller General of the United States, or any of their authorized representatives access to any books, documents, papers, and records of the Contractor which are directly pertinent to this contract for the purposes of making audits, examinations, excerpts, and transcriptions.

- The Contractor agrees to permit aby of the foregoing parties to reproduce by any means whatsoever of to copy excerpts and transcriptions as reasonably needed.

- The contractor agrees to provide the FEMA Administrator or his authorized representative access to construction or other work sites pertaining to the work being completed under the contract.

- In compliance with the Disaster Recovery Act of 2018, the Department of Resources Recycling and Recovery and the Contractor acknowledge and agree that no language in this contract is intended to prohibit audits or internal reviews by the FEMA Administrator or the Comptroller General of the United States.

- DHS Seal, Logo, and Flags:

The contractor shall not use the DHS seal(s), logos, crests, or reproductions of flags or likenesses of DHS agency officials without specific FEMA pre-approval.

- Compliance with Federal Law, Regulations, and Executive Orders

This is an acknowledgement that FEMA financial assistance will be used to fund this contract only.  The contractor will comply with all federal law, regulations, executive orders, FEMA policies, procedures, and directives.

- No Obligation by Federal Government

The Federal Government is not a party to this contract and is not subject to any obligations or liabilities to the non-Federal entity, contractor, or any other party pertaining to any matter resulting from the contract.

- Program Fraud and False or Fraudulent Statements or Related Acts

The contractor acknowledges the 31 U.S.C. Chapter 38 (Administrative Remedies for False Claims and Statements) applies to the contractor’s action.

- Required Affirmative Steps to Assure Certain Firms Are Used (Reference: 2 CFR 200.321)

During the performance of this contract, the contractor agrees, if subcontracts are to be let, to take the following affirmative steps:

(1) Placing qualified small and minority businesses and women's business enterprises on solicitation lists;

(2) Assuring that small and minority businesses, and women's business enterprises are solicited whenever they are potential sources;

(3) Dividing total requirements, when economically feasible, into smaller tasks or quantities to permit maximum participation by small and minority businesses, and women's business enterprises;

(4) Establishing delivery schedules, where the requirement permits, which encourage participation by small and minority businesses, and women's business enterprises;

(5) Using the services and assistance, as appropriate, of such organizations as the Small Business Administration and the Minority Business Development Agency of the Department of Commerce.

- Procurement of Recovered Materials (Reference 2 CFR 200.322)

The contractor must comply with section 6002 of the Solid Waste Disposal Act, as amended by the Resource Conservation and Recovery Act.

1) In the performance of this contract, the Contractor shall make maximum use of products containing recovered materials that are EPA- designated items unless the product cannot be acquired—

(i) Competitively within a timeframe providing for compliance with the contract performance schedule;

(ii) Meeting contract performance requirements; or

(iii) At a reasonable price.

(2) Information about this requirement, along with the list of EPA-designate items, is available at EPA’s Comprehensive Procurement Guidelines web site, https://www.epa.gov/smm/comprehensive-procurement-guideline-cpg-program.

| STATE OF CALIFORNIA | To be completed by Contractor |  |
| --- | --- | --- |
| Department of Resources Recycling and Recovery (CalRecycle) | Name of Contractor: |  |
| CalRecycle 74C (Rev. 06/10 for Contracts) | Contract #: | Work Order #: |

Recycled Content Certification

Check this box if no products, materials, goods, or supplies were purchased with contract dollars and submit to the CalRecycle Contract Manager.

This form to be completed by contractor. The form must be completed and returned to CalRecycle

with a row completed for each product purchased with contract dollars. Attach additional sheets if

necessary. Information must be included, even if the product does not contain recycled-content

material. Product labels, catalog/website descriptions, or bid specifications may be attached to this

form as a method of providing that information.  Add additional rows as needed.

| Contractor’s Name |  |  |  |  |  |  |  |  | Date |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Address |  |  |  |  |  |  |  |  |  |  |
| Fax |  |  |  |  | Phone |  |  |  |  |  |
| E-mail |  |  |  |  |  | Website |  |  |  |  |

| Product Manufacturer | Product Description / Brand | Purchase Amount ($) | 1Percent Postconsumer Material | 2SABRC Product Category Code | Meets SABRC |
| --- | --- | --- | --- | --- | --- |

Public Contract Code sections 12205 (a) (1) (2) (3) (b) (1) (2) (3).

I certify that the above information is true. I further certify that these environmental claims for recycled content regarding these products are consistent with the Federal Trade Commission’s Environmental Marketing Guidelines in accordance with PCC section 12205.

| Print name |  | Signature |  | Company |  | Date |
| --- | --- | --- | --- | --- | --- | --- |

(See footnotes on the back of this page.)

Postconsumer material comes from products that were bought by consumers, used, and then recycled. For example: a newspaper that has been purchased and read, next recycled, and then used to make another product would be postconsumer material.

If the product does not fit into any of the product categories, enter “N/A.”  Common N/A products include wood products, natural textiles, aggregate, concrete, electronics such as computers, TV, software on a disk or CD, or telephone.

- Product category refers to one of the product categories listed below, into which the reportable purchase falls. For products made from multiple materials, choose the category that comprises most of the product by weight, or volume.

Note: For reused or refurbished products, there is no minimum content requirement.

For additional information visit www.calrecycle.ca.gov/BuyRecycled/

| Code | Description | Minimum content requirement |
| --- | --- | --- |
|  | Product Categories (11) |  |
| 1 | Paper Products - Recycled | 30 percent postconsumer fiber, by fiber weight |
| 2 | Printing and Writing - Recycled | 30 percent postconsumer fiber, by fiber weight |
| 3 | Compost, Co-compost, and Mulch – Recycled | 80 percent recovered materials. i.e., material that would otherwise be normally disposed of in a landfill |
| 4 | Glass – Recycled | 10 percent postconsumer, by weight |
| 5 | Rerefined Lubricating Oil - Recycled | 70 percent re-refined base oil |
| 6a | Plastic – Recycled | 10 percent postconsumer, by weight |
| 6b | Printer or duplication cartridges | - Have 10 percent postconsumer material, or - Are purchased as remanufactured, or - Are backed by a vendor-offered program that will take back the printer cartridges after their useful life and ensure that the cartridges are recycled and comply with the definition of recycled as set forth in Section 12156 of the Public Contract Code. |
| 7 | Paint – Recycled | 50 percent postconsumer paint (exceptions when 50% postconsumer content is not available or is restricted by a local air quality management district, then 10% postconsumer content may be substituted) |
| 8 | Antifreeze – Recycled | 70 percent postconsumer material |
| 9 | Retreated Tires - Recycled | Use existing casing that has undergone retreading or recapping process in accordance with Public Resource Code (commencing with section 42400). |
| 10 | Tire- Derived - Recycled | 50 percent postconsumer tires |
| 11 | Metals – Recycled | 10 percent postconsumer, by weight |

## Proposal Completion Checklist

Please use this checklist to assist in the preparation of your Proposal package to ensure that all required items are included.

|  | Cover Letter with contact information and statements as required in the RFP. |
| --- | --- |
|  | Organizational information and Personnel Information (Resumes) |
|  | Technical Proposal (detailed Work Plan) |
|  | Samples of Written Work |
|  | Copy of Required License(s) (Secretary of State) |
|  | Cost Proposal Sheet (Attachment A) |
|  | Bidder Declaration Form REQUIRED- Write zero on form if no participation. (Attachment C) |
|  | Darfur Contracting Act Certification (Attachment E) |
|  | Iran Contracting Act Certification (Attachment F) |
|  | Civil Rights Law Certification (Attachment G) |
|  | Contractor Status Form (Attachment H) |
|  | Client References (Attachment I) |
|  | Byrd Anti-Lobbying Certification (see Attachment J, Sample Agreement, Exhibit G, Item F) |

The following number of PROPOSAL packages must be submitted as the Contractor’s response to this RFP:

|  | One (1) unbound reproducible original Proposal package marked “Original” |
| --- | --- |
|  | One (1) original, signed bid sheet in a separate sealed envelope marked “Proposal Cost-Do Not Open”. |
|  | Three (3) bound copy of the Proposal package marked “Copy”. Do not include the bid sheet in these copies. |
|  | One (1) Electronic copy of Proposal Package in Adobe Acrobat format with all documents in a single file, including the bid sheet and all other attachments. |

The following form is only required upon submittal as applicable pursuant to the provisions outlined in Section III, Submittal Requirements:

|  | Certification of Target Area Contract Preference Act |
| --- | --- |

The following forms are not required at the time of the proposal submission but will be required by the successful contractor during the contract period:

|  | Recycled Content Certification (end of Attachment J) |
| --- | --- |
|  | Small Business (SB) and Disabled Veteran Business Enterprise (DVBE) Subcontractor Payment Certification (Attachment D) |
|  | Payee Data Record (Standard Form 204) viewable at http://www.calrecycle.ca.gov/Contracts/Forms/default.htm) |

Please note that if any of the items are missing from the Proposal package, the package will be considered incomplete and will be disqualified from the process.