Department of Resources Recycling and Recovery

Notice to Prospective Proposers

March 3, 2020

You are invited to review and respond to this Request for Proposal (RFP) Primary, entitled “Organics Recycling Characterization Study” DRR19070.  In submitting your Proposal, you shall comply with the instructions herein.

Note that all Agreements entered into with the State of California will include by reference General Terms and Conditions, Special Terms and Conditions and Contractor Certification Clauses which are referenced in Section II of this package.

In the opinion of the Department of Resources Recycling and Recovery (CalRecycle) this RFP is complete and without need of explanation.  However, if you have questions, or should you need any clarifying information, the contact person for this RFP is:

Melissa Mojonnier

contracts@calrecycle.ca.gov

Phone: (916) 341-6048

Fax: (916) 319-7345

Please note that no verbal information given will be binding upon the State unless such information is issued in writing as an official addendum.

Melissa Mojonnier

Contract Administrator

Table of Contents

Section I	Overview	1

General Information	1

CalRecycle Contact Information	1

Service Needed	1

Contract Budget	1

Payment Withhold	1

Contract Term	2

Process Type	2

Process Schedule	2

Section II	Rules and Conditions	3

Introduction	3

Commitment	3

Antitrust Claims	3

Contractor’s Cost	4

Information	4

Written Questions	4

Addenda	5

Modification of Submittals	5

Errors in Submittals	5

Unreliable List	5

Electronic Waste Recycling	6

Use Tax	6

Subcontractors	6

Section III	Proposal Submittal Requirements	7

Introduction	7

Deadline	7

Addressing	7

Number of Copies	7

Document Printing	7

Cover Letter	8

Table of Contents	8

Summary	8

Methodology	8

Organization	9

Qualifications and Resources	9

References	9

Samples of Written Work	10

Contractor Eligibility	10

Licenses	10

Small Business (SB) Participation	10

Disabled Veteran Business Enterprise (DVBE) Participation	11

Disabled Veteran Business Enterprise (DVBE) Incentive Application	11

Target Area Contract Preference Act (TACPA)	12

Maximum Combined Preferences and Rules for Award	13

Section IV	Cost Proposal Submittal	14

Overview	14

Cost Breakdown	14

Travel and Per Diem	14

Section V	Evaluation and Selection	17

Introduction	17

Selection Process	17

Grounds for Rejection	18

Award of Agreement	18

Notice of Intent to Award	19

Rejection of Award	19

Protest of Award	19

Section VI	Description of Work	20

Work to be Performed	20

Tasks Identified	20

Contract/Task Time Frame	52

Location of Services	52

Control of Work	52

Section VII	Definition and Terms	54

Attachments	57

Cost Proposal Sheet	58

Proposal Scoring Sheet	60

Bidder Declaration	64

Small Business (SB) and Disabled Veteran Business Enterprise (DVBE) Subcontractor Payment Certification	66

Iran Contracting Act	68

Darfur Contracting Act	69

California Civil Rights Laws Certification	70

Contractor Status Form	71

Client References	72

DRAFT Standard Agreement (STD 213)	73

Proposal Completion Checklist	120

# Section I	Overview

## General Information

CalRecycle promotes a zero waste California in partnership with local government, industry, and the public. This means managing the estimated 76 million tons of waste generated each year by reducing waste whenever possible, promoting the management of all materials to their highest and best use, and protecting public health and safety and the environment.

## CalRecycle Contact Information

Department of Resources Recycling and Recovery

Physical Address: 	1001 I Street

Sacramento, CA 95814

CalRecycle Contracts Unit, MS-19A

Mailing Address:   	PO Box 4025

Sacramento, CA 95812-4025

Attn: Contracts Unit, MS-19A

Phone:  (916) 341-6048

FAX:  (916) 319-7345

EMAIL:  contracts@calrecycle.ca.gov

Any documents delivered in person shall be received by 2:00 p.m. on April 10, 2020 in the Visitor’s & Environmental Service Center located in the lobby of the CalEPA Headquarters Building at 1001 I Street, Sacramento, CA 95814.

## Service Needed

This Contract is for a three-part study to research and identify organic materials, compostable and potentially compostable packaging materials, and food service ware associated with food waste in California’s organic recycling stream that are not being recycled. The objective of this Contract is to gather useful and accurate composition data from sampling facilities throughout the state.

## Contract Budget

Subject to the availability of funds and approval by CalRecycle, there is a current maximum budget of $800,000 (eight hundred thousand dollars). CalRecycle reserves the right to amend the budget for this Agreement as needs arise.

## Payment Withhold

The provisions for payment under this contract will be subject to a ten percent (10%) withholding per task. The withheld payment amount will be included in the final payment to the contractor and will only be released when all required work has been completed to the satisfaction of CalRecycle.

## Contract Term

The term of this Agreement will span approximately 24 months and is expected to begin in June 2020. CalRecycle reserves the right to amend the term of this Agreement as needs arise.

## Process Type

Request for Proposal (RFP) (Primary Method).

## Process Schedule

This process will be conducted according to the following tentative schedule where all times are Pacific Time

| Advertisement Date | March 3, 2020 |
| --- | --- |
| Written Questions Due by 5:00 pm | March 19, 2020 |
| Submittals Due by 2:00 pm | April 10, 2020 |
| Cost Proposal Opening at 10:00 am | April 27, 2020 |
| Post Notice of Intent to Award | April 28, 2020 |

# Section II	Rules and Conditions

## Introduction

There are conditions that this RFP, submitting Proposers, Proposals and resulting Agreements are subject to and/or required to comply with.

## Commitment

Upon submittal of a Proposal, the Contractor has committed to comply with the following requirements:

- All items noted in RFP documents

- Special Terms and Conditions available for viewing at https://calrecycle.ca.gov/Contracts/Forms/SpeTermsCond.pdf

- General Terms and Conditions (GTCs) available for viewing at https://www.dgs.ca.gov/OLS/Resources/Page-Content/Office-of-Legal-Services-Resources-List-Folder/Standard-Contract-Language

- Contractor Certification Clauses (CCCs) available for viewing at https://www.dgs.ca.gov/OLS/Resources/Page-Content/Office-of-Legal-Services-Resources-List-Folder/Standard-Contract-Language

The above terms, conditions, and requirements are not subject to negotiation.  Any Proposal that reserves a right to negotiate or expresses any exception to the above terms, conditions, and requirements will be disqualified.  However, requests to revise any of the above terms, conditions, and requirements may be submitted during the formal question and answer period.  Any such requests shall include the current language, the proposed revised language, and the justification for the proposed revision. Any revisions are at the sole discretion of CalRecycle and will only be made under very limited circumstances in which the revisions apply to all Proposers and benefit or enhance the Contract.

If the Proposer fails to meet any of the requirements or comply with CalRecycle requests, CalRecycle can reject, disqualify, or remove the firm from the process. CalRecycle is not committed to award an Agreement resulting from this RFP.

## Antitrust Claims

In submitting a Proposal Package to a public purchasing body, the Proposer offers and agrees that if the Proposal Package is accepted, it will assign to the purchasing body all rights, title, and interest in and to all causes of action it may have under Section 4 of the Clayton Act (15 United States Code, § 15) or under the Cartwright Act (Chapter 2 [commencing with Section 16700] of Study 2 of Division 7 of the Business and Professions Code), arising from purchases of goods, materials, or services by the Proposer for sale to the purchasing body pursuant to the Proposal Package.  Such assignment shall be made and become effective at the time the purchasing body tenders final payment to the Proposer.  (See Gov. Code, § 4552.)

If an awarding body or public purchasing body receives, either through judgment or settlement, a monetary recovery for a cause of action assigned under this chapter, the assignor shall be entitled to receive reimbursement for actual legal costs incurred and may, upon demand, recover from the public body any portion of the recovery, including treble damages, attributable to overcharges that were paid by the assignor but were not paid by the public body as Study of the Proposal Package price, less the expenses incurred in obtaining that portion of the recovery.  (See Gov. Code, § 4553.)

Upon demand in writing by the assignor, the assignee shall, within one year from such demand, reassign the cause of action assigned under this Study if the assignor has been or may have been injured by the violation of law for which the cause of action arose and (a) the assignee has not been injured thereby, or (b) the assignee declines to file a court action for the cause of action.  (See Gov. Code, § 4554.)

## Contractor’s Cost

All costs resulting from the Contractor’s participation in the RFP process are at the firm’s expense.  No costs incurred by the Contractor participating in the RFP process will be reimbursed by CalRecycle.

## Information

All materials submitted in response to this RFP will become the property of CalRecycle and, as such, are subject to the Public Records Act (Gov. Code, § 6250, et seq.).  CalRecycle will disregard any language purporting to render all or portions of any RFP package confidential.

All information obtained or produced during the course of the Agreement will be made available to CalRecycle.

Any information obtained or produced during the course of the Agreement that qualifies as confidential or a trade secret(s) under the Public Records Act (PRA) or the Public Contract Code (PCC) and is thus exempt from disclosure under those statutes shall be so marked by the firm prior to submission to CalRecycle.  Any claims of confidentiality or trade secret(s) except as to information that qualifies as such under the PRA or PCC may result in disqualification.

CalRecycle will hold information obtained or produced during the course of the Agreement deemed confidential or trade secret(s) by the firm to the extent allowable by the California PRA and the PCC.

## Written Questions

The RFP includes a formal question and answer period in which Proposers have the opportunity to submit questions to the CalRecycle’s Contracts Unit regarding the RFP.  All inquiries shall be submitted in writing either by mail, fax, or e-mail to the CalRecycle Contact as listed in Section I no later than 5:00 pm on March 19, 2020 regardless of postmark.  If the inquiries are faxed, then the time and date on the fax must not be later than the due date and time.

Questions, suggestions, or objections regarding the content of this solicitation, including but not limited to, the purpose and scope of work, not submitted by the deadline for questions shall be deemed waived and may not be raised at a later time.

Oral communications with CalRecycle officers and employees shall be non-binding on the State and shall in no way exclude the Bidder of any obligations as set forth in this package.

E-mails and faxes should be clearly marked “Questions Relating to SOLICITATION DRR19070”

The questions and answers will be published in an Addendum to the IFB (see below, Addenda).

## Addenda

CalRecycle reserves the right to amend, alter, or change the rules and conditions of this RFP.

Any ambiguity, conflict, discrepancy, omission, or other error discovered in the RFP should immediately be reported to CalRecycle prior to the deadline for submission of written questions.  CalRecycle will issue addenda to address such issues.

## Modification of Submittals

A Proposal submitted prior to the submittal deadline, can be withdrawn or modified by the submitting Proposer.  The Proposer shall:

- Provide a written request

- Identify the requesting individual and their association to the Proposer

A Proposal cannot be withdrawn for modification after the submittal deadline has passed.

## Errors in Submittals

An error in a Proposal package may be cause for rejection of that Proposal.

CalRecycle may make certain corrections, if the Proposer’s intent is clearly established based on review of the complete Proposal.

## Unreliable List

Any Contractor or Subcontractor currently of CalRecycle Unreliable list, is ineligible to apply for or participate in this contract.

## Electronic Waste Recycling

If the Contractor or any Subcontractors participate in activities that result in the disposition of electronic components, they shall comply with the provisions of PRC Chapter 8.5.

## Use Tax

If, during the course of the Agreement, the Contractor will be involved in the re-sale of goods to the State, they shall comply with the requirements of Sections 6452.1, 6487, 6487.3, 7101, and 18510 of the Revenue and Taxation Code, in addition to Section 10295.1 of the PCC.

## Subcontractors

All Subcontractors identified in the Proposal, must be experts in their respective disciplines and capable of performing the tasks for which they are hired.

The Department of General Services (DGS), Office of Small Business and Disabled Veteran Business Enterprise Services (OSDS) oversees the Small Business (SB) and Disabled Veteran Business Enterprise (DVBE) certification programs. If awarded the Contract, the Contractor must use all of the SB and DVBE firms identified on the Bidder Declaration form.

Contractor understands and agrees that should award of this contract be based in part on their commitment to use the DVBE subcontractor(s) identified in their Proposal, per Military and Veterans Code (M&VC) section 999.5(e), a DVBE subcontractor may only be replaced by another DVBE subcontractor and must be approved by the DGS. Changes to the scope of work that impact the DVBE subcontractor(s) identified in the Proposal and approved DVBE substitutions will be documented by contract amendment.

Failure of Contractor to seek substitution and adhere to the DVBE participation level identified in the Proposal may be cause for contract termination, recovery of damages under rights and remedies due to the State, and penalties as outlined in M&VC section 999.9; or PCC sections 10115.10 and 4110 (applies to public works only).

CalRecycle reserves the right to approve substitutions of subcontractors, as long as, certified business participation levels remain unchanged.

# Section III	Proposal Submittal Requirements

## Introduction

Failure to follow the instructions contained in this document may be grounds for rejection of a Proposal.

CalRecycle may reject any Proposal if it is conditional, incomplete or contains irregularities.

CalRecycle may waive an immaterial deviation in a Proposal, if deemed in the best interest of CalRecycle.

## Deadline

The Proposal package shall be received by CalRecycle, at the address listed in Section I, Overview by 2:00 p.m. on April 10, 2020.

Proposals received after the deadline, will be considered late and returned to the Proposer unopened.

## Addressing

The Proposal package shall clearly state that it is in response to this RFP and note the RFP number listed with the direction of “Mailroom – do not open.”

## Number of Copies

The Proposer is required to submit all required documents in the following format:

- One original, non-bound hard copy marked “Original” (Do not include Cost Proposal Sheet in this set.)

- One original signed Cost Proposal Sheet in a separate sealed envelope marked “Cost Proposal - Do Not Open”

- Three (3) bound, hard copies of the bid package marked “Copy” (Do not include Cost Proposal Sheet in these sets.)

- One electronic copy on a USB flash drive viewable by Adobe Acrobat Reader.  The entire Proposal, including any attachments, shall be saved as a single document. (Do not include Cost Proposal Sheet in the electronic copy.)

It is the submitting Proposer’s responsibility to ensure that the electronic copy is formatted in Adobe Acrobat Reader and viewable by CalRecycle.

## Document Printing

All documents shall be submitted double-sided on paper with a minimum of 100% post-consumer recycled content fiber.

## Cover Letter

The cover letter shall be signed by an individual who is authorized to bind the Proposer and shall indicate that person's title or position. The cover letter shall be on the Proposer's company letterhead and contain the following information:

- Name and address of the Proposer submitting qualifications;

- Proposer’s Headquarters for purposes of this Agreement, if awarded;

- Name, telephone number, and e-mail address of a person who can be contacted if further information is required;

- Name, title, address, telephone number, and e-mail address of individual(s) with authority to execute a binding Agreement on behalf of the Proposer;

- Statement that personnel who will provide services under the Agreement will have the required certifications and that bidder will have qualified personnel available to meet the service needs;

- Statement attesting to the fact of the percentage of post-consumer recycled content fiber paper used in the compilation of the Proposal package;

- Statement stating that the Contractor and any Subcontractors to be used during the performance of the contract are eligible to contract with the State of California, pursuant to PCC section 10286; and

- List of Contractor’s and any subcontractor(s’) business names, identification of certified Small Business (SB) or Disabled Veteran Business Enterprise (DVBE) status, if applicable, and corresponding Office of Small Business and Disabled Veteran Business Enterprise Services (OSDS) Reference number(s) issued by DGS.

## Table of Contents

The information shall be organized as presented with corresponding page references.

## Summary

The Proposer shall include a brief overview of the project and summarize the Proposer’s approach to the work.

## Methodology

The Proposal shall include a draft study design (Work Plan) describing the methods to be employed to accomplish the contract activities described in Section VI Description of Work.  The methodology shall be described in sufficient detail to allow CalRecycle staff to evaluate the methods and shall address all tasks and items in the Scope of Work.

Proposals shall describe how the objectives will be met and the methods the Contractor will use. The description shall include not only what work will be performed, but how it will be performed.

The tasks described in the Scope of Work outline a general approach for meeting the requirements; however, alternative approaches for some or all of the tasks may be proposed if they meet or exceed the requirements in meeting the project objectives.

## Organization

Provide a brief description of the organization’s services and activities, including:

- Date of establishment

- History

- Location

- Any known conflicts of interest

## Qualifications and Resources

The prospective Contractor shall have the experience, qualifications, and resources to perform the required tasks of the project. The prospective contractor must have the experience, qualifications, and resources to perform the required tasks of the project. Because of the comprehensive nature and complexity of this study, Proposers shall demonstrate their experience in the following areas:

- conducting large-scale (regional or statewide) waste characterization studies including the development of a representative sampling plan and a plan for collecting samples from facilities with various processing flows and feedstocks;

- the collection of detailed field sorting data;

- working with disposal and/or processing facilities including coordinating field work and following health and safety plans; and

- ensuring data integrity through appropriate quality assurance and quality control (QA/QC) processes and data entry procedures.

Each Proposal must include a description of the resources to be used on the project while demonstrating an individual or team members’ abilities to perform the work. The Proposals must include resumes for the Project Manager, Personnel and Subcontractors, that include:

- Experience

- Knowledge

- Educational Background

- Professional Licenses where required by law or industry standards

## References

The Proposer’s team shall provide a minimum of three (3) verifiable references for the proposer and for each proposed subcontractor which support the above qualifications.

If a reference or project experience is unable to be verified, it will be disregarded.

## Samples of Written Work

The Proposer’s team shall include a copy of a verifiable written work that is similar in nature to the proposed project and deliverables.

At least one example should demonstrate each of the following:

- Knowledge of and understanding of California’s recycling management system in various parts of the state;

- Experience in implementing a large-scale facility-based characterization study including initial project set-up, site coordination, fieldwork, identifying when contingency plans have been implemented and steps taken, data preparation, and project deliverables;

- Knowledge of and understanding of conducting analysis of recyclable materials;

- Experience in implementing and adjusting a pre-determined work plan for characterization of materials including steps taken for analysis.

## Contractor Eligibility

The Proposer shall include a written declaration, stating that the Contractor and any Subcontractors to be used during the performance of the contract are eligible to contract with the State of California, pursuant to PCC section 10286.1.  The written declaration may be included in the cover letter.

## Licenses

The Contractor shall be an individual or firm qualified to do business in California.  Required documentation includes the following as applicable:

- A copy of the Proposer’s registration with the Secretary of State.

- Additionally, pursuant to the California Business and Professions Code, for services of a “professional” nature requiring a professional license issued by the CA Department of Consumer Affairs, Proposers shall submit a copy of the appropriate license(s) for each team member who will provide “professional” services under the contract.

## Small Business (SB) Participation

CalRecycle requires a minimum of twenty-five percent (25%) of the project services to be contracted to a California OSDS Certified SB that performs a commercially useful function.

This goal can be achieved by a combined effort of the prime and/or any Subcontractors, which includes:

- If the Proposer is a Certified OSDS SB, as defined in Section V Definitions and Terms, the Bidder Declaration form (Attachment C) shall be completed and submitted with the Proposal.

- If the Proposer has identified Subcontractors to be utilized to meet this goal, the Bidder Declaration form (Attachment C) shall be completed and submitted with the Proposal.

Small Business and non-small business may receive preference as set forth below.

For purposes of this RFP, references to “Small Business” include “Microbusiness” unless contrary to law.

## Disabled Veteran Business Enterprise (DVBE) Participation

CalRecycle requires a minimum of three percent (3%) of the project services to be contracted to a California OSDS Certified DVBE that performs a commercially useful function.

This goal can be achieved by a combined effort of the prime and/or any Subcontractors, which includes:

- If the Proposer is a Certified OSDS DVBE, as defined in Section V, Definitions and Terms, the Bidder Declaration form (Attachment C) shall be completed and submitted with the Proposal.

- If the Proposer has identified Subcontractors to be utilized to meet this goal, the Bidder Declaration form (Attachment C) shall be completed and submitted with the Proposal.

## Disabled Veteran Business Enterprise (DVBE) Incentive Application

Any Proposer competing in this process as a California certified DVBE, or as a non-DVBE certifying to subcontract a minimum of 3% of the total contract services to a California certified DVBE, will receive an incentive.  The incentive amounts for DVBE participation percent are as shown below:

1.  Five percent (5%) and above participation level = bid will receive five percent (5%) incentive calculation.

2.  Four percent (4%) participation level = bid will receive two percent (2%) incentive calculation.

3.  Three percent (3%) participation level = bid will receive one percent (1%) incentive calculation.

Certification must be provided by DGS, OSDS.

The incentive is available to a non-DVBE claiming a minimum of three percent (3%) California certified DVBE subcontractor participation. If claiming the non-DVBE subcontractor incentive, the bid response must include a list of the DVBE(s) with which you commit to subcontract in an amount of at least three percent (3%) of the net bid price with one of more California certified DVBEs. Each listed certified DVBE must perform a “commercially useful function” in the performance of the contract as defined in GC section 14837(d)(4).

The required list of California certified DVBE subcontracts must be attached to the bid response and must include the following: (1) subcontractor name, (2) address, (3) phone number, (4) a description of the work to be performed and/or products supplied, and (5) the dollar amount or percentage of the net bid price (as specified in the solicitation) per subcontractor.  Use the Bidder Declaration form to report this information.

Questions regarding certification should be directed to OSDC at (916) 375-4940.

The incentive is applied during the evaluation process and is only applied for responsive bids from responsible bidders proposing the percentage(s) of DVBE participation for the incentive(s) specified above.

For award based on low price, the incentive is applied by reducing the bid price by the amount of incentive as computed from the lowest responsive and responsible bid price.  The computation is for evaluation purposes only.  Application of the incentive shall not displace an award to a small business with a non-small business.

Application of the incentive shall not displace an award to a DVBE with a non-DVBE.

A copy of the Proposer’s DVBE certification should be included with the proposal Package.

If awarded, the Proposer who has made a commitment to achieve disabled veteran business enterprise (DVBE) participation, must within 60 days of receiving final payment under this agreement (or within such other time period as may be specified elsewhere in this agreement) certify in a report to the awarding department: (1) the total amount the prime contractor received under the contract; (2) the name and address of the DVBE(s) that participated in the performance of the contract; (3) the amount each DVBE received from the prime contractor; (4) that all payments under the contract have been made to the DVBE(s); and (5) the actual percentage of DVBE participation that was achieved.  A person or entity that knowingly provides false information shall be subject to a civil penalty for each violation (M&VC, § 999.5(d)).  Refer to Attachment D to fulfill this requirement.

## Target Area Contract Preference Act (TACPA)

If the budget for services outlined in this announcement, exceeds $100,000, CalRecycle will grant a preference for TACPA qualified Proposers.

The Proposer shall provide reasonable demonstration of contract labor hours and certify that they will comply with the requirements of the TACPA.

If the Proposer is qualified for this preference, the TACPA Preference Request Form shall be included in the Proposal submittal.

The form may be downloaded at https://www.calrecycle.ca.gov/contracts/forms.

## Maximum Combined Preferences and Rules for Award

In combination with any other preferences (TACPA, SB, or DVBE participation) the maximum limit of the combined preferences is 15% of the bid amount and, in no case, more than $100,000.00 per solicitation.

Preference programs for TACPA or the non-SB subcontracting preference cannot displace a direct award to a certified SB. In the event of a tie between a SB and a firm that is SB and DVBE, the award shall be made to the firm that is SB and DVBE.

# Section IV	Cost Proposal Submittal

## Overview

The Cost Proposal shall be submitted in a separate, sealed envelope by the due date identified in the Schedule of Section I.

The envelope shall read “Cost Proposal - Do Not Open”.

## Cost Breakdown

Attachment A, Cost Proposal Sheet, must be completed, specifying the total cost and including detailed project costs and subcontractor commitments, identified by each task and dollar amount. The awarded Proposer’s invoices shall be itemized as shown in the submitted Cost Proposal Sheet.

All travel must be itemized in the Attachment A, under Column 6.  Travel expenses and per diem cannot exceed the rates established by CalHR. For further travel information read the following section, Travel and Per Diem.

The costs identified in the Attachment A, should take into consideration the length of the contract, rise in salaries and overhead costs

If fringe benefits and/or overhead are not specifically itemized in Attachment A and if the Proposer inserts a $0, Proposer shall explain on Attachment A why these line items are not itemized.  A blank space for either fringe benefits or overhead will be grounds for immediate disqualification.

Failure to include on the Cost Proposal Sheet budgeted costs for all tasks included in the Scope of Work will be grounds for disqualification.

The Cost Proposal sheet is a self-contained document for purposes of calculating cost points and evaluating whether all information required by the RFP has been submitted. Therefore, all information (such as explanations of $0 instead of itemized costs) shall be included on the Cost Proposal sheet. Reference by incorporation to the Proposal is not acceptable.

The amounts identified in Attachment A may not be changed and will remain in effect for the life of the Agreement.

## Travel and Per Diem

All travel must be pre-approved by the Contract Manager.  When determining the least costly travel method, the Contractor should take into consideration not only direct expenses, but also the time billed.  If the Contractor is unsure what least costly method may be, he or she shall consult with the Contract Manager.  All travel will be reimbursed at the excluded employee travel rates in accordance with the California Code of Regulations Title 2, Division 1, Chapter 3, Subchapter 1, Article 2, Section 599.615.1 et seq.  At the time of the RFP release, the rates listed below apply.  However, they are subject to change and the Contractor will be held to the State per diem rates in effect at the time of travel.  Per diem (lodging, meals and incidentals) will not be reimbursed for travel within 50 miles of Contractor’s headquarters.

- Lodging (receipts required) per day:

All counties/cities located in California (except as noted below):

Actual lodging expense, supported by a receipt, up to $90 per night, plus tax and mandatory fees.

Napa, Riverside, and Sacramento Counties:

Actual lodging expense, supported by a receipt, up to $95 per night, plus tax and mandatory fees.

Marin:

Actual lodging expense, supported by a receipt, up to $110 per night, plus tax and mandatory fees.

Los Angeles, Orange, and Ventura Counties and Edwards AFB, excluding the City of Santa Monica:

Actual lodging expense, supported by a receipt, up to $120 per night, plus tax and mandatory fees.

Monterey, San Diego Counties:

Actual lodging expense, supported by a receipt, up to $125 per night, plus tax and mandatory fees.

Alameda, San Mateo, and Santa Clara Counties:

Actual lodging expense, supported by a receipt, up to $140 per night, plus tax and mandatory fees.

City of Santa Monica:

Actual lodging expense, supported by a receipt, up to $150 per night, plus tax and mandatory fees.

San Francisco:

Actual lodging expense, supported by a receipt, up to $250 per night, plus tax and mandatory fees.

- Meals (actual expense) (up to $7 for breakfast, $11 for lunch and $23 for dinner) – up to a maximum of $41 per day

- Incidentals – up to a maximum of $5 per day.

- Coach airfare, mid-size/economy rental cars, parking and fuel – actual costs verified by bills or receipts.  Expenses for rental car insurance, fuel for rental cars purchased from the rental car company, and additional air travel expenses such as preferred boarding, will not be reimbursed.  First Class or Business Class air travel is not allowed.  Airport parking must be at the most economical rate.  Expenses for one way rental car expense (i.e. charges for returning a rental car to a location other than that from which it was rented) will only be reimbursed if preapproval is given by the Contract Manager prior to the expense being incurred.

- Personal Vehicle Use for travel is reimbursed at $0.575 per mile; however fuel will not be reimbursed if a personal vehicle is used.

# Section V	Evaluation and Selection

## Introduction

CalRecycle will perform a Pre-Qualification Evaluation process to ensure that the Proposer has included all required documentation in the Proposal submittal.  Each Proposal will first be reviewed to ensure the following items: Proposal is received by date and time specified; Proposal contains all the required documents (see Proposal Completion Checklist); and that the Proposal meets the format requirements specified.

If a Proposal package does not meet all of the requirements set forth in this RFP, it will be considered non-responsive and rejected from further competition.

Those Proposer’s submittals that pass this review will be forwarded to the Selection Committee for Evaluation.

## Selection Process

The evaluation team will, individually or as a team, review, evaluate, and numerically score all Proposals passing the Pre-Qualification Evaluation, utilizing the following scoring system to assign points.  Following this chart is a list of the considerations that the evaluation team may take into account when assigning individual points to a technical Proposal.

| Points | Interpretation | General basis for point assignment |
| --- | --- | --- |
| 0 | Inadequate | Proposal response (i.e., content and/or explanation offered) is inadequate or does not meet CalRecycle’s needs/requirements or expectations. The omission(s), flaw(s), or defect(s) are significant and unacceptable. |
| 1 | Barely Adequate | Proposal response (i.e., content and/or explanation offered) is barely adequate or barely meets CalRecycle’s needs/requirements or expectations. The omission(s), flaw(s), or defect(s), are inconsequential and acceptable. |
| 2 | Fully Adequate | Proposal response (i.e., content and/or explanation offered) is fully adequate or fully meets CalRecycle’s needs/requirements or expectations. The omission(s), flaw(s), or defect(s), if any, are inconsequential and acceptable. |
| 3 | Excellent or Outstanding | Proposal response (i.e., content and/or explanation offered) is above average or exceeds CalRecycle’s needs/requirements or expectations. Minimal weaknesses are acceptable. Proposer offers one or more enhancing feature, method, or approach that will enable performance to exceed our basic expectations. |

In assigning points for individual rating factors, raters may consider issues including, but not limited to, the extent to which a Proposal response:

- Is lacking information, lacking depth or breadth or lacking significant facts and/or details, and/or;

- Is fully developed, comprehensive and has few if any weaknesses, defects or deficiencies, and/or;

- Demonstrates that the Proposer understands CalRecycle’s need’s, the services sought, and/or the Contractor's responsibilities, and/or;

- Illustrates the Proposer’s capability to perform all services and meet all scope of work requirements, and/or;

- If implemented, will contribute to the achievement of CalRecycle’s goals and objectives, and/or;

- Demonstrates the Proposer’s capacity, capability and/or commitment to exceed regular service needs (i.e., enhanced features, approaches, or methods; creative or innovative business solutions).

Responses which only restate or paraphrase information found in the RFP will receive 0 or 1 point.

## Grounds for Rejection

All Proposals may be rejected whenever the determination is made that the Proposals received are not really competitive, when the cost is not reasonable, or when the cost exceeds the amount expected.

Additionally, a Proposal may be rejected if:

- It is received after the due date and time for submittal.

- The Cost Proposal submittal is unsigned.

- The Cost Proposal is not prepared as required by the RFP.

- The Proposer has been prohibited from contracting with the State by the Department of Fair Employment and Housing.

- The Proposer has received a substantive negative contract performance from the State.

- Any items required by the RFP are not included with the submittal.

No Proposal may be rejected arbitrarily or without reasonable cause.

## Award of Agreement

The award of this Agreement will be to the lowest responsive responsible Proposer meeting all of the RFP requirements.

In the event of a tie, CalRecycle may utilize a tie breaker to determine the winning Proposer.  The tie breaker will be determined based on which Proposer has the most SB and DVBE participation identified in the bid package.

CalRecycle reserves the right to not award an Agreement.

## Notice of Intent to Award

CalRecycle will post a notice of intent to award this Contract five (5) working days prior to the award being made.

Notice of the intent to award will be posted on CalRecycle’s website at https://www.calrecycle.ca.gov/contracts/forms and at the headquarters building noted in Section I.  It is the Proposer’s responsibility to check one of these locations for a copy of the Notice of Intent to Award.

## Rejection of Award

If the Proposer fails to enter into a satisfactory Agreement within a reasonable timeframe after the award is made, CalRecycle may deem that the Proposer has rejected the award.

CalRecycle reserves the right to disqualify the awardee and award the Agreement to the next highest ranked Proposer.

## Protest of Award

A Proposer may protest the proposed award by filing an official protest with the Department of General Services.  The protest shall be filed after the notice of intent to award the contract, but before the actual award.

Within five (5) working days of the initial protest filing, the Proposer shall submit a detailed written statement with information that supports that the Proposer would have been awarded the contract and the grounds for that position.

The Agreement will not be awarded until a decision has been made on the filed protest.

The protest documents should be sent via registered mail to the following parties:

Department of General Services

Office of Legal Services

Attn: Protest Coordinator

707 Third Street, 7th floor

Sacramento, CA  95605

Fax (916) 376-5088

Department of Resources Recycling and Recovery

Attn: Contracts Unit

1001 I Street, MS-19A

Sacramento, CA  95814

Fax (916) 319-7345

Email contracts@calrecycle.ca.gov

# Section VI	Description of Work

## Work to be Performed

The Proposer shall describe how to sample recycling streams in three studies based on the following requirements.

Study 1: The Processing Facility-based Residual Characterization Study – Sampling material recovery facility and processing facility residuals, and pre-sorted rejections destined for disposal, including dual-stream processing lines, commingled single stream processing lines, mixed waste processing lines, and organic processing lines with food waste inflows to determine the composition of material destined for disposal at composting and anaerobic digestion facilities.

Study 2: The Organics Recycling Inflow Characterization Study – Sampling incoming material to composter and anaerobic digestion facilities that accept food waste from commercial and residential sources, including solid waste permitted composting facilities accepting material from residential and commercial sources and anaerobic digestion facilities accepting material from residential and commercial sources to determine the composition of incoming organic material sent from a variety of generators, including but not limited to recyclable processing facilities (processed), transfer facilities (unprocessed), direct hauled from generators (unprocessed), and anaerobic digestion facilities (processed). This stream must be sampled in order to improve understanding of the materials/ material fragments found in the residual/rejected stream in Study 3 of the study.

Study 3: The Organics Recycling Residuals Characterization Study – Sampling material destined for disposal from composter and anaerobic digestion facilities that accept food waste (e.g., biosolids, overs, residuals, rejects, physical contaminants), including solid waste permitted composting facilities and anaerobic digestion facilities to determine the residual composition of traditional recycling and organic recycling processing lines.

## Tasks Identified

The following apply to Tasks 1 through 3

- The Proposer shall have a health and safety plan, implement health and safety measures, conduct training and monitor effectiveness.

- The Proposer shall comply with all local, state, and federal health and safety codes, regulations, and laws.

- The Proposer shall provide all equipment needed for fieldwork, including health and safety equipment. During the initial site recruitment, CalRecycle will determine if a loader/bobcat and driver are available on-site. If a loader/bobcat or similar equipment and a certified driver are not available, the Proposer shall arrange to rent a loader/bobcat or similar equipment and provide a certified driver.

- The Proposer shall accommodate observation by the Contract Manager, other CalRecycle staff, and possibly other interested parties, at the sampling sites.

- The Proposer shall implement QA/QC measures in the field to ensure the accuracy of the data collected.

Task 1 – Initial Meeting(s) to Review Proposed Study Design (Work Plan)

- The Proposer shall meet with the Contract Manager in person at the CalRecycle office in Sacramento (subsequent meetings can be virtual) to identify logistical details and fine-tune the Work Plan.  Discussion will pertain to:

- Study design as submitted in the Proposer proposal.

- Tentative schedule for when subsequent tasks will begin (proposed by Contractor).

- The timeline and logistics for sampling.

- Estimated number of samples that can be accurately collected in a day.

- Replacement site recruitment criteria (i.e., amount of time to recruit replacements dependent on days before scheduled sampling).

- The targeted materials to be included for each study.

- Additional information required by subsequent tasks.

- For the Processing Facility-based Residual characterization Study: the potential sampling locations, lines for sampling, and number of samples.

- For the Organics Recycling Inflow Characterization Study: the potential sampling locations, number of samples from inflow types (processed and unprocessed), and number of samples.

- For the Organics Recycling Residuals Characterization Study: the potential sampling locations and number of samples.

- CalRecycle reserves the right to update locations if necessary.

- The Proposer shall submit the revised Work Plan based on decisions made at the initial meeting to the Contract Manager for approval within 15 calendar days of the meeting date.

- The Contract Manager will review this submittal to ensure it accurately represents the agreed upon details and is consistent with both this RFP and with the Proposal. The Contract Manager will respond within 15 calendar days with any needed final edits to the proposed revisions.

- The Proposer shall make required changes, if any, and submit to the Contract Manager within 15 calendar days of receiving the edits.

- No work shall commence on subsequent tasks without the Contract Manager’s written approval of the Work Plan.

Task 2 – Coordinate with Processing Facilities and Determine Field Schedule

- Within 15 days of receiving the final list of sampling locations, the Proposer shall provide the Contract Manager with the tentative number of sampling days expected at each site, the number of samples to be sorted at each site, and instruction on whether additional information is needed. The Contract Manager will provide the Proposer with the final list of sampling locations at least 45 calendar days before sampling begins and if additional information is needed, the Contract Manager will attempt to provide it within 10 calendar days of receiving notice.

- The Proposer shall promptly contact each location/site to confirm all of the logistics, specifically sample collection date(s), that health and safety requirements have been met, the availability of a loader/bobcat and driver if needed, and any other factors which will affect the sampling.

- The Proposer shall notify the Contract Manager by email within two business days of learning of a circumstance which will negatively impact the field schedule, requesting replacement sampling sites if needed.

- The Proposer shall ensure accurate and representative sampling at each sampling site by incorporating information on variations in site operations, residual flows, on-site processing/handling, and other relevant information into a sampling plan. At a minimum this information shall include:

- Type of facility.

- How facility manages their rejects and residuals, including any sent for further processing.

- Type of sorting and screening done and any other pre- or post-processing, like floor sorts, etc.

- Flow diagram and quantity of material destined for disposal from pre-sort and all ejection points.

- The origins of any pre-processed material accepted that may be sampled.

- Estimated percentage of inflow from commercial and residential sectors.

- Average length of active phase (Study 3).

- At least 15 calendar days before each sampling period begins, the Proposer shall provide the Contract Manager with:

  - a tentative schedule for sampling site order.

  - an overall schedule for fieldwork, describing start-up tasks, travel, set-up, and sorting days, and confirm the number of samples at each site and from each line.

- The Proposer shall address any concerns the Contract Manager identifies within 7 calendar days of receiving notice from the Contract Manager of any identified concerns. The Contract Manager will review the schedule and identify any concerns within 7 calendar days of receiving it.

- The Proposer shall follow the agreed upon final coordination and logistical arrangements with each site.

Task 3 – Perform Fieldwork/ Field Sampling and Sorting at Processing Facilities

- Task 3 Fieldwork for STUDY 1-Processing Facility-based Residual Characterization Study:

- The Proposer shall collect samples of residuals and pre-sort rejects from selected processing lines at sampling sites. Samples will represent only materials destined for disposal. The Proposer shall apply the methodology proposed and accepted by CalRecycle to collect a representative sample of residuals, based upon the processing flow and how residuals are managed and stored at each facility. The processing facility sampling shall result in data which allows the Proposer to produce an overall composition for residual disposal that accurately represents the proportions from the different ejection points. The Proposer shall also capture pre-sort rejects material removed before processing, overs (items that are too large for the processing system), unders (items that are too small for the processing system), and other materials separated for disposal.

- The Proposer shall identify the source sector (the location from which material is generated, i.e., from residential, commercial, industrial, or mixed residential and commercial pickups), or at a minimum the proportion of the incoming recycling stream from each sector when it is not possible to distinguish between source sectors, based on information provided by the facility.

- The Proposer shall hand-sort samples into individual material types on the finalized Processing Facility Material List (List A).

- The Proposer shall characterize fines (materials too fine to sort) according to the methodology laid out in their study plan and confirmed at the initial meeting described in Task 1.

- The Proposer shall make their best judgement to categorize the material that is difficult-to-sort due to adhesion, wetness, or partial decomposition and separate joined materials (such as a zip lock bag with metal screws in it) when it is practical to do so.

- The Proposer shall take and provide digital images with a minimum resolution of 12-megapixels of each load/sample, placing the sample number on, adjacent, or near the sample clearly identifying the unique load/sample ID number, location, and date.

- The Proposer shall assign each digital image file an electronic filename that correlates to the unique load/sample ID (e.g., Sample 1 from Facility A pictures are labeled Facility A_1_1, Facility A_1_2, etc.).

- The Proposer shall take a minimum of two clear digital images of the residual sample (covering 100% of sample combined), breaking open garbage bags and/or spreading out the sample to obtain acceptable images if necessary, before the sample is sorted. For each remainder composite category and mixed residue category, the Proposer shall take a digital image of the picture of the contents spread out on the ground from one sample at each facility throughout all of Study 1 sampling. For all other categories, the Proposer shall take a digital image of each material type from one sample at each facility throughout all of Study 1 sampling.

- The Proposer shall record the weight of each sorted material type and total sample weight (in decimal pounds), using a scale that is accurate to within 0.01 pounds and which is connected to a computer to record weights.

Task 3 Fieldwork for STUDY 2-Organics Recycling Inflow Characterization Study

- The Proposer shall collect samples of incoming material (prior to on-site processing) from selected sampling sites. Samples will only be taken from loads that include food waste and/or mixed materials. The Proposer shall apply the methodology proposed and accepted by CalRecycle to collect a representative sample from processed and unprocessed incoming loads from both residential and commercial sources.

- The Proposer shall hand-sort all samples into individual material types on the finalized Organics Facility Material List (List B).

- The Proposer shall make their best judgement to categorize the material that is difficult-to-sort due to adhesion, wetness, or partial decomposition and separate joined materials (such as a zip lock bag with metal screws in it) when it is practical to do so.

- The Proposer shall take and provide digital images with a minimum resolution of 12-megapixels of each load/sample, placing on, adjacent, or near the sample a written sample number clearly identifying the unique load/sample ID number, location, and date, and shall assign a filename to each digital image file which correlates to the unique load/sample ID (e.g., Sample 1 from Facility A pictures are labeled Facility A_1_1, Facility A_1_2, etc.).

- The Proposer shall take a minimum of two clear images of the residual sample before it is sorted that capture a clear shot of all the material in the sample (two pictures covering 100% of sample).

- If needed, the Proposer shall break open garbage bags and/or spread out the sample to obtain adequate digital images.

- For each remainder composite category and mixed residue category, the Proposer shall take a digital image of the picture of the contents spread out on the ground from one sample at each facility throughout all of Study 2 sampling. For all other categories, the Proposer shall take a digital image of each material type from one sample at each facility throughout all of Study 2 sampling.

- The Proposer shall record all characterization data for each sample, including:

- the weight of each sorted material type,

- the total sample weight,

- the sector origin for sample (residential, commercial or mixed), and

- whether or not the sample has been processed or not before delivery to the compost or anaerobic digestion operation (some operations may be on the same site as recyclable processing facilities).

- The Proposer shall record weights in decimal pounds using a scale that is accurate to within 0.01 pounds and is connected to a computer to record weights.

Task 3 Fieldwork for STUDY 3 - Organics Recycling Residuals Characterization Study

- The Proposer shall collect samples of material destined for landfill from selected sites. Samples will only be collected from materials generated from pre- and post-processing (i.e., before and after composting or digestion process) from loads of materials that include food from residential and/or commercial sources. The samples themselves may or may not include identifiable food. The Proposer shall apply the methodology proposed and accepted by CalRecycle to collect a representative sample of residuals, based upon the processing flow and how residuals are managed and stored at each facility. The Proposer shall capture pre-sort rejects material removed before processing, overs, unders, and other materials separated for disposal.

- The Proposer shall determine if any pre-sort rejects or residuals (e.g. overs, unders) are sent for further processing, and if so, where and what quantity or proportion of the residual material.

- The Proposer shall hand-sort all samples into individual material types on the finalized material list (List B).

- The Proposer shall take digital images, with a minimum resolution of 12-megapixels, of each load/sample, placing a sample number on, adjacent, or near the sample clearly identifying the unique load/sample ID number, location, and date.

- The Proposer shall assign to each digital image a filename which correlates to the unique load/sample ID (e.g. Sample 1 from Facility A pictures are labeled Facility A_1_1, Facility A_1_2, etc.).

- The Proposer shall take a minimum of two clear images of the residual sample before it is sorted, which clearly capture all of the material in the sample (two pictures covering 100% of sample), breaking open garbage bags and/or spreading out the sample, if necessary to obtain adequate digital images.

- For each remainder composite category and mixed residue category, the Proposer shall take a digital image of the contents spread out on the ground from one sample at each facility throughout all of Study 3 sampling. For all other categories, the Proposer shall take a digital image of each material type from one sample at each facility throughout all of Study 3 sampling.

- The Proposer shall record all characterization data for each sample, including:

  - The weight of each sorted material type, AND

  - the total sample weights.

- The Proposer shall record weights in decimal pounds using a scale that is accurate to within 0.01 pounds and is connected to a computer to record weights.

Task 4 – Data Entry and Data QA/QC

- The Proposer shall provide sample printouts displaying database or spreadsheet format to the Contract Manager for approval.

- The Proposer shall implement QA/QC measures when providing field-sorting data for each sorted sample (weight of each material type in the sample) and total sample weight for all study Parts.

- The Proposer shall perform all data entry and follow all quality control measures in their plan to ensure the accuracy of the data entered. The Proposer shall resolve any errors or discrepancies in data discovered during quality control activities and/or review by the Contract Manager.

- The Proposer shall enter all data collected into electronic spreadsheets (e.g., Microsoft Excel) compatible with CalRecycle’s computer system. The Contract Manager will approve the format and software. The Proposer shall present the data in a format such as in Sample Data Format. The Proposer shall submit all final data to CalRecycle in electronic form (e.g., via e-mail or uploaded to a secure shared drive).

- The Proposer shall submit complete data for each sample, including, at a minimum:

- unique sample ID number,

- name of facility/site sample was collected from (unless privacy/confidential concerns and prior agreement between facility and CalRecycle),

- date of collection,

- total sample weight,

- weight of each component in the samples by material type,

- data used to calculate amounts,

- any notes on special circumstance or other information, as applicable, and

- all digital images.

- The Proposer shall submit final and correct data, after the Proposer has thoroughly reviewed and subjected the data to stringent QA/QC procedures.

- The Proposer shall submit all data required for the three studies.

- The Proposer shall identify data limitations CalRecycle should consider for its data analysis.

- The Contract Manager shall review the submitted data to ensure it is complete, understandable, and usable for subsequent analyses. The Proposer shall respond to any questions and address any problems or discrepancies found by the Contract Manager within 15 calendar days.

Task 5 – Submit Field Data and Summary Reports to CalRecycle

- During the sample collection periods, the Proposer shall provide weekly status reports in the format of the Sample Weekly Report.  Upon request by the Contract Manager, the Proposer shall provide monthly status reports outside the field work period. The reports shall include project statuses including progress made, work done and work pending, and any deviation from the plan and provide a detailed explanation for the deviation. When appropriate, these reports shall also include meeting minutes.

- Not more than 20 calendar days after the completion of data collection, the Proposer shall notify the Contract Manager if there are any changes or corrections to the data already submitted and submit the corrected data.

- Not more than 20 calendar days after the end of the sampling period, the Proposer shall prepare and submit to the Contract Manager a report summarizing information on all samples completed including the following:

- The total number of samples collected and characterized,

- For each sample, corresponding site names the samples were obtained from,

- For each sample, the sector and/or subsector (where recorded),

- A description and explanation of any differences between the final sampling plan and the actual field sampling performed, and

- A description of any unusual circumstances.

CalRecycle Responsibilities:

- For all three studies, CalRecycle is responsible for:

  - Recruiting sampling sites. The Contractor’s suggested or desired sites will be taken into consideration. A list of possible composting and anaerobic digestion sites is attached (Table 1 and Table 2).

  - If a replacement site is needed, and dependent on how soon the replacement is needed, CalRecycle will secure a replacement site in the same region or reallocate those samples. This replacement criteria will be determined at the initial meeting outlined in Task 1.

  - Upon receiving feedback about material types from the Contractor, CalRecycle may elect to change the material type list.

  - CalRecycle will conduct analyses of the data and prepare any final reports.

- For the Processing Facility-Based Residual Characterization Study:

  - CalRecycle will prioritize recruiting processing facilities that have both organic processing lines that handle food waste and traditional commodity recycling lines but acknowledges that there are a limited number of these facilities.

  - CalRecycle anticipates most of the recruited sites will be adjacent to or in the San Francisco Bay Area, Los Angeles Basin, and the Central Valley.

  - CalRecycle will determine the material types for hand-sorting characterizations (from Processing Facility Material – List A).

- For the Organics Recycling Inflow Characterization Study:

  - CalRecycle will recruit only:

    - Solid waste permitted anaerobic and aerobic composting facilities accepting food waste.

    - Anaerobic digestion facilities accepting food waste as a feedstock.

  - CalRecycle anticipates most of the recruited sites will be adjacent to or in the San Francisco Bay Area, Los Angeles Basin, and the Central Valley.

  - CalRecycle will determine the material types for hand-sorting characterizations (from Organics Facility Material - List B).

- For the Organics Recycling Residuals Characterization Study:

  - The same facilities used for Study 2 of the sampling will be prioritized for Study 3. If a selected organics processing facility does not wish to participate in both Studies, but only one, the Contractor will allocate more samples to another selected facility or a new facility (which CalRecycle will recruit).

  - CalRecycle anticipates most of the recruited sites will be adjacent to or in the San Francisco Bay Area, Los Angeles Basin, and the Central Valley.

  - CalRecycle will determine the material types for hand-sorting characterizations (from Organics Facility Material - List B).

List A – Processing Facility Material List and Definitions by Category

| Total | Category Code | Material Type and Definition | Examples |
| --- | --- | --- | --- |
| 1 | P1 | Uncoated Corrugated Cardboard means a paper laminate usually composed of three layers. The center wavy layer is sandwiched between the two outer layers. This type does not include paperboard boxes such as cereal and tissue boxes. Excludes glossy and waxed cardboard. | - shipping and moving boxes - sheets and pieces used as dividers in boxes - very clean pizza boxes (no food residue and only lightly stained) |
| 2 | P2 | Coated Corrugated Cardboard means a paper laminate usually composed of three layers. The center wavy layer is sandwiched between the two outer layers. It has a glossy coating on the inside, outside or both sides. This type does not include paperboard boxes such as cereal and tissue boxes. Excludes non-glossy, uncoated cardboard. | - computer packaging cartons - boxes used for primary packaging of various consumer goods |
| 3 | P3 | Uncoated Paper means all non-corrugated paper and paperboard that is not coated with another material. Can be bleached or colored. May be contaminated with food and/or moisture. | - paper grocery bags and other kraft bags - lunch bags - rice, flour and sugar bags - white office type paper and mail - envelopes without plastic windows - newspapers and election guides - manila envelopes and index cards - toilet paper and paper towel tubes |
| 4 | P4 | Coated Paper means all non-corrugated paper that is coated with another material, making the item glossy or waxy. This includes most paperboard packaging. May be contaminated with food and/or moisture. | - magazines - newspaper ad inserts - glossy brochures and catalogs - wrapping paper - breakfast cereal and frozen food boxes - cigarette cartons |
| 5 | P5 | Paper/Fiber Food Service Ware means items made mostly of paper that are used to consume, contain, or transport prepared food items. Includes paper and molded fiber, including compostable and non-compostable items. May be contaminated with food and/or moisture. | - plates, bowls, cups, and utensils - straws and stirrers - take-out containers - pizza boxes - bakery/bread bags - condiment cups |
| 6 | P6 | Aseptic Containers and Gable-top Cartons means bleached polycoated paperboard containers or paper containers with a foil liner of various sizes and shapes that contain shelf-stable food products (i.e., aseptic containers) and paper-based cartons with a triangular top used for refrigerated and non-refrigerated items (i.e., gable-top cartons) Containers may include a plastic pour spout as part of the container. | - containers for apple juice, soup, soy/rice milk - cartons used for milk, egg substitutes, and juice - gable-top containers used for snacks |
| 7 | P7 | Padded Envelopes – Paper means envelopes with a paper exterior, that may have plastic or other another material lining the interior of the envelope. Excludes envelopes with a plastic window. | - Kraft padded shipping envelopes - Kraft poly bubble mailers |
| 8 | P8 | Remainder/Composite Paper means items made mostly of paper that do not fit into any of the other paper types or are combined with large amounts of other materials. These are items that do not fit into any other categories and are not generally compostable or recyclable. | - blueprints - sepia and carbon paper - photographs - sheets of paper stick-on labels - chipboard - bagged shredded paper - envelope with plastic window |
| 9 | PL1 | Plastic Packaging means CRV or non-CRV bottles, jars, containers, lids, and other packaging that are made of types of all plastic types (1-7). This includes beverages, food or household product containers. Excludes EPS, flexible plastic pouches, compostable bags and film. | - beverage containers for soda, juice, etc. - jars and containers for food - containers for household products (e.g., shampoo, cleaning products) - vitamin bottles - yogurt cups, microwave food trays and cookie trays - single-use plant containers |
| 10 | PL2 | Expanded Polystyrene means all items made of expanded polystyrene. | - polystyrene cups, plates, bowls and clamshells - egg cartons - foam ice chests - polystyrene transport and other packaging for shipping |
| 11 | PL3 | Film Plastic means all film plastic used for plastic bags, sheeting, packaging and non-packaging uses. Excludes identifiable compostable plastic bags and flexible plastic pouches. | - garbage bags and can liners - grocery, merchandise and dry-cleaning bags - agricultural film, plastic sheeting and drop cloths - plastic food wrap, frozen vegetable bags and candy wrappers - sandwich bags, bread bags and zipper bags - newspaper and produce bags - mattress bags and furniture bags - film bubble wrap |
| 12 | PL4 | Compostable Plastic Bags means film plastic bags identifiable as compostable or biodegradable by the texture, color or labeling on the plastic. If unknown whether compostable, item should go in film plastic. | - compostable trash bags and compostable bin liners - compostable pet poop bags |
| 13 | PL5 | Flexible Plastic Pouches means plastic pouches made of thicker, multi-layer flexible material. Material is thicker than potato chip bags and frozen vegetable bags. May have a flat bottom so that package would stand up on its own, but not always. May have plastic screw tops. | - child resistant pouch bags - plastic coffee bags - juice pouches (e.g., Capri Sun) and baby food pouches - food pouches for soup, salad, wine, or backpacking meals - soap refill pouches |
| 14 | PL6 | Padded Envelopes – Plastic means envelopes with a plastic (any type) exterior with an interior lining of plastic or any other material. | - plastic poly bubble mailers - silver foil bubble bags |
| 15 | PL7 | Plastic Food Service Ware means items made partially or entirely of plastic that are used to consume, contain, or transport prepared food items. Includes all plastic types including compostable plastics. Excludes expanded polystyrene products. | - plates, bowls, and cups (and lids) - utensils, straws, and stirrers - take-out containers - bakery bags - condiment cups |
| 16 | PL8 | Durable Plastic Items means plastic items that are made to last for more than one use. These items may bear the numbers 1 through 7 in the triangular recycling symbol. | - crates, totes, buckets, and tubs - plastic garbage cans - flowerpots larger than one gallon - lawn furniture - plastic toys and sporting goods - CDs and cases plastic housewares including durable plates, cups, utensils - building materials such as house siding, housing for electronics, fan blades, plastic pipes and fittings |
| 17 | PL9 | Remainder/Composite Plastic means plastic that cannot be put in any other type. This type also includes items made mostly of plastic but combined with other materials. | - window blinds - insulating foam - imitation ceramics - handles and knobs, plastic lumber - rigid bubble/foil packaging (e.g., blister pack) and empty condiment packets - some toys, kitchenware and auto parts |
| 18 | G1 | Glass Bottles and Containers means all CRV and non-CRV clear and colored glass containers intended for single use, whole or broken. | - CRV glass like soda, fruit juice, beer and wine cooler bottles - non-CRV glass like wine and liquor bottles - food jars (e.g., pasta sauce, salsa, jam) |
| 19 | G2 | Remainder/Composite Glass means whole or broken glass that cannot be put Glass Bottles and Containers. It includes flat and curved glass and items made mostly of glass but combined with other materials. It also includes durable glass containers meant to be used more than once. | - windowpanes, doors and tabletop glass - automotive glass - safety glass - Pyrex and kitchen glass - crystal and glass tableware - drinking glasses - mirrors - non-fluorescent light bulbs - laminated glass |
| 20 | M1 | Metal Containers means all CRV and non-CRV cans and metal containers made from all metal types intended for single use. These may hold food, beverages, paint, and a variety of other household and consumer products. | - canned food and beverage containers - empty metal paint cans, spray paint cans and aerosol containers - bimetal containers with steel sides and aluminum ends - pet food, meat and wine cans |
| 21 | M2 | Major Appliances means discarded major appliances encased in metal, of any color. These items are often enamel-coated. This type does not include electronics, such as televisions and stereos. | - washing machines and dryers - hot water heater - stoves and refrigerators |
| 22 | M3 | Other Metal (ferrous, non-ferrous, and composite) means any metal item that does not fit in the Metal Containers or Appliances categories. This type includes items made mostly of metal but combined with other materials and items made of both ferrous metal and non-ferrous metal combined. | - structural steel beams - metal clothes hangers - metal pipes and brass pipes - metal cookware and reusable water bottles - aluminum foil - scrap ferrous items - aluminum window frames and siding - copper wire and insulated wire - shell casings - motors |
| 23 | SpW1 | Electronics means hard-to-handle items that are not defined elsewhere in the material types list, including furniture and large items that usually need electric currents or electromagnetic fields to operate. This also includes covered video display devices, consumer electronics and small equipment. Excludes major appliances that are generally not electronic. | - electronic musical equipment and exercise equipment - printers, computers, calculators, and mobile phones - toasters, irons, electric knives, sewing machines, and hair dryers - some toys and some sports equipment - hair care appliances |
| 24 | OR1 | Food – Packaged means any food item that is not easily separable from its packaging. This does not include packages with food residue only. | - half-full condiment jars - opened or unopened condiment packets - unopened soup can |
| 25 | OR2 | Food – Unpackaged means any food product, whole or partially consumed that is not in a container or is easily separated from its container. The container would then be sorted into one of the other material types. | - opened and unopened package of mushrooms, fruit salad, and salad greens - fruit and vegetable peels or trimmings - pits, shells, rinds, bones, and corn cobs - partially consumed burrito in foil - whole or partial fruits and vegetables - half eaten sandwich in original packaging - unfinished bag of chips - partially consumed frozen meals in tray |
| 26 | OR3 | Green Waste, Yard Waste and Manures means all woody and non-woody plant material of any diameter from public or private sources, or agricultural material. Also includes manure and soiled bedding items from large domestic, farm or ranch animals. Does not include feces from small household pets such as dogs and cats. | - leaves, grass clippings, plants, seaweed - pruning from shrubs, shrubs - branches, stumps - manure, soiled bedding from animal operations - agricultural crop residues |
| 27 | OR4 | Wood – Recyclable means clean dimensional lumber, clean engineered wood, clean pallets and crates, or other recyclable wood. This may include scrap from production of prefabricated wood products that have not been treated with paint, stain, or other chemical finish. Wood material should not be contaminated with another material (e.g., tar). Some trace contaminants and nails okay. | - 2 x 4s, 2 x 6s, 2 x 12s - residual materials from framing and related construction activities - plywood, particle board, wafer board - oriented strand board - residual materials used for sheathing and related construction uses - unpainted wood pallets and unpainted crates - lumber/engineered wood packaging - untreated scrap from production of prefabricated wood products (e.g. from cabinets or furniture) - untreated/unpainted fencing and recyclable demolition wood - untreated/unpainted wood roofing and siding |
| 28 | OR5 | Wood Waste (Nonrecyclable) – Treated/Painted/Stained Wood means wood that has been treated with a chemical preservative for purposes of protecting the wood against attacks from insects, microorganisms, fungi, and other environmental conditions that can lead to decay of the wood; and wood that has had an external coating such as paint, varnish, or other finish applied. | - handrails - finished furniture - other wood and wood products with paint, varnish, or other finish applied |
| 29 | OR6 | Remainder/Composite Organic means organic material that cannot be put in any other type. | - natural cork, hemp rope, straw baskets - small wood products (e.g., popsicle sticks, toothpicks) - sawdust and hair - animal carcasses - dryer sheets |
| 30 | InOth1 | Rock and Soil means rock pieces of any size and soil, dirt, and other matter. This type also includes nonhazardous contaminated soil. | - rock - stones - sand and clay - soil - compost |
| 31 | InOth2 | Remainder/Composite Inerts and Other means all inerts that are not rocks, soil or fines, including concrete, asphalt roofing, gypsum board and carpet. This type also may include items from different types combined, which would be very hard to separate. This type may also include demolition debris that is a mixture of items such as plate glass, wood, tiles, gypsum board, synthetic counter tops, fiber or composite acoustic ceiling tiles, and aluminum scrap. | - carpet - gypsum board, sheet rock, drywall, plasterboard - brick, ceramics, tiles - toilets and sinks - dried paint not attached to any materials - fiberglass and insulation - carpet padding - asphalt roofing, shingles, and paving - concrete paving, cinder blocks - pieces of building foundations |
| 32 | HHW1 | All Household Hazardous Waste & Special Waste Means household hazardous waste and special waste from other sectors that, if improperly put in the solid waste stream, may present handling problems or other hazards. Excludes dried paint, empty paint cans, or empty aerosol containers. | - paint and spent lubricating oil (e.g., crankcase and transmission oil, gear oil, hydraulic oil) - auto batteries, AA batteries, rechargeable batteries - asbestos-containing materials (e.g., certain pipes, insulation, floor tiles) - all propane gas cylinders - pills, liquid medications, creams and ointments - mercury-containing items such as thermostats or thermometers - treated medical waste and untreated medical waste (e.g., tubes, oxygen masks) |
| 33 | SW1 | Bulky Items Means bulky items like tires, furniture, and mattresses and foundations. | - automobile tires, bike tires, and lawn mower tires - mattresses and mattress foundations - couches and furniture - non-electronic musical equipment and exercise equipment |
| 34 | MISC1 | Textiles – Cloth and Clothing means cloth, clothing, sheets and towels, rope, and other textile items made of organic, synthetic, unknown, and mixed fibers. Textiles with zippers and buttons are included. | - cloth and rags - clothing - towels and sheets - rope |
| 35 | MISC2 | Textiles – Shoes, Belts and Bags means all shoes and boots, belts and bags whether made of leather, rubber, other materials, or a combination thereof. | - shoes and sandals - purses and backpacks - leather and cloth belts |
| 36 | MISC4 | Miscellaneous Residue means inorganic, organic or mixed material that cannot be put in any other type or category. | - kitchen ceramics - synthetic rubber products - diapers and feminine hygiene products - cosmetics |
| 37 | MISC5 | MRF Fines means material of small size that is too small to identify and sort and is ultimately sent to landfills for disposal. | - MRF residual fines - shredded paper pieces |

List B – Organics Facility Material List and Definitions by Category

| Total | Category Code | Material Type and Definition | Examples |
| --- | --- | --- | --- |
| 1 | P1 | Uncoated Corrugated Cardboard means a paper laminate usually composed of three layers. The center wavy layer is sandwiched between the two outer layers. This type does not include paperboard boxes such as cereal and tissue boxes. Excludes glossy and waxed cardboard. | - shipping and moving boxes - sheets and pieces used as dividers in boxes - very clean pizza boxes (no food residue and only lightly stained) |
| 2 | P2 | Coated Corrugated Cardboard means a paper laminate usually composed of three layers. The center wavy layer is sandwiched between the two outer layers. It has a glossy coating on the inside, outside or both sides. This type does not include paperboard boxes such as cereal and tissue boxes. Excludes non-glossy, uncoated cardboard. | - computer packaging cartons - boxes used for primary packaging of various consumer goods |
| 3 | P3 | Uncoated Paper means all non-corrugated paper that is not coated with another material. Can be bleached or colored. May be contaminated with food and/or moisture. | - paper grocery bags and other Kraft bags - lunch bags - pet food, rice, flour and sugar bags - white office type paper and mail - envelopes without plastic windows - newspapers and election guides - manila envelopes and index cards - toilet paper and paper towel tubes |
| 4 | P4 | Coated Paper means all non-corrugated paper that is coated with another material, making the item glossy or waxy. This includes most paperboard packaging. May be contaminated with food and/or moisture. | - magazines - newspaper ad inserts - glossy brochures and catalogs - wrapping paper - breakfast cereal and frozen food boxes - cigarette cartons |
| 5 | P5 | Paper/Fiber Food Service Ware means items made mostly of paper that are used to consume, contain, or transport prepared food items. Includes paper and molded fiber, including compostable and non- compostable items. May be contaminated with food and/or moisture. | - plates, bowls, cups, and utensils - straws and stirrers - take-out containers - pizza boxes - bakery/bread bags - condiment cups |
| 6 | P6 | Aseptic Containers and Gable-top Cartons means bleached polycoated paperboard containers or paper containers with a foil liner of various sizes and shapes that contain shelf-stable food products (i.e. aseptic containers) and paper-based cartons with a triangular top used for refrigerated and non-refrigerated items (i.e., gable-top cartons). Containers may include a plastic pour spout as part of the container. | - containers for apple juice, soup, and soy/rice milk - cartons used for milk, egg substitutes, and juice - gable-top containers used for snacks |
| 7 | P7 | Padded Envelopes – Paper means envelopes with a paper exterior, that may have plastic or other another material lining the interior of the envelope. Excludes envelopes with a plastic window. | - Kraft padded shipping envelopes - Kraft poly bubble mailers |
| 8 | P8 | Remainder/Composite Paper means items made mostly of paper that do not fit into any of the other paper types or are combined with large amounts of other materials. These are items that do not fit into any other categories and are not generally compostable or recyclable. | - blueprints - sepia and carbon paper - photographs - sheets of paper stick-on labels - chipboard - bagged shredded paper - envelope with plastic window |
| 9 | PL1 | Plastic Packaging. means CRV or non-CRV bottles, jars, containers, lids, and other packaging that are made of types of all plastic types (1-7). This includes beverages, food or household product containers. Excludes EPS, flexible plastic pouches, compostable bags and film. | - beverage containers for soda, juice, etc. - jars and containers for food - containers for household products (e.g. shampoo, cleaning products) - vitamin bottles - yogurt cups, microwave food trays and cookie trays - single-use plant containers |
| 10 | PL2 | Expanded Polystyrene means items made of expanded polystyrene. | - polystyrene cups, plates, bowls and clamshells - egg cartons - foam ice chests - polystyrene transport and other packaging for shipping |
| 11 | PL3 | Film Plastic means all film plastic used for plastic bags, sheeting, packaging and non-packaging uses. Excludes flexible plastic pouches and identifiable compostable plastic bags. | - garbage bags and can liners - grocery, merchandise and dry-cleaning bags - agricultural film, plastic sheeting and drop cloths - plastic food wrap, frozen vegetable bags and candy wrappers - sandwich bags, bread bags and zipper bags - newspaper and produce bags - mattress bags and furniture bags - film bubble wrap |
| 12 | PL4 | Compostable Plastic Bags means film plastic identifiable as compostable or biodegradable by the texture, color or labeling on the plastic. | - compostable trash bags and compostable bin liners - compostable pet poop bags |
| 13 | PL5 | Flexible Plastic Pouches means plastic pouches made of thicker, multi-layer flexible material. Material is thicker than potato chip bags and frozen vegetable bags. May have a flat bottom so that package would stand up on its own, but not always. May have plastic screw tops. | - child resistant pouch bags - plastic coffee bags - juice pouches and baby food pouches - food pouches for soup, salad, wine - backpacking meals - soap refill pouches |
| 14 | PL6 | Padded Envelopes – Plastic means envelopes with a plastic (any type) exterior with an interior lining of plastic or any other material. | - plastic poly bubble mailers - silver foil bubble bags |
| 15 | PL7 | Plastic Food Service Ware means items made partially or entirely of plastic that are used to consume, contain, or transport prepared food items. Includes all plastic types including compostable plastics. Excludes expanded polystyrene products. | - plates, bowls, and cups (and lids) - utensils, straws, and stirrers - take-out containers - bakery bags - condiment cups |
| 16 | PL8 | Durable Plastic Items means plastic items that are made to last for more than one use. These items may bear the numbers 1 through 7 in the triangular recycling symbol. | - crates, totes, buckets, and tubs - plastic garbage cans - flowerpots larger than one gallon - lawn furniture - plastic toys and sporting goods - CDs and cases plastic housewares including durable plates, cups, utensils - building materials such as house siding, housing for electronics, fan blades, plastic pipes and fittings |
| 17 | PL9 | Remainder/Composite Plastic means plastic that cannot be put in any other type. This type also includes items made mostly of plastic but combined with other materials. | - window blinds - insulating foam - imitation ceramics - handles and knobs, plastic lumber - rigid bubble/foil packaging (e.g. blister pack) and empty condiment packets - some toys, kitchenware and auto parts |
| 18 | G1 | All Glass means CRV and non-CRV glass of any color or type, whole or broken. This includes bottle and container glass, flat glass, curved glass, and items made mostly of glass but combined with other materials. | - CRV glass like soda, fruit juice, beer and wine cooler bottles - non-CRV wine and liquor bottles - food jars - windowpanes, door and tabletop glass - automotive glass and safety glass - Pyrex and kitchen glass - drinking glasses - mirrors - non-fluorescent light bulbs |
| 19 | M1 | All Metal means all metal containers and non-containers made from all metal types. May hold food, beverages, paint, and a variety of other household and consumer products. This also includes major appliances but not electronics. | - canned food and beverage containers - empty aerosol cans - pet food, meat and wine cans - bimetal containers with steel sides and aluminum ends - major appliances - metal hangers, scrap ferrous items - copper wire and insulated wire |
| 20 | OR1 | Food – Packaged means any food item that is not easily separable from its packaging. This does not include packages with food residue only. | - half-full condiment jars - opened or unopened condiment packets - unopened soup can |
| 21 | OR2 | Food – Unpackaged means any food product, whole or partially consumed that is not in a container or is easily separated from its container. The container would then be sorted into one of the other material types. | - opened and unopened package of mushrooms, fruit salad, and salad greens - fruit and vegetable peels or trimmings - pits, shells, rinds, bones, and corn cobs - partially consumed burrito in foil - whole or partial fruits and vegetables - half eaten sandwich in original packaging - unfinished bag of chips - partially consumed frozen meals in tray |
| 22 | OR3 | Green Waste, Yard Waste and Manures means all woody and non-woody plant material of any diameter from public or private sources, or agricultural material. Also includes manure and soiled bedding items from large domestic, farm or ranch animals. Does not include feces from small household pets such as dogs and cats. | - leaves, grass clippings, plants, seaweed - pruning from shrubs, shrubs - branches, stumps - manure, soiled bedding from animal operations - agricultural crop residues |
| 23 | OR4 | Sludge Means mixture of liquid and solid components that cannot be further sorted. | - Mud |
| 24 | OR5 | Wood – Recyclable means clean dimensional lumber, clean engineered wood, clean pallets and crates, or other recyclable wood. This may include scrap from production of prefabricated wood products that have not been treated with paint, stain, or other chemical finish. Wood material should not be contaminated with another material (e.g., tar). Some trace contaminants and nails okay. | - 2 x 4s, 2 x 6s, 2 x 12s - residual materials from framing and related construction activities - plywood, particle board, wafer board - oriented strand board - residual materials used for sheathing and related construction uses - unpainted wood pallets and unpainted crates - lumber/engineered wood packaging - untreated scrap from production of prefabricated wood products (e.g., from cabinets or furniture) - untreated/unpainted fencing and recyclable demolition wood - untreated/unpainted wood roofing and siding |
| 25 | OR6 | Wood Waste (Nonrecyclable) – Treated/Painted/Stained Wood means wood that has been treated with a chemical preservative for purposes of protecting the wood against attacks from insects, microorganisms, fungi, and other environmental conditions that can lead to decay of the wood; and wood that has had an external coating such as paint, varnish, or other finish applied. | - handrails - finished furniture - other wood and wood products with paint, varnish, or other finish applied |
| 26 | OR7 | Remainder/Composite Organic means organic material that cannot be put in any other type. | - natural cork, hemp rope, straw baskets - small wood products (e.g., popsicle sticks, toothpicks) - sawdust and hair - animal carcasses - dryer sheets |
| 27 | InOth1 | All Inerts means all inerts of any size, including rock, soil, dines, concrete, carpet, and items from different types combined which would be very difficult to separate. | - rock, stones, sand and clay - soil and compost - carpet, drywall, fiberglass and dried paint - toilets and sinks |
| 28 | MISC1 | All Textiles means cloth, clothing, sheets and towels, rope, and other textile items made of organic, synthetic, unknown, and mixed fiber as well as all shoes, purses, belts and other primarily-textile accessories. | - cloth and rags - clothing, towels, sheets and rope - shoes and sandals - purses and belts, bags, and backpacks |
| 29 | MISC2 | Miscellaneous Residue means bulky items, household hazardous waste, special wastes and inorganic items that cannot be put in any other type but could be sorted. | - diapers and feminine hygiene products - cosmetics - treated and untreated medical waste - paint - pills, liquid medications, creams and ointments - thermostats or thermometers - all propane gas cylinders |
| 30 | MISC3 | Fines means material of small size that is too small to identify and sort and is ultimately sent to landfills for disposal. | - clumping kitty litter - feces from household pets - MRF residual fines - shredded paper pieces - plastic nurdles |

Sample Weekly Report

Project Name:

Project Status Reporting Period: From: To:

Project Manager:

Report Prepared By:

Weekly Project Summary: Enter a brief summary of the project status, noting any key issues for the week. Comment on major deliverables completed; milestones reached and percent complete.

Current Task Summary

| Task or Deliverable | Scheduled Completion Date | Actual Completion Date | Issues? If yes, explain |
| --- | --- | --- | --- |
| Example: Sample Task 1 | 31 March 2020 | 1 April 2020 | No issues for Sample Task 1 |

Accomplished this week

Sites and samples

Sorting: Indicate number of hand-sorts completed per sector (and subsector), at which sites and day(s) and provide required attachments such as photos or site details

Attachments provided? (Such as copies of paper field sheets (if any), digital images, electronic files that contain data from the previous week) Yes/No If no, provide a reasonable explanation and a date when the attachments will be submitted.

Other items such as problems, contingency measures taken, significant findings encountered, recommendations:

Weekly look ahead - Planned/Scheduled Completion in Next Two Weeks

What sites and how many days per site?

Sample Plan (Confirm the Plan Provided by CalRecycle)

Deliverables Due:

Other items, concerns, issues:

Sample Data Collection Plan

Facility:

[Site Visit – if doing]:

Stream/line type:

Contact:

Confirmed Sort Dates:

Processing Overview:

Residual/reject management:

Residual/Reject Summary

| Residual Sources | Description | Estimated Contribution to Total Residual/Amount |
| --- | --- | --- |
| 1 | [ex. front of line rejects] |  |
| 2 | [ex. container residual] |  |
|  | Total |  |

Diverted Material Summary

|  | Description | Estimated Amount/% of residuals |
| --- | --- | --- |
| 1 |  |  |
| 2 |  |  |
|  | Total |  |

Inflows

|  | Description | Estimated % |
| --- | --- | --- |
| 1 | Residential |  |
| 2 | Commercial |  |
|  | Total |  |

Flow Diagram:

Residual Sampling Plan:

Origins of Preprocessed material that may be sampled?

Study 3 – Length of active phase?

Facility Support:

Proposed Work Area:

THIS PAGE INTENTIONALLY LEFT BLANK

| Sample Data Format for the Organics Recycling Characterization Study |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| For the Processing Facility-based Residual Characterization Study, at a minimum, the following fields are required: |  |  |  |  |  |  |  |  |  |  |  |
| Sample Date | Unique Sample ID Number | Name of Facility/Site Sample was Collected From | Stream | Sector | Total Sample Weight (pounds) | Material Type #1 (pounds) | Material Type #2 etc. (pounds) | General Information, Special Circumstances, etc. |  |  |  |  |
| For the Organics Recycling Inflow Characterization Study, at a minimum, the following fields are required: |  |  |  |  |  |  |  |  |  |  |
| Sample Date | Unique Sample ID Number | Name of Facility/Site Sample was Collected From | AD/ Compost Details | Sector | Unprocessed/ processed | Total Sample Weight (pounds) | Material Type #1 (pounds) | Material Type #2-etc. (pounds) | General Information, Special Circumstances, etc. |  |  |  |
| For the Organics Recycling Residual Characterization Study, at a minimum, the following fields are required: |  |  |  |  |  |  |  |  |  |  |  |
| Sample Date | Unique Sample ID Number | Name of Facility/Site Sample was Collected From | AD/ Compost Details | Sector | Total Sample Weight (pounds) | Material Type #1 (pounds) | Material Type #2-etc. (pounds) | General Information, Special Circumstances, etc. |  |  |  |  |

Table 1

| Food Waste Composting Facilities (Active Composting) |  |  |  |
| --- | --- | --- | --- |
| Facility | County | Type | SWIS Link |
| AgroThrive, Inc. | Monterey | Within - Vessel (tanks) | https://www2.calrecycle.ca.gov/swfacilities/Directory/27-AA-0119/ |
| B. Goodrow, Inc. Composting | San Luis Obispo | Windrow | https://www2.calrecycle.ca.gov/swfacilities/Directory/40-AA-0037/ |
| City Of Modesto Co-Compost Project | Stanislaus | Windrow | https://www2.calrecycle.ca.gov/swfacilities/Directory/50-AA-0018/ |
| City of Napa Composting Facility | Napa | ASP & Windrows | https://www2.calrecycle.ca.gov/swfacilities/Directory/28-AA-0030/ |
| Coachella Valley Composting Facility | Riverside | Windrow | https://www2.calrecycle.ca.gov/swfacilities/Directory/33-AA-0292/ |
| Cold Creek Compost, Inc. | Mendocino | ASP & Windrows | https://www2.calrecycle.ca.gov/swfacilities/Directory/23-AA-0029/ |
| El Corazon Compost Facility | San Diego | ASP - Biofilter | https://www2.calrecycle.ca.gov/swfacilities/Directory/37-AA-0907/ |
| Engel & Gray Inc | Santa Barbara | Windrows | https://www2.calrecycle.ca.gov/swfacilities/Directory/42-AA-0053/ |
| Feather River Organics | Yuba | Windrow | https://www2.calrecycle.ca.gov/swfacilities/Directory/58-AA-0015/ |
| Forward Resource Recovery Facility | San Joaquin | Windrow | https://www2.calrecycle.ca.gov/swfacilities/Directory/39-AA-0020/ |
| Gabilan Ag Services | Monterey | Windrow | https://www2.calrecycle.ca.gov/swfacilities/Directory/27-AA-0085/ |
| Harvest Power California, LLC | Tulare | Windrow | https://www2.calrecycle.ca.gov/swfacilities/Directory/54-AA-0026/ |
| Harvest-Lathrop | San Joaquin | Windrow | https://www2.calrecycle.ca.gov/swfacilities/Directory/39-AA-0051/ |
| Jepson Prairie Organics Composting Fac | Solano | Windrow / ASP | https://www2.calrecycle.ca.gov/swfacilities/Directory/48-AA-0083/ |
| Kochergen Farms Composting | Kings | Windrow | https://www2.calrecycle.ca.gov/swfacilities/Directory/16-AA-0022/ |
| Liberty Composting Inc. | Kern | Windrow | https://www2.calrecycle.ca.gov/swfacilities/Directory/15-AA-0287 |
| Mariposa Co. Composting Facility | Mariposa | In-Vessel | https://www2.calrecycle.ca.gov/swfacilities/Directory/22-AA-0013/ |
| MidValley Disposal Transfer Recycling St | Fresno | ASP | https://www2.calrecycle.ca.gov/swfacilities/Directory/10-AA-0201/ |
| Miramar Greenery | San Diego | Windrow | https://www2.calrecycle.ca.gov/swfacilities/Directory/37-AB-0003/ |
| Monterey Peninsula Landfill | Monterey | Windrow | https://www2.calrecycle.ca.gov/swfacilities/Directory/27-AA-0010/ |
| Mt Vernon Ave Recycling & Composting Fac | Kern | Windrow | https://www2.calrecycle.ca.gov/swfacilities/Directory/15-AA-0311/ |
| Newby Island Compost Facility | San Jose | Windrow | https://www2.calrecycle.ca.gov/swfacilities/Directory/43-AN-0017/ |
| Pebbly Beach (Avalon) Disposal Site | Los Angeles | Windrow | https://www2.calrecycle.ca.gov/swfacilities/Directory/19-AA-0061/ |
| Recology Blossom Valley Organics N Verna | San Joaquin | Windrow | https://www2.calrecycle.ca.gov/swfacilities/Directory/50-AA-0020/ |
| Recology Blossom Valley Organics- South | Kern | Windrow | https://www2.calrecycle.ca.gov/swfacilities/Directory/15-AA-0307/ |
| Robert A Nelson Transfer Station & MRF | Riverside | Covered ASP | https://www2.calrecycle.ca.gov/swfacilities/Directory/33-AA-0258/ |
| South Lake Resource Recovery and Compost | Lake | Windrow | https://www2.calrecycle.ca.gov/swfacilities/Directory/17-AA-0014/ |
| South Valley Organic Composting Facility | Santa Clara | Windrow | https://www2.calrecycle.ca.gov/swfacilities/Directory/43-AA-0017/ |
| Tierra Verde Industries EcoCentre | Orange | Windrow | https://www2.calrecycle.ca.gov/swfacilities/Directory/30-AB-0403/ |
| Victor Valley Regional Composting Fac. | San Bernardino | Windrow | https://www2.calrecycle.ca.gov/swfacilities/Directory/36-AA-0403/ |
| Waste Management Altamont | Alameda | ASP | https://www2.calrecycle.ca.gov/swfacilities/Directory/01-AA-0325/ |
| WCCSLF Organic Materials Processing | Contra Costa | Windrow | https://www2.calrecycle.ca.gov/swfacilities/Directory/07-AA-0044/ |
| West Valley Materials Recovery Facility | San Bernardino | Windrow | https://www2.calrecycle.ca.gov/swfacilities/Directory/36-AA-0341/ |
| WM Earthcare of Marin | Marin | ASP | https://www2.calrecycle.ca.gov/swfacilities/Directory/21-AA-0068/ |
| Z-Best Composting Facility | Santa Clara | Windrow/ AgBag | https://www2.calrecycle.ca.gov/swfacilities/Directory/43-AA-0015/ |

Table 2 - California Anaerobic Digestion Projects Accepting Organics from the Municipal Solid Waste Stream (November 2019)

| Project Name | Location | Site | Feedstocks | Diges--tion | Biogas Use | Status | Project Website |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Blue Line Biogenic CNG Facility | South San Francisco | Stand-Alone | Green Waste & Food Waste | Dry | CNG Transpor--tation Fuel | Operational | http://ssfscavenger.com/ad-facility/ |
| Central Marin Organic Waste Receiving Program | San Rafael | Co-Digestion | Food Waste, Fats, Oils, & Grease (FOG), & Sewage Sludge | Wet | Electricity | Operational | https://marinsanitaryservice.com/food2energy/ |
| CR&R Material Recovery Facility | Perris | Stand-Alone | Green Waste & Food Waste | High Solids | CNG Transport-ation Fuel & Pipeline Injection | Operational | http://crrwasteservices.com/sustainability/anaerobic-digestion/ |
| East Bay Municipal Utilities District – Wastewater Treatment Plant | Oakland | Co-Digestion | Food Waste, Sewage Sludge, & FOG | Wet | Electricity | Operational | http://www.ebmud.com/wastewater/recycling-water-and-energy/ |
| Los Angeles County Sanitation District – Joint Water Pollution Control Plant | Carson | Co-Digestion | Food Waste & Sewage Sludge | Wet | Electricity | Operational | https://www.lacsd.org/services/solidwasteprogram/food_waste_recycling.asp |
| North State Rendering | Oroville | Co-Digestion | Food Waste, FOG, & Sewage Sludge | Wet | Electricity & CNG Transport-ation Fuel | Operational | https://www.biocycle.net/2019/09/18/evolution-food-waste-digester/ |
| Ralphs Renewable Energy Facility – Compton Distribution Center | Compton | Stand-Alone | Food Waste | Wet | Electricity | Operational | https://www.greenbiz.com/news/2013/08/09/kroger-fuels-warehouse-food-waste |
| San Luis Obispo Kompogas AD Facility | San Luis Obispo | Stand-Alone | Green Waste & Food Waste | Dry | Electricity | Operational | https://www.sanluisgarbage.com/organics/dry-anaerobic-digestion/ |
| UC Davis Renewable Energy Anaerobic Digester (READ) | Davis | Stand-Alone | Food Waste | High Solids | Off-Site Boilers | Operational | https://facilities.ucdavis.edu/utilities/read |
| Victor Valley Wastewater Reclamation Authority – Wastewater Treatment Plant | Victorville | Co-Digestion | Food Waste, FOG, & Sewage Sludge | Wet | Electricity | Operational | https://www.vvwra.com/depts/human_resources/planning_and_development/projects.htm |
| Yolo County Anaerobic Composter | Woodland | Stand-Alone | Food Waste & Green Waste | High Solids | CNG Transport--ation Fuel & Electricity | Operational | https://www.calrecycle.ca.gov/blogs/in-the-loop/in-the-loop/2019/11/18/yolo-county-ad- composter |
| Zero Waste Energy Development (ZWED) | San Jose | Stand-Alone | Green Waste, Food Waste, & Manure | Dry | Electricity | Operational | http://zwedc.com/ |
| Incline Clean Energy (Formerly Clean World South Area Transfer Station) | Sacramento | Stand-Alone | Food Waste | High Solids | CNG Transport-ation Fuel & Electricity | Inactive | http://www.cleanworld.com/news/cleanworlds-sacramento-biodigester-named-international- bioenergy-project-of-the-year/ |
| Inland Empire Utilities Agency – Regional Water Recycling Plant No. 5 Solids Handling Facility | Chino | Co-Digestion | Food Waste, Sewage Sludge, & Manure | Wet | Electricity | Inactive | http://www.ieua.org/facilities/rp-5-shf/ |
| Monterey Zero Waste Energy | Marina | Stand-Alone | Green Waste & Food Waste | Dry | Electricity | Inactive | http://www.mrwmd.org/organics-to-energy/ |
| Agromin Zero Waste Energy | Oxnard | Stand-Alone | Green Waste & Food Waste | Dry |  | Pending | http://zerowasteenergy.com/wp-content/uploads/2013/11/ZWE-SmartfermOxnardFlyer.pdf |
| City of Manteca Wastewater Quality Control Facility Waste-to-Fuel Program | Manteca | Co-Digestion | Food Waste, Sewage Sludge, & FOG | Wet | CNG Transport-ation Fuel | Pending | https://www.ci.manteca.ca.us/PublicWorks/Pages/Waste-to-Fuel-Program.aspx |
| City of Napa Materials Diversion Facility | American Canyon | Stand-Alone | Green Waste & Food Waste | Dry | CNG Transportation Fuel | Pending | https://zerowasteenergy.com/our-projects/city-napa-napa-recycling-waste-services/ |
| Davis Street Anaerobic Digester | San Leandro | Stand-Alone | Green Waste & Food Waste | Dry |  | Pending | https://www2.calrecycle.ca.gov/swfacilities/Directory/01-AA-0007/ |
| East County Bioenergy Project | Antioch | Co-Digestion | Food Waste, Sewage Sludge, & FOG | Wet |  | Pending | https://www.deltadiablo.org/east-county-bioenergy-project |
| Escondido Resource Recovery | Escondido | Stand-Alone | Food Waste & Green Waste | Dry | CNG Transport- ation Fuel & Pipeline Injection | Pending | https://www.escondidodisposal.com/edco-recycling--transfer-in-signal-hill.htm |
| Lakeside Food-Scraps-to-Energy | Lakeside | Stand-Alone | Food Waste & FOG | Dry | Electricity | Pending | https://www.foodscraps2energy.com/ |
| Orange County Sanitation District Plant 2 | Huntington Beach | Co-Digestion | Food Waste & Sewage Sludge | Wet |  | Pending | https://www.ocsd.com/Home/ShowDocument?id=23427 |
| Renewable Sonoma Organics Processing Facility | Santa Rosa |  | Green Waste & Food Waste |  |  | Pending | https://zerowastesonoma.gov/organicsfacility |
| ReSource Center (Formerly Tajiguas Resource Recovery Project) | Santa Barbara County | Stand-Alone | Green Waste & Food Waste | Dry | Electricity | Pending | http://www.resourcerecoveryproject.com/ |
| Rialto Bioenergy Facility | Rialto | Stand-Alone | Food Waste & FOG | Wet | Electricity & RNG Pipeline Injection | Pending | https://www.waste360.com/anaerobic-digestion/anaergia-launches-rialto-calif-food-diversion- energy-recovery-plant |
| San Bernardino BioDigester | San Bernardino | Stand-Alone | Food Waste | Wet | Electricity | Pending | http://innovation.energy.ca.gov/SearchResultProject.aspx?p=30049&tks=637091531255109632 |
| Silicon Valley Clean Water – Wastewater Treatment Plant | Redwood City | Co-Digestion | Food Waste, FOG, & Sewage Sludge | Wet |  | Pending | http://www.svcw.org/innovation/SitePages/foodwastetoenergy.aspx |

## Contract/Task Time Frame

| Task | Start Date | End Date |
| --- | --- | --- |
| Contract must be signed and executed |  | No later than June 30, 2020 |
| Task 1 Initial Meeting | Within 15 days of contract execution | January 1, 2021 |
| Task 2 Coordinate with Processing Facilities and Determine Field Schedule | Before January 1, 2021 | January 1, 2022 |
| Task 3 Fieldwork | Before January 1, 2021 | January 1, 2022 |
| Task 4 Data Entry and Data QA/QC | Concurrent with Task 3 | January 21, 2022 |
| Task 5 Submit Field Data and Summary Reports to CalRecycle | Concurrent with Task 3 | January 21, 2022 |

## Location of Services

Services will be provided state-wide. There will be at least one meeting held in Sacramento, CA.  Other meeting locations will be determined by the Contract Manager.  Teleconferences may be used for meetings.

## Control of Work

- The Contract Manager has the authority to determine the quality and acceptability of the following:

- Work to be performed

- Rate and progress of the work

- Fulfillment of the services provided by the Contractor

- Compensation for services provided by the Contractor

These decisions will be deemed final and enforceable by the Contract Manager when the Contractor fails to complete orders required by this Contract.

The Contractor shall immediately bring any unanticipated issues to the attention of the Contract Manager. The Contract Manager will confer with appropriate CalRecycle staff, if necessary, and the Contractor to resolve the issue.

- The Contractor will designate a Project Manager who holds the following authority:

  - Act as the Contractor’s Representative for work to be provided under this Contract

  - Act as the Contractor’s Representative regarding contractual matters relating to this Contract

If during the course of the Contract, it is deemed necessary to replace the Project Manager, Contract Manager approval is required.

# Section VII	Definition and Terms

General

Unless the context otherwise requires, wherever in this RFP or addenda, the following abbreviations and terms, or pronouns in place of them, are used, the intent and meaning shall be interpreted as provided in this Section.

Working titles having a masculine gender, such as “draftsman” and “journeyman” and the pronoun “he”, are utilized in these provisions for the sake of brevity, and are intended to refer to persons of either sex.

Abbreviations

ADA	Americans with Disabilities Act

CAL EPA	California Environmental Protection Agency

CCR	California Code of Regulations

DVBE	Disabled Veteran Business Enterprise

EPA	Environmental Protection Agency (Federal Government)

GC	Government Code

PCC	Public Contract Code

RFP	Request for Proposals

SB	Small Business

SOW	Scope of Work

OSDS	The Department of General Services (DGS), Procurement Division (PD), Office of Small Business and DVBE Services (OSDS)

Agreement

The written Agreement covering performance of the work and furnishing of labor, materials, tools, and equipment in providing the work.  The Agreement shall include the RFP, Proposal, general and specific terms and conditions, Work Orders, and supplemental Agreements which may be required to complete the work in a substantial and acceptable manner.

Cal EPA

The California Environmental Protection Agency

CalRecycle Staff

Staff of the Department of Resources Recycling and Recovery involved in the implementation of this contract or representatives of Consultant to the Department of Resources Recycling and Recovery as designated in the Work Orders.

Consultant

The person or persons, firm, partnership, corporation, or combination thereof, which may enter into this Agreement with CalRecycle to provide work pursuant to this RFP or his or their legal representatives

Contract

A legally binding Agreement between the state & another entity, public or private, for the provision of goods or services

Contract Manager

A person designated by the responsible state agency or department to manage performance under a contract.

Contractor

A party contracting with the awarding agency.  Vendor is often used synonymously with Contractor.

Cost Proposal Opening

A public meeting, where the costs bid by a Proposer on an advertised project, are opened and a determination is made as to the apparent low bidder.

Director

The Executive Director of the Department of Resources Recycling and Recovery, or his/her designees.  Any references to Executive Officer shall mean the Executive Director and/or designated officer.

Disabled Veteran Business Enterprise (DVBE Certified)

A business that meets all of the following criteria:  (1) at least 51% of the business is owned by one or more disabled veterans or, in a business whose stock is publicly held, at least 51% or more of the stockholders are disabled veterans (2) the management and control of the business are exercised by one or more disabled veterans; (3) the business is domestically owned and its home office is in the United States; and (4) the business has been certified as a DVBE by the State of California, Department of General Services (DGS), Procurement Division (PD), Office of Small Business and DVBE Services (OSDS).

Legal Holiday

Those days designated as State holidays in the Government Code.

Project Manager

Contractor’s representative for all work performed under this Agreement.  All official correspondence, reports, submittals, billings, and other work done under this Agreement shall be reviewed and signed by the Project Manager prior to submittal to CalRecycle.

Scope of Work

The description of work required of a Contractor by the awarding agency.

Small Business (Certified)

A business that has been certified by the Department of General Services (DGS), Procurement Division (PD), Office of Small Business and DVBE Services (OSDS), as a small business as defined in GC section 14837 and 2 CCR section 1896.

State

The State of California.

State Contract Law

The Public Contract Code and other applicable laws that form and constitute a Study of the provisions of this Agreement to the same extent as if set forth herein in full.

Subcontractor

A person or entity which contracts with the Contractor to perform all or a portion of the work as specified in the Scope of Work.

# Attachments

## Cost Proposal Sheet

2020 Organics Recycling Waste Characterization Study, DRR19070

Complete this form and submit the original in accordance with the requirements of this RFP.  Any invoices submitted by Contractor will identify line item costs and corresponding task number.

| Contractor/Company Name: |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Task # |  | Personnel Services: (Do not include travel or overhead) estimated # of hours needed for contract services multiplied by the individual or position rates per hour. (Include name/position title and hours) |  |  |  |  | Fringe Benefits (Identify fringe benefit costs citing actual benefits or as a percentage of personal services costs) | Operating Expenses (operating expenses related to the services provided in this Agreement, including rent and supplies, as applicable) | Equipment Costs (Include a description of equipment) | Travel Expenses (Include travel expenses and per diem. Rates are set at the rate specified by CalHR for excluded employees) | Overhead (This information shall be provided) |  | Other (any other specific breakdown required to sufficiently explain the budget costs) | Total by Task |
|  |  | Name / Position | $/Hr |  | Hrs | Total $ |  |  |  |  |  |  |  |  |
| Total by Line Item |  | (Sum of Total $) |  |  |  |  |  |  |  |  |  |  |  | GRAND TOTAL |

| Acknowledgement/Authorization |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| The undersigned acknowledges the submittal of this Proposal constitutes an irrevocable offer for a ninety (90) day period for CalRecycle to award an Agreement. Additional acknowledgement is made of receipt of all competitive documents, including Addenda, relating to this Agreement. The undersigned acknowledges that the Proposer has read all of the requirements set forth in CalRecycle documents and will comply with said provisions. The undersigned hereby authorizes and requests any person, firm, agency, or corporation to furnish any information requested by CalRecycle in verification of the recitals comprising this Proposal and also hereby authorizes CalRecycle to contact such persons, firms, etc., in order to obtain information regarding the undersigned. The undersigned acknowledges that there are no potential conflicts of interest, as defined in Public Contract Code (PCC) section 10410, 10411, and Government Code (GC) section 87100, by the submitting firm and/or any Subcontractors listed in the Proposal. |  |  |  |  |  |  |  |  |  |
| I declare under penalty of perjury that the foregoing is true and correct. |  |  |  |  |  |  |  |  |  |  |
| Contractor Name: |  |  | Address: |  |  |  |  |  |  |  |  |
| Telephone #: |  |  | City, State Zip: |  |  |  |  |  |  |  |  |
| Name & Title of Authorized Representative: |  |  | Email: |  |  |  |  |  |  |  |  |
| Signature of Authorized Representative: |  |  | Date Signed: |  |  |  |  |  |  |  |  |
| If fringe benefits and/or overhead are not specifically itemized in the Cost Proposal Sheet and if the Proposer inserts a $0, the Proposer shall explain why these line items are not itemized. A blank space for either fringe benefits or overhead will be grounds for immediate disqualification. |  |  |  |  |  |  |  |  |

## Proposal Scoring Sheet

2020 Organics Recycling Waste Characterization Study, DRR19070

| Contractor/Company Name: |  |
| --- | --- |

| EXPERIENCE (Minimum 20 of 30 points to qualify) |  | MULTIPLIER |  | SCORE (0-3) |  | Score * Multiplier |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| (1) Project Manager demonstrates experience in and knowledge of implementing a study design, leading large, complex, multi-site characterization studies, and adaptability to unforeseen circumstances. (3 pts.) |  | 3 |  |  |  |  |  |
| (2) Key members of the project team demonstrate professional experience in conducting waste characterization studies, including broad experience implementing a study design, leading large, complex, multi-site waste characterization studies. (3 pts.) |  | 3 |  |  |  |  |  |
| (3) Key members of the project team demonstrate knowledge of California’s recycling infrastructure, handling and processing systems, as relevant to the study objectives, including experience working in various parts of the state and/or with the suite of facilities types and operators. (3 pts.) |  | 2 |  |  |  |  |  |
| (4) All field supervisors and the majority of sorters have field experience for sampling, sorting, QA/QC protocols, health and safety protocols, coordinating with recycling and organics processing facilities and data collection. (3 pts.) |  | 2 |  |  |  |  |  |
| Experience Subtotal (If minimum points attained, continue scoring in the next section) |  |  |  |  |  |  |  |
| METHODOLOGY (Minimum 48 of 69 points to qualify) |  | MULTIPLIER |  | SCORE (0-3) |  | Score * Multiplier |  |  |
| Proposed number of samples for all Studies combined: (3 pts.) # of Samples Score |  | 2 |  |  |  |  |  |  |
| <600 0 |  |  |  |  |  |  |  |  |
| 601-800 1 |  |  |  |  |  |  |  |  |
| 801-1000 2 |  |  |  |  |  |  |  |  |
| >1000 3 |  |  |  |  |  |  |  |  |
| (5) Provides a study design (Work Plan) with a thorough explanation of proposed approaches, methodologies, and/or alternatives to achieve the goals of each Study. (3 pts.) |  | 3 |  |  |  |  |  |  |
| (6) Provides a clear justification for why the proposed number of samples is adequate to result in data representative of the facilities sampled (e.g. prior experience, literature review, statistical analyses). (3 pts.) |  | 2 |  |  |  |  |  |  |
| (7) Proposes what sample weights are adequate and provides justification (e.g. prior experience, literature review, statistical analyses). (3 pts.) |  | 1 |  |  |  |  |  |  |
| (8) Addresses how random samples will be selected that are representative of the chosen load and does not introduce bias, and how adequate sample weights will be achieved. (3 pts.) |  | 1 |  |  |  |  |  |  |
| (9) Identifies strategies to determine source sector information required in each study. (3 pts.) |  | 1 |  |  |  |  |  |  |
| (7)(e) Proposes method for differentiating between inorganic and organic fines for all study parts, resulting in percentage of inorganic v. organic fines in sample.(3 pts.) |  | 1 |  |  |  |  |  |  |
| (7)(f) Proposes methodology and justification for sorting to a minimum particle size for each Study of the study (e.g. prior experience, literature review, statistical analyses). (3 pts.) |  | 1 |  |  |  |  |  |  |
| (7)(h) Addresses field sampling and sorting approach to obtain accurate data, including sorting protocols, training and supervision of field workers, health and safety protocols, data recording and quality assurance. (3 pts.) |  | 1 |  |  |  |  |  |  |
| (7)(i) Provides timeline for carrying out Study 1,2 & 3 that are within the bounds of the dates in the Contract/Task Time Frame. (3 pts.) |  | 1 |  |  |  |  |  |  |
| (8) Describes how the Project Manager will staff the project including roles, responsibilities, and numbers of staff and supervisors. (3 pts.) |  | 1 |  |  |  |  |  |  |
| Addresses how the Project Manager will train staff and a tentative timeline of work, including: start-up tasks, logistical arrangements, training, travel, set-up, sample collection/sorting/analysis (as applicable to each part), data entry, data quality control, and delivery of final data sets to CalRecycle.(3 pts.) |  | 1 |  |  |  |  |  |  |
| All Studies: Describes how the project team will accomplish the objectives in Task 2 (Coordinate with Processing Facilities and Determine Field Schedule), how the members of the project team will coordinate logistics and field schedules with processing facilities, and how the project fieldwork timeline will be maintained.(3 pts.) |  | 2 |  |  |  |  |  |  |
| All Studies: Describes how the project team will accomplish the objectives in Task 3 (Perform Fieldwork-Field Sampling and Sorting at Facilities). (3 pts.) |  | 2 |  |  |  |  |  |  |
| Clearly describes methods for QA/QC of characterization data and photographs (Task 4 - Data Entry and Data QA/QC). (3 pts.) |  | 1 |  |  |  |  |  |  |
| Clearly describes how the project team will accomplish the objectives in Task 5 (Submit Field Data and Summary Reports to CalRecycle), including a weekly status report template, and specifies how to ensure timely communication (e.g. weekly and monthly reports) with CalRecycle Contract Manager through the life of the contract. (3 pts.) |  | 1 |  |  |  |  |  |  |
| Clearly describes how the project team will submit data and other information to CalRecycle per Task 5 (Submit Field Data and Summary Reports). (3 pts.) |  | 1 |  |  |  |  |  |  |
| Methodology Subtotal (If minimum points attained, continue scoring in the next section) |  |  |  |  |  |  |  |  |
| SUBTOTAL of Experience and Methodology Points |  |  |  |  |  |  |  |  |
| DVBE Incentive |  |  |  |  |  |  |  |  |
| Final Score |  |  |  |  |  |  |  |  |

THIS PAGE INTENTIONALLY LEFT BLANK

## Bidder Declaration

| State of California—Department of General Services, Procurement Division GSPD–05–105 (EST 8/09) |  |  |  |  |  | Solicitation Number |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | BIDDER DECLARATION |  |  |  |  |  |  |  |
| - Prime Bidder information (Review attached Bidder Declaration Instructions prior to completion of this form): |  |  |  |  |  |  |  |  |  |
| - Identify current California certification(s) (MB, SB, NVSA, DVBE): or None |  |  |  |  |  |  |  |  |  |
| - Will Subcontractors be used for this Contract? Yes No (If yes, indicate the distinct element of work your firm will perform in this Contract e.g., list the proposed products produced by your firm, state if your firm owns the transportation vehicles that will deliver the products to the State, identify which solicited services your firm will perform, etc.). Use additional sheets, as necessary. |  |  |  |  |  |  |  |  |  |
| - If you are a California certified DVBE: |  |  | (1) Are you a broker or agent? Yes No |  |  |  |  |  |  |
|  |  |  | (2) If the Contract includes equipment rental, does your company own at least 51% of the equipment provided in this Contract (quantity and value)? Yes No N/A |  |  |  |  |  |  |
| - If no Subcontractors will be used, skip to certification below. Otherwise, list all Subcontractors for this Contract. (Attach additional pages if necessary): |  |  |  |  |  |  |  |  |  |
| Subcontractor Name, Contact Person, Phone Number & Fax Number | Subcontractor Address & Email Address |  |  | CA Certification (MB, SB, DVBE or None) | Work performed or goods provided for this Contract |  | Corresponding % of bid price | Good Standing? | 51% Rental? |
| CERTIFICATION: By signing the bid response, I certify under penalty of perjury that the information provided is true and correct |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  | Page _____ of _____ |  |  |

| State of California—Department of General Services, Procurement |  |  |  |
| --- | --- | --- | --- |
| Division GSPD–05–105 (EST 8/09) Instructions | BIDDER DECLARATION Instructions |  |  |
| All prime Bidders (the firm submitting the bid) must complete the Bidder Declaration. - Identify all current certifications issued by the State of California. If the prime Bidder has no California certification(s), check the line labeled“None”and proceed to Item #2. If the prime Bidder possesses one or more of the following certifications, enter the applicable certification(s) on the line: - Microbusiness (MB) - Small Business (SB) - Small Business Nonprofit Veteran Service Agency (SB/NVSA) - Disabled Veteran Business Enterprise (DVBE) - Mark either“Yes”or“No” to identify whether Subcontractors will be used for the Contract. If the response is “No”, proceed to Item #1.c. If“Yes”, enter on the line the distinct element of work contained in the Contract to be performed or the goods to be provided by the prime Bidder. Do not include goods or services to be provided by Subcontractors. Bidders certified as MB, SB, SB/NVSA, and/or DVBE must provide a commercially useful function as defined in Military and Veterans Code Section 999(e)(2)(A) for DVBEs and Government Code Section 14837(d)(4)(A) for small/microbusinesses. For questions regarding commercially useful function determinations made in conjunction with certification approval, contact the Department of General Services, Procurement Division, Office of Small Business and DVBE Certification (OSDC), OSDC Certification and Compliance Unit via email at: osdchelp@dgs.ca.gov Bids must propose that certified Bidders provide a commercially useful function for the resulting Contract or the bid will be deemed non-responsive and rejected by the State. For questions regarding the solicitation, contact the procurement official identified in the solicitation. Note:A Subcontractor is any person, firm, corporation, or organization Contracting to perform Study of the prime’s Contract. - This item is only to be completed by businesses certified by California as a DVBE. - Declare whether the prime Bidder is a broker or agent by marking either“Yes”or“No”. The Military and Veterans Code Section 999.2 (b) defines“broker”or“agent”as a certified DVBE Contractor or Subcontractor that does not have title, possession, control, and risk of loss of materials, supplies, services, or equipment provided to an awarding department, unless one or more of the disabled veteran owners has at least 51-percent ownership of the quantity and value of the materials, supplies, services, and of each piece of equipment provided under the Contract. If bidding rental equipment, mark either“Yes” or“No”to identify if the prime Bidder owns at least 51% of the equipment provided (quantity and value). If not bidding rental equipment, mark“N/A”for“not applicable.” __________________________________________________________________________________________ - If no Subcontractors are proposed, do not complete the table. Read the certification at the bottom of the form and complete“Page of ”on the form. If Subcontractors will be used, complete the table listing all Subcontractors. If necessary, attach additional pages and complete the“Page of ”accordingly. |  | - (continued) Column Labels Subcontractor Name, Contact Person, Phone Number & Fax Number—List each element for all Subcontractors. Subcontractor Address & Email Address—Enter the address and if available, an Email address. CA Certification (MB, SB, DVBE or None)—If the Subcontractor possesses a current State of California certification(s), verify on the OSDC website (www.pd.dgs.ca.gov/smbus) that it is still valid and list all current certifications here. Otherwise, enter“None”. [Note: A SB/NVSA should not be participating as a Subcontractor] Work performed or goods provided for this Contract—Identify the distinct element of work contained in the Contract to be performed or the goods to be provided by each Subcontractor. Certified Subcontractors must provide a commercially useful function for the Contract. (See paragraph 1.b above for code citations regarding the definition of commercially useful function.) If a certified Subcontractor is further subcontracting a greater portion of the work or goods provided for the resulting Contract than would be expected by normal industry practices, attach a separate sheet of paper explaining the situation. Corresponding % of bid price—Enter the corresponding percentage of the total bid price for the goods and/or services to be provided by each Subcontractor. Do not enter a dollar amount. Good Standing?—Provide a response for each Subcontractor listed. Enter either“Yes”or“No”to indicate that the prime Bidder has verified that the Subcontractor(s) is in good standing for all of the following: - Possesses valid license(s) for any license(s) or permits required by the solicitation or by law - If a corporation, the company is qualified to do business in California and designated by the State of California Secretary of State to be in good standing - Possesses valid State of California certification(s) if claiming MB, SB, and/or DVBE status - Is not listed on the OSDC website as ineligible to transact business with the State 51% Rental?—This pertains to the applicability of rental equipment. Based on the following parameters, enter either“N/A” (not applicable),“Yes”or“No”for each Subcontractor listed. Enter“N/A”if the: - Subcontractor is NOT a DVBE (regardless of whether or not rental equipment is provided by the Subcontractor) or - Subcontractor is NOT providing rental equipment (regardless of whether or not Subcontractor is a DVBE) Enter“Yes”if the Subcontractor is a California certified DVBE providing rental equipment and the Subcontractor owns at least 51% of the rental equipment (quantity and value) it will be providing for the Contract. Enter“No”if the Subcontractor is a California certified DVBE providing rental equipment but the Subcontractor does NOT own at least 51% of the rental equipment (quantity and value) it will be providing. Read the certification at the bottom of the page and complete the “Page of ” accordingly. |  |

## Small Business (SB) and Disabled Veteran Business Enterprise (DVBE) Subcontractor Payment Certification

As Contractor of record for the Department of Resources Recycling and Recovery, Contract number ___________________, I certify, in accordance with Government Code 14841 and Military and Veteran Code § 999.5, that pursuant to the terms and conditions of the contract, all payments have been made to the SB or DVBE firm(s) listed below for commodities or services rendered as the SB or DVBE subcontractor(s) of record.   I understand certification must be made to the Department of Resources Recycling and Recovery within 60 days of receiving final payment under this Agreement.   I further understand and acknowledge that falsification of this Certification may result in the imposition of civil or criminal penalties for not less than $2,500 or more than $25,000 for each violation.

Please copy this form to include as many SB or DVBE firms as necessary.  Authorized signatures and information are required on each separately submitted form. Return to: Department of Resources Recycling and Recovery, Contracts Unit- MS 19-A, Attn: SB/DVBE Advocate, P.O. Box 4025, Sacramento, CA 95812-4025

SB/MB/DVBE SUBCONTRACTOR INFORMATION

| Contract Firm Name |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Name of Firm Representative |  |  |  |  |  |  |  |  |  |  |  |  |
| Title |  |  |  |  |  |  |  |  |  |  |  |  |
| Phone: |  |  |  |  |  | Fax: |  |  |  |  |  |  |
| Firm Address |  |  | Street: |  |  |  |  |  |  |  |  |  |
| City: |  |  |  |  |  |  |  |  | State: |  | Zip: |  |
| Contract Number |  |  |  |  |  |  |  |  |  |  |  |  |
| Total Amount Received Under this Contract |  |  |  |  | $ Date Final Payment Received: / / |  |  |  |  |  |  |  |

SB/DVBE SUBCONTRACTOR INFORMATION

| SB/DVBE Subcontractor |  | Street Address City State Zip |  |  | Amount Paid | Participation Achieved |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  | % |
|  |  |  |  |  |  | % |
|  |  |  |  |  |  | % |
|  |  |  |  |  |  | % |
| Printed Name |  |  | Signature: |  |  |  |
| Title: |  |  | Report Date: |  |  |  |

THIS PAGE INTENTIONALLY LEFT BLANK

## Iran Contracting Act

Public Contract Code Sections 2202-2208

Prior to bidding on, submitting a proposal or executing a contract or renewal for a State of California contract for goods or services of $1,000,000 or more, a vendor must either:  a) certify it is not on the current list of persons engaged in investment activities in Iran created by the California Department of General Services (“DGS”) pursuant to Public Contract Code section 2203(b) and is not a financial institution extending twenty million dollars ($20,000,000) or more in credit to another person, for 45 days or more, if that other person will use the credit to provide goods or services in the energy sector in Iran and is identified on the current list of persons engaged in investment activities in Iran created by DGS; or b) demonstrate it has been exempted from the certification requirement for that solicitation or contract pursuant to Public Contract Code section 2203(c) or (d).

To comply with this requirement, please insert your vendor or financial institution name and Federal ID Number (if available) and complete one of the options below. Please note: California law establishes penalties for providing false certifications, including civil penalties equal to the greater of $250,000 or twice the amount of the contract for which the false certification was made; contract termination; and three-year ineligibility to bid on contracts. (Public Contract Code section 2205.)

OPTION #1 – CERTIFICATION

I, the official named below, certify I am duly authorized to execute this certification on behalf of the vendor/financial institution identified below, and the vendor/financial institution identified below is not on the current list of persons engaged in investment activities in Iran created by DGS and is not a financial institution extending twenty million dollars ($20,000,000) or more in credit to another person/vendor, for 45 days or more, if that other person/vendor will use the credit to provide goods or services in the energy sector in Iran and is identified on the current list of persons engaged in investment activities in Iran created by DGS.

| Vendor Name/Financial Institution (Printed) |  | Federal ID Number (or n/a) |
| --- | --- | --- |
| By (Authorized Signature) |  |  |
| Printed Name and Title of Person Signing |  |  |
| Date Executed | Executed in |  |

OPTION #2 – EXEMPTION

Pursuant to Public Contract Code sections 2203(c) and (d), a public entity may permit a vendor/financial institution engaged in investment activities in Iran, on a case-by-case basis, to be eligible for, or to bid on, submit a proposal for, or enters into or renews, a contract for goods and services.

If you have obtained an exemption from the certification requirement under the Iran Contracting Act, please fill out the information below, and attach documentation demonstrating the exemption approval.

| Vendor Name/Financial Institution (Printed) |  | Federal ID Number (or n/a) |
| --- | --- | --- |
| By (Authorized Signature) |  |  |
| Printed Name and Title of Person Signing | Date Executed |  |

## Darfur Contracting Act

Pursuant to Public Contract Code section 10478, if a bidder or Proposer currently or within the previous three years has had business activities or other operations outside of the United States, it must certify that it is not a “scrutinized” company as defined in Public Contract Code section 10476.

Therefore, to be eligible to submit a bid or Proposal, please complete only one of the following three paragraphs (via initials for Paragraph # 1 or Paragraph # 2, or via initials and certification for Paragraph # 3):

| 1. |  | We do not currently have, or we have not had within the previous three years, business activities or other operations outside of the United States. |  |
| --- | --- | --- | --- |
|  | Initials |  |  |
|  |  | OR |  |
| 2. |  | We are a scrutinized company as defined in Public Contract Code section 10476, but we have received written permission from the Department of General Services (DGS) to submit a bid or Proposal pursuant to Public Contract Code section 10477(b). A copy of the written permission from DGS is included with our bid or Proposal. |
|  | Initials |  |
|  |  | OR |
| 3. |  | We currently have, or we have had within the previous three years, business activities or other operations outside of the United States, but we certify below that we are not a scrutinized company as defined in Public Contract Code section 10476. |
|  | Initials + Certification below |  |

CERTIFICATION For # 3.

I, the official named below, CERTIFY UNDER PENALTY OF PERJURY that I am duly authorized to legally bind the prospective Proposer/bidder to the clause listed above in # 3.  This certification is made under the laws of the State of California.

| Proposer/Bidder Firm Name (Printed) |  | Federal ID Number |  |
| --- | --- | --- | --- |
| By (Authorized Signature) |  |  |  |
| Printed Name and Title of Person Signing |  |  |  |
| Date Executed | Executed in the County and State of |  |

YOUR BID OR PROPOSAL WILL BE DISQUALIFIED UNLESS YOUR BID OR PROPOSAL INCLUDES THIS FORM WITH EITHER PARAGRAPH # 1 OR # 2 INITIALED OR PARAGRAPH # 3 INITIALED AND CERTIFIED.

## California Civil Rights Laws Certification

Pursuant to Public Contract Code section 2010, if a bidder or proposer executes or renews a contract over $100,000 on or after January 1, 2017, the bidder or proposer hereby certifies compliance with the following:

1.  CALIFORNIA CIVIL RIGHTS LAWS:  For contracts over $100,000 executed or renewed after January 1, 2017, the contractor certifies compliance with the Unruh Civil Rights Act (Section 51 of the Civil Code) and the Fair Employment and Housing Act (Section 12960 of the Government Code); and

2.  EMPLOYER DISCRIMINATORY POLICIES: For contracts over $100,000 executed or renewed after January 1, 2017, if a Contractor has an internal policy against a sovereign nation or peoples recognized by the United States government, the Contractor certifies that such policies are not used in violation of the Unruh Civil Rights Act (Section 51 of the Civil Code) or the Fair Employment and Housing Act (Section 12960 of the Government Code).

CERTIFICATION

| I, the official named below, certify under penalty of perjury under the laws of the State of California that the foregoing is true and correct. Proposer/Bidder Firm Name (Printed) |  | Federal ID Number |
| --- | --- | --- |
| By (Authorized Signature) |  |  |
| Printed Name and Title of Person Signing |  |  |
| Date Executed | Executed in the County and State of |  |

## Contractor Status Form

| Contractor’s Name: |  |  |  |  |  |  |  | County: |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Address: |  |  |  |  |  |  |  | Phone Number: |  |  |
|  |  |  |  |  |  |  |  | Fax Number: |  |  |
| Federal Employer Identification Number: |  |  |  |  |  |  |  |  |  |  |
| STATUS OF CONTRACTOR PROPOSING TO DO BUSINESS |  |  |  |  |  |  |  |  |  |  |
| Individual Limited Partnership General Partnership Corporation Other |  |  |  |  |  |  |  |  |  |  |
| If Individual or sole proprietorship, state the true name of sole proprietor: |  |  |  |  |  |  |  |  |  |  |
| If a Limited or General Partnership, list each partner and state their true name and interest in the partnership: |  |  |  |  |  |  |  |  |  |  |
| If a Corporation, state place and date of incorporation: |  |  |  |  |  |  |  |  |  |  |
| President: |  |  |  |  |  |  | Vice President: |  |  |  |
| Secretary: |  |  |  |  |  |  | Treasurer: |  |  |  |
| Other Officer: |  |  |  |  |  |  | Other Officer: |  |  |  |
| Provide explanation if claiming Other: |  |  |  |  |  |  |  |  |  |  |
| SMALL BUSINESS PREFERECE |  |  |  |  |  |  |  |  |  |  |
| Are you claiming preference for small/micro business? |  |  |  | YES – Attach approval letter from Office of Small Business Certification and Resources NO |  |  |  |  |  |  |
| Are you claiming preference for DVBE? |  |  |  | YES – Attach approval letter from Office of Small Business Certification and Resources NO |  |  |  |  |  |  |
| NOTE: THIS FORM MUST BE COMPLETED OR YOUR BID MAY BE REJECTED |  |  |  |  |  |  |  |  |  |  |

## Client References

List at least three (3) client references that can attest to the Bidder’s qualifications to fulfill the requirements of the Scope of Work.  List the most recent first.  Client references shall also be provided for any Subcontractors identified in the Bidder’s response.  Duplicate and attach additional pages as necessary.

| BIDDER / SUBCONTRACTOR’S NAME: |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| REFERENCE 1 |  |  |  |  |  |
| Name of Firm |  |  |  |  |  |
| Street Address | City |  |  | State | Zip Code |
| Contact Person |  | Telephone Number |  |  |  |
| Dates of Service |  |  | Cost of Service |  |  |
| Brief Description of Service Provided |  |  |  |  |  |
| REFERENCE 2 |  |  |  |  |  |
| Name of Firm |  |  |  |  |  |
| Street Address | City |  |  | State | Zip Code |
| Contact Person |  | Telephone Number |  |  |  |
| Dates of Service |  |  | Cost of Service |  |  |
| Brief Description of Service Provided |  |  |  |  |  |
| REFERENCE 3 |  |  |  |  |  |
| Name of Firm |  |  |  |  |  |
| Street Address | City |  |  | State | Zip Code |
| Contact Person |  | Telephone Number |  |  |  |
| Dates of Service |  |  | Cost of Service |  |  |
| Brief Description of Service Provided |  |  |  |  |  |
| If three references cannot be provided, explain why: |  |  |  |  |  |

## DRAFT Standard Agreement (STD 213)

| STATE OF CALIFORNIA - DEPARTMENT OF GENERAL SERVICES |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| STANDARD AGREEMENT |  |  | AGREEMENT NUMBER |  | PURCHASING AUTHORITY NUMBER (If Applicable) |  |  |  |
| STD 213 (Rev. 03/2019) |  |  | DRR19070 |  |  |  |  |  |
| 1. This Agreement is entered into between the Contracting Agency and the Contractor named below: |  |  |  |  |  |  |  |  |
| CONTRACTING AGENCY NAME |  |  |  |  |  |  |  |  |
| Department of Resources Recycling and Recovery (CalRecycle) |  |  |  |  |  |  |  |  |
| CONTRACTOR NAME |  |  |  |  |  |  |  |  |
| TBD |  |  |  |  |  |  |  |  |
| 2. The term of this Agreement is: |  |  |  |  |  |  |  |  |
| START DATE |  |  |  |  |  |  |  |  |
| or Upon DGS Approval, whichever is later |  |  |  |  |  |  |  |  |
| THROUGH END DATE |  |  |  |  |  |  |  |  |
| 3. The maximum amount of this Agreement is: |  |  |  |  |  |  |  |  |
| ( dollars and zero cents) |  |  |  |  |  |  |  |  |
| 4. The parties agree to comply with the terms and conditions of the following exhibits, which are by this reference made a Study of the Agreement. |  |  |  |  |  |  |  |  |
| EXHIBITS |  | TITLE |  |  |  |  | PAGES |  |
|  | Exhibit A | Scope of Work |  |  |  |  |  |  |
|  | Exhibit B | Budget Detail and Payment Provisions |  |  |  |  |  |  |
|  | Exhibit C* | General Terms and Conditions GTC 04/2017 |  |  |  |  |  |  |
| Exhibit D |  | Special Terms and Conditions |  |  |  |  |  |  |
|  |  | Attachment 1 Recycled Content Certification |  |  |  |  |  |  |
| Exhibit E** |  | from company name in response to DRR19070 |  |  |  |  |  |  |
|  |  | Items shown with double Asterisks (**) are hereby incorporated by reference and made Study of this agreement as if attached hereto. |  |  |  |  |  |  |
| Items shown with an asterisk (*), are hereby incorporated by reference and made Study of this agreement as if attached hereto. These documents can be viewed at https://www.dgs.ca.gov/OLS/Resources |  |  |  |  |  |  |  |  |
| IN WITNESS WHEREOF, THIS AGREEMENT HAS BEEN EXECUTED BY THE PARTIES HERETO. |  |  |  |  |  |  |  |  |
| CONTRACTOR |  |  |  |  |  |  |  |  |
| CONTRACTOR NAME (if other than an individual, state whether a corporation, partnership, etc.) |  |  |  |  |  |  |  |  |
| TBD |  |  |  |  |  |  |  |  |
| CONTRACTOR BUSINESS ADDRESS |  |  |  | CITY |  | STATE |  | ZIP |  |
| PRINTED NAME OF PERSON SIGNING |  |  |  | TITLE |  |  |  |  |  |
| CONTRACTOR AUTHORIZED SIGNATURE |  |  |  | DATE SIGNED |  |  |  |  |  |
| STATE OF CALIFORNIA |  |  |  |  |  |  |  |  |  |
| CONTRACTING AGENCY NAME |  |  |  |  |  |  |  |  |  |
| Department of Resources Recycling and Recovery |  |  |  |  |  |  |  |  |  |
| CONTRACTING AGENCY ADDRESS |  |  |  | CITY |  | STATE |  | ZIP |  |
| 1001 “I” Street |  |  |  | Sacramento |  | CA |  | 95814 |  |
| PRINTED NAME OF PERSON SIGNING |  |  |  | TITLE |  |  |  |  |  |
| Noah Valadez |  |  |  | Adminstrative Services Branch Chief |  |  |  |  |  |
| CONTRACTING AGENCY AUTHORIZED SIGNATURE |  |  |  | DATE SIGNED |  |  |  |  |  |

| STATE OF CALIFORNIA - DEPARTMENT OF GENERAL SERVICES |  |  |  |
| --- | --- | --- | --- |
| STANDARD AGREEMENT | AGREEMENT NUMBER |  | PURCHASING AUTHORITY NUMBER (If Applicable) |
| STD 213 (Rev. 03/2019) | DRR19070 |  |  |
| CALIFORNIA DEPARTMENT OF GENERAL SERVICES APPROVAL |  | EXEMPTION (If Applicable) |  |

EXHIBIT A

SCOPE OF WORK

- TBD (Contractor) agrees to provide to the Department of Resources Recycling and Recovery (CalRecycle), with organics recycling waste characterization study services as described herein.

- The Project Coordinators during the term of this Agreement will be:

| CalRecycle Contract Manager |  |  | TBD |  |
| --- | --- | --- | --- | --- |
| Name: | Katherine Wilkins |  | Name: | TBD |
| Phone: | (916) 322-2503 |  | Phone: | ( ) - |
| Fax: | (916) 319-7113 |  | Fax: | ( ) - |
| Email: | Katherine.Wilkins@calrecycle.ca.gov |  | Email: | @ |
| Direct all Agreement inquiries to: |  |  |  |  |
| CalRecycle Contract Analyst |  |  | TBD |  |
| Contracts Unit |  |  |  |  |
| Attention: |  | Melissa Mojonnier | Attention: | TBD |
| Address: |  | 1001 I St., MS 19-A | Address: |  |
|  |  | Sacramento, CA 95814 |  |  |
| Phone: |  | (916) 341-6048 | Phone: | ( ) - |
| Fax: |  | (916) 319-7390 | Fax: | ( ) - |
| Email: |  | melissa.mojonnier@calrecycle.ca.gov | Email: | @ |

- Work To Be Performed

- The Contractor shall sample recycling streams in three studies.

- Study 1: The Processing Facility-based Residual Characterization Study – Sampling material recovery facility and processing facility residuals, and pre-sorted rejections destined for disposal, including dual-stream processing lines, commingled single stream processing lines, mixed waste processing lines, and organic processing lines with food waste inflows to determine the composition of material destined for disposal at composting and anaerobic digestion facilities.

- Study 2: The Organics Recycling Inflow Characterization Study – Sampling incoming material to composter and anaerobic digestion facilities that accept food waste from commercial and residential sources, including solid waste permitted composting facilities accepting material from residential and commercial sources and anaerobic digestion facilities accepting material from residential and commercial sources to determine the composition of incoming organic material sent from a variety of generators, including but not limited to recyclable processing facilities (processed), transfer facilities (unprocessed), direct hauled from generators (unprocessed), and anaerobic digestion facilities (processed). This stream must be sampled in order to improve understanding of the materials/ material fragments found in the residual/rejected stream in Study 3 of the study.

- Study 3: The Organics Recycling Residuals Characterization Study – Sampling material destined for disposal from composter and anaerobic digestion facilities that accept food waste (e.g., biosolids, overs, residuals, rejects, physical contaminants), including solid waste permitted composting facilities and anaerobic digestion facilities to determine the residual composition of traditional recycling and organic recycling processing lines.

- Tasks Identified

The following apply to Tasks 1 through 3:

- The Contractor shall have a health and safety plan, implement health and safety measures, conduct training and monitor effectiveness.

- The Contractor shall comply with all local, state, and federal health and safety codes, regulations, and laws.

- The Contractor shall provide all equipment needed for fieldwork, including health and safety equipment. During the initial site recruitment, CalRecycle will determine if a loader/bobcat and driver are available on-site. If a loader/bobcat or similar equipment and a certified driver are not available, the Contractor shall arrange to rent a loader/bobcat or similar equipment and provide a certified driver.

- The Contractor shall accommodate observation by the Contract Manager, other CalRecycle staff, and possibly other interested parties, at the sampling sites.

- The Contractor shall implement QA/QC measures in the field to ensure the accuracy of the data collected.

Task 1 – Initial Meeting(s) to Review Proposed Study Design (Work Plan)

- The Contractor shall meet with the Contract Manager in person at the CalRecycle office in Sacramento (subsequent meetings can be virtual) to identify logistical details and fine-tune the Work Plan.  Discussion will pertain to:

- Study design as submitted in the contractor proposal.

- Tentative schedule for when subsequent tasks will begin (proposed by Contractor).

- The timeline and logistics for sampling.

- Estimated number of samples that can be accurately collected in a day.

- Replacement site recruitment criteria (i.e., amount of time to recruit replacements dependent on days before scheduled sampling).

- The targeted materials to be included for each study.

- Additional information required by subsequent tasks.

- For the Processing Facility-based Residual characterization Study: the potential sampling locations, lines for sampling, and number of samples.

- For the Organics Recycling Inflow Characterization Study: the potential sampling locations, number of samples from inflow types (processed and unprocessed), and number of samples.

- For the Organics Recycling Residuals Characterization Study: the potential sampling locations and number of samples.

- CalRecycle reserves the right to update locations if necessary.

- The Contractor shall submit the revised Work Plan based on decisions made at the initial meeting to the Contract Manager for approval within 15 calendar days of the meeting date.

- The Contract Manager will review this submittal to ensure it accurately represents the agreed upon details and is consistent with both the RFP and with the winning Proposal. The Contract Manager will respond within 15 calendar days with any needed final edits to the proposed revisions.

- The Contractor shall make required changes, if any, and submit to the Contract Manager within 15 calendar days of receiving the edits.

- No work shall commence on subsequent tasks without the Contract Manager’s written approval of the Work Plan.

Task 2 – Coordinate with Processing Facilities and Determine Field Schedule

- The Contractor shall, within 15 calendar days from receipt of the final list of sampling locations, inform the Contract Manager the tentative how many sampling days are expected at each site and how many samples will be sorted at each site, as well as if additional information is needed. The Contract Manager will provide the Contractor with the final list of sampling locations at least 45 calendar days before sampling begins and if additional information is needed, the Contract Manager will attempt to provide it within 10 calendar days of receiving notice.

- The Contractor shall promptly contact each location/site to confirm all of the logistics, specifically sample collection date(s), that health and safety requirements have been met, the availability of a loader/bobcat and driver if needed, and any other factors which will affect the sampling.

- The Contractor shall notify the Contract Manager by email within two business days of learning of a circumstance which will negatively impact the field schedule, requesting replacement sampling sites if needed.

- The Contractor shall ensure accurate and representative sampling at each sampling site by incorporating information on variations in site operations, residual flows, on-site processing/handling, and other relevant information into a sampling plan. At a minimum this information shall include:

- Type of facility.

- How facility manages their rejects and residuals, including any sent for further processing.

- Type of sorting and screening done and any other pre- or post-processing, like floor sorts, etc.

- Flow diagram and quantity of material destined for disposal from pre-sort and all ejection points.

- The origins of any pre-processed material accepted that may be sampled.

- Estimated percentage of inflow from commercial and residential sectors.

- Average length of active phase (Study 3).

- At least 15 calendar days before each sampling period begins, the Contractor shall provide the Contract Manager with:

  - a tentative schedule for sampling site order.

  - an overall schedule for fieldwork, describing start-up tasks, travel, set-up, and sorting days, and confirm the number of samples at each site and from each line.

- The Contractor shall address any concerns the Contract Manager identifies within 7 calendar days of receiving notice from the Contract Manager of any identified concerns. The Contract Manager will review the schedule and identify any concerns within 7 calendar days of receiving it.

- The Contractor shall follow the agreed upon final coordination and logistical arrangements with each site.

Task 3 – Perform Fieldwork/ Field Sampling and Sorting at Processing Facilities

- Task 3 Fieldwork for STUDY 1-Processing Facility-based Residual Characterization Study:

- The Contractor shall collect samples of residuals and pre-sort rejects from selected processing lines at sampling sites. Samples will represent only materials destined for disposal. The Contractor shall apply the methodology proposed and accepted by CalRecycle to collect a representative sample of residuals, based upon the processing flow and how residuals are managed and stored at each facility. The processing facility sampling shall result in data which allows the Contractor to produce an overall composition for residual disposal that accurately represents the proportions from the different ejection points. The Contractor shall also capture pre-sort rejects material removed before processing, overs (items that are too large for the processing system), unders (items that are too small for the processing system), and other materials separated for disposal.

- The Contractor shall identify the source sector (the location from which material is generated, i.e., from residential, commercial, industrial, or mixed residential and commercial pickups), or at a minimum the proportion of the incoming recycling stream from each sector when it is not possible to distinguish between source sectors, based on information provided by the facility.

- The Contractor shall hand-sort samples into individual material types on the finalized Processing Facility Material List (List A).

- The Contractor shall characterize fines (materials too fine to sort) according to the methodology laid out in their study plan and confirmed at the initial meeting described in Task 1.

- The Contractor shall make their best judgement to categorize the material that is difficult-to-sort due to adhesion, wetness, or partial decomposition and separate joined materials (such as a zip lock bag with metal screws in it) when it is practical to do so.

- The Contractor shall take and provide digital images with a minimum resolution of 12-megapixels of each load/sample, placing the sample number on, adjacent, or near the sample clearly identifying the unique load/sample ID number, location, and date.

- The Contractor shall assign each digital image file an electronic filename that correlates to the unique load/sample ID (e.g., Sample 1 from Facility A pictures are labeled Facility A_1_1, Facility A_1_2, etc.).

- The Contractor shall take a minimum of two clear digital images of the residual sample (covering 100% of sample combined), breaking open garbage bags and/or spreading out the sample to obtain acceptable images if necessary, before the sample is sorted. For each remainder composite category and mixed residue category, the Contractor shall take a digital image of the picture of the contents spread out on the ground from one sample at each facility throughout all of Study 1 sampling. For all other categories, the Contractor shall take a digital image of each material type from one sample at each facility throughout all of Study 1 sampling.

- The Contractor shall record the weight of each sorted material type and total sample weight (in decimal pounds), using a scale that is accurate to within 0.01 pounds and which is connected to a computer to record weights.

Task 3 Fieldwork for STUDY 2-Organics Recycling Inflow Characterization Study

- The Contractor shall collect samples of incoming material (prior to on-site processing) from selected sampling sites. Samples will only be taken from loads that include food waste and/or mixed materials. The Contractor shall apply the methodology proposed and accepted by CalRecycle to collect a representative sample from processed and unprocessed incoming loads from both residential and commercial sources.

- The Contractor shall hand-sort all samples into individual material types on the finalized Organics Facility Material List (List B).

- The Contractor shall make their best judgement to categorize the material that is difficult-to-sort due to adhesion, wetness, or partial decomposition and separate joined materials (such as a zip lock bag with metal screws in it) when it is practical to do so.

- The Contractor shall take and provide digital images with a minimum resolution of 12-megapixels of each load/sample, placing on, adjacent, or near the sample a written sample number clearly identifying the unique load/sample ID number, location, and date, and shall assign a filename to each digital image file which correlates to the unique load/sample ID (e.g., Sample 1 from Facility A pictures are labeled Facility A_1_1, Facility A_1_2, etc.).

- The Contractor shall take a minimum of two clear images of the residual sample before it is sorted that capture a clear shot of all the material in the sample (two pictures covering 100% of sample).

- If needed, the Contractor shall break open garbage bags and/or spread out the sample to obtain adequate digital images.

- For each remainder composite category and mixed residue category, the Contractor shall take a digital image of the picture of the contents spread out on the ground from one sample at each facility throughout all of Study 2 sampling. For all other categories, the Contractor shall take a digital image of each material type from one sample at each facility throughout all of Study 2 sampling.

- The Contractor shall record all characterization data for each sample, including:

- the weight of each sorted material type,

- the total sample weight,

- the sector origin for sample (residential, commercial or mixed), and

- whether or not the sample has been processed or not before delivery to the compost or anaerobic digestion operation (some operations may be on the same site as recyclable processing facilities).

- The Contractor shall record weights in decimal pounds using a scale that is accurate to within 0.01 pounds and is connected to a computer to record weights.

Task 3 Fieldwork for STUDY 3 - Organics Recycling Residuals Characterization Study

- The Contractor shall collect samples of material destined for landfill from selected sites. Samples will only be collected from materials generated from pre- and post-processing (i.e., before and after composting or digestion process) from loads of materials that include food from residential and/or commercial sources. The samples themselves may or may not include identifiable food. The Contractor shall apply the methodology proposed and accepted by CalRecycle to collect a representative sample of residuals, based upon the processing flow and how residuals are managed and stored at each facility. The Contractor shall capture pre-sort rejects material removed before processing, overs, unders, and other materials separated for disposal.

- The Contractor shall determine if any pre-sort rejects or residuals (e.g. overs, unders) are sent for further processing, and if so, where and what quantity or proportion of the residual material.

- The Contractor shall hand-sort all samples into individual material types on the finalized material list (List B).

- The Contractor shall take digital images, with a minimum resolution of 12-megapixels, of each load/sample, placing a sample number on, adjacent, or near the sample clearly identifying the unique load/sample ID number, location, and date.

- The Contractor shall assign to each digital image a filename which correlates to the unique load/sample ID (e.g. Sample 1 from Facility A pictures are labeled Facility A_1_1, Facility A_1_2, etc.).

- The Contractor shall take a minimum of two clear images of the residual sample before it is sorted, which clearly capture all of the material in the sample (two pictures covering 100% of sample), breaking open garbage bags and/or spreading out the sample, if necessary to obtain adequate digital images.

- For each remainder composite category and mixed residue category, the Contractor shall take a digital image of the contents spread out on the ground from one sample at each facility throughout all of Study 3 sampling. For all other categories, the Contractor shall take a digital image of each material type from one sample at each facility throughout all of Study 3 sampling.

- The Contractor shall record all characterization data for each sample, including:

  - The weight of each sorted material type, AND

  - the total sample weights.

- The Contractor shall record weights in decimal pounds using a scale that is accurate to within 0.01 pounds and is connected to a computer to record weights

Task 4 – Data Entry and Data QA/QC

- The Contractor shall provide sample printouts displaying database or spreadsheet format to the Contract Manager for approval.

- The Contractor shall implement QA/QC measures when providing field-sorting data for each sorted sample (weight of each material type in the sample) and total sample weight for all study Parts.

- The Contractor shall perform all data entry and follow all quality control measures in their plan to ensure the accuracy of the data entered. The Contractor shall resolve any errors or discrepancies in data discovered during quality control activities and/or review by the Contract Manager.

- The Contractor shall enter all data collected into electronic spreadsheets (e.g., Microsoft Excel) compatible with CalRecycle’s computer system. The Contract Manager will approve the format and software. The Contractor shall present the data in a format such as in Sample Data Format. The Contractor shall submit all final data to CalRecycle in electronic form (e.g., via e-mail or uploaded to a secure shared drive).

- The Contractor shall submit complete data for each sample, including, at a minimum:

- unique sample ID number,

- name of facility/site sample was collected from (unless privacy/confidential concerns and prior agreement between facility and CalRecycle),

- date of collection,

- total sample weight,

- weight of each component in the samples by material type,

- data used to calculate amounts,

- any notes on special circumstance or other information, as applicable, and

- all digital images.

- The Contractor shall submit final and correct data, after the Contractor has thoroughly reviewed and subjected the data to stringent QA/QC procedures.

- The Contractor shall submit all data required for the three studies.

- The Contractor shall identify data limitations CalRecycle should consider for its data analysis.

The Contract Manager shall review the submitted data to ensure it is complete, understandable, and usable for subsequent analyses. The Contractor shall respond to any questions and address any problems or discrepancies found by the Contract Manager within 15 calendar days.

Task 5 – Submit Field Data and Summary Reports to CalRecycle

- During the sample collection periods, the Contractor shall provide weekly status reports in the format of the Sample Weekly Report.  Upon request by the Contract Manager, the Contractor shall provide monthly status reports outside the field work period. The reports shall include project statuses including progress made, work done and work pending, and any deviation from the plan and provide a detailed explanation for the deviation. When appropriate, these reports shall also include meeting minutes.

- Not more than 20 calendar days after the completion of data collection, the Contractor shall notify the Contract Manager if there are any changes or corrections to the data already submitted and submit the corrected data.

- Not more than 20 calendar days after the end of the sampling period, the Contractor shall prepare and submit to the Contract Manager a report summarizing information on all samples completed including the following:

- The total number of samples collected and characterized,

- For each sample, corresponding site names the samples were obtained from,

- For each sample, the sector and/or subsector (where recorded),

- A description and explanation of any differences between the final sampling plan and the actual field sampling performed, and

- A description of any unusual circumstances.

- CalRecycle Responsibilities:

- For all three studies, CalRecycle is responsible for:

  - Recruiting sampling sites. The Contractor’s suggested or desired sites will be taken into consideration. A list of possible composting and anaerobic digestion sites is attached (Table 1 and Table 2).

  - If a replacement site is needed, and dependent on how soon the replacement is needed, CalRecycle will secure a replacement site in the same region or reallocate those samples. This replacement criteria will be determined at the initial meeting outlined in Task 1.

  - Upon receiving feedback about material types from the Contractor, CalRecycle may elect to change the material type list.

  - CalRecycle will conduct analyses of the data and prepare any final reports.

- For the Processing Facility-Based Residual Characterization Study:

  - CalRecycle will prioritize recruiting processing facilities that have both organic processing lines that handle food waste and traditional commodity recycling lines but acknowledges that there are a limited number of these facilities.

  - CalRecycle anticipates most of the recruited sites will be adjacent to or in the San Francisco Bay Area, Los Angeles Basin, and the Central Valley.

  - CalRecycle will determine the material types for hand-sorting characterizations (from Processing Facility Material – List A).

- For the Organics Recycling Inflow Characterization Study:

  - CalRecycle will recruit only:

    - Solid waste permitted anaerobic and aerobic composting facilities accepting food waste.

    - Anaerobic digestion facilities accepting food waste as a feedstock.

  - CalRecycle anticipates most of the recruited sites will be adjacent to or in the San Francisco Bay Area, Los Angeles Basin, and the Central Valley.

  - CalRecycle will determine the material types for hand-sorting characterizations (from Organics Facility Material - List B).

- For the Organics Recycling Residuals Characterization Study:

  - The same facilities used for Study 2 of the sampling will be prioritized for Study 3. If a selected organics processing facility does not wish to participate in both Studies, but only one, the Contractor will allocate more samples to another selected facility or a new facility (which CalRecycle will recruit).

  - CalRecycle anticipates most of the recruited sites will be adjacent to or in the San Francisco Bay Area, Los Angeles Basin, and the Central Valley.

  - CalRecycle will determine the material types for hand-sorting characterizations (from Organics Facility Material - List B).

List A – Processing Facility Material List and Definitions by Category

| Total | Category Code | Material Type and Definition | Examples |
| --- | --- | --- | --- |
| 1 | P1 | Uncoated Corrugated Cardboard means a paper laminate usually composed of three layers. The center wavy layer is sandwiched between the two outer layers. This type does not include paperboard boxes such as cereal and tissue boxes. Excludes glossy and waxed cardboard. | - shipping and moving boxes - sheets and pieces used as dividers in boxes - very clean pizza boxes (no food residue and only lightly stained) |
| 2 | P2 | Coated Corrugated Cardboard means a paper laminate usually composed of three layers. The center wavy layer is sandwiched between the two outer layers. It has a glossy coating on the inside, outside or both sides. This type does not include paperboard boxes such as cereal and tissue boxes. Excludes non-glossy, uncoated cardboard. | - computer packaging cartons - boxes used for primary packaging of various consumer goods |
| 3 | P3 | Uncoated Paper means all non-corrugated paper and paperboard that is not coated with another material. Can be bleached or colored. May be contaminated with food and/or moisture. | - paper grocery bags and other kraft bags - lunch bags - rice, flour and sugar bags - white office type paper and mail - envelopes without plastic windows - newspapers and election guides - manila envelopes and index cards - toilet paper and paper towel tubes |
| 4 | P4 | Coated Paper means all non-corrugated paper that is coated with another material, making the item glossy or waxy. This includes most paperboard packaging. May be contaminated with food and/or moisture. | - magazines - newspaper ad inserts - glossy brochures and catalogs - wrapping paper - breakfast cereal and frozen food boxes - cigarette cartons |
| 5 | P5 | Paper/Fiber Food Service Ware means items made mostly of paper that are used to consume, contain, or transport prepared food items. Includes paper and molded fiber, including compostable and non-compostable items. May be contaminated with food and/or moisture. | - plates, bowls, cups, and utensils - straws and stirrers - take-out containers - pizza boxes - bakery/bread bags - condiment cups |
| 6 | P6 | Aseptic Containers and Gable-top Cartons means bleached polycoated paperboard containers or paper containers with a foil liner of various sizes and shapes that contain shelf-stable food products (i.e., aseptic containers) and paper-based cartons with a triangular top used for refrigerated and non-refrigerated items (i.e., gable-top cartons) Containers may include a plastic pour spout as part of the container. | - containers for apple juice, soup, soy/rice milk - cartons used for milk, egg substitutes, and juice - gable-top containers used for snacks |
| 7 | P7 | Padded Envelopes – Paper means envelopes with a paper exterior, that may have plastic or other another material lining the interior of the envelope. Excludes envelopes with a plastic window. | - Kraft padded shipping envelopes - Kraft poly bubble mailers |
| 8 | P8 | Remainder/Composite Paper means items made mostly of paper that do not fit into any of the other paper types or are combined with large amounts of other materials. These are items that do not fit into any other categories and are not generally compostable or recyclable. | - blueprints - sepia and carbon paper - photographs - sheets of paper stick-on labels - chipboard - bagged shredded paper - envelope with plastic window |
| 9 | PL1 | Plastic Packaging means CRV or non-CRV bottles, jars, containers, lids, and other packaging that are made of types of all plastic types (1-7). This includes beverages, food or household product containers. Excludes EPS, flexible plastic pouches, compostable bags and film. | - beverage containers for soda, juice, etc. - jars and containers for food - containers for household products (e.g., shampoo, cleaning products) - vitamin bottles - yogurt cups, microwave food trays and cookie trays - single-use plant containers |
| 10 | PL2 | Expanded Polystyrene means all items made of expanded polystyrene. | - polystyrene cups, plates, bowls and clamshells - egg cartons - foam ice chests - polystyrene transport and other packaging for shipping |
| 11 | PL3 | Film Plastic means all film plastic used for plastic bags, sheeting, packaging and non-packaging uses. Excludes identifiable compostable plastic bags and flexible plastic pouches. | - garbage bags and can liners - grocery, merchandise and dry-cleaning bags - agricultural film, plastic sheeting and drop cloths - plastic food wrap, frozen vegetable bags and candy wrappers - sandwich bags, bread bags and zipper bags - newspaper and produce bags - mattress bags and furniture bags - film bubble wrap |
| 12 | PL4 | Compostable Plastic Bags means film plastic bags identifiable as compostable or biodegradable by the texture, color or labeling on the plastic. If unknown whether compostable, item should go in film plastic. | - compostable trash bags and compostable bin liners - compostable pet poop bags |
| 13 | PL5 | Flexible Plastic Pouches means plastic pouches made of thicker, multi-layer flexible material. Material is thicker than potato chip bags and frozen vegetable bags. May have a flat bottom so that package would stand up on its own, but not always. May have plastic screw tops. | - child resistant pouch bags - plastic coffee bags - juice pouches (e.g., Capri Sun) and baby food pouches - food pouches for soup, salad, wine, or backpacking meals - soap refill pouches |
| 14 | PL6 | Padded Envelopes – Plastic means envelopes with a plastic (any type) exterior with an interior lining of plastic or any other material. | - plastic poly bubble mailers - silver foil bubble bags |
| 15 | PL7 | Plastic Food Service Ware means items made partially or entirely of plastic that are used to consume, contain, or transport prepared food items. Includes all plastic types including compostable plastics. Excludes expanded polystyrene products. | - plates, bowls, and cups (and lids) - utensils, straws, and stirrers - take-out containers - bakery bags - condiment cups |
| 16 | PL8 | Durable Plastic Items means plastic items that are made to last for more than one use. These items may bear the numbers 1 through 7 in the triangular recycling symbol. | - crates, totes, buckets, and tubs - plastic garbage cans - flowerpots larger than one gallon - lawn furniture - plastic toys and sporting goods - CDs and cases plastic housewares including durable plates, cups, utensils - building materials such as house siding, housing for electronics, fan blades, plastic pipes and fittings |
| 17 | PL9 | Remainder/Composite Plastic means plastic that cannot be put in any other type. This type also includes items made mostly of plastic but combined with other materials. | - window blinds - insulating foam - imitation ceramics - handles and knobs, plastic lumber - rigid bubble/foil packaging (e.g., blister pack) and empty condiment packets - some toys, kitchenware and auto parts |
| 18 | G1 | Glass Bottles and Containers means all CRV and non-CRV clear and colored glass containers intended for single use, whole or broken. | - CRV glass like soda, fruit juice, beer and wine cooler bottles - non-CRV glass like wine and liquor bottles - food jars (e.g., pasta sauce, salsa, jam) |
| 19 | G2 | Remainder/Composite Glass means whole or broken glass that cannot be put Glass Bottles and Containers. It includes flat and curved glass and items made mostly of glass but combined with other materials. It also includes durable glass containers meant to be used more than once. | - windowpanes, doors and tabletop glass - automotive glass - safety glass - Pyrex and kitchen glass - crystal and glass tableware - drinking glasses - mirrors - non-fluorescent light bulbs - laminated glass |
| 20 | M1 | Metal Containers means all CRV and non-CRV cans and metal containers made from all metal types intended for single use. These may hold food, beverages, paint, and a variety of other household and consumer products. | - canned food and beverage containers - empty metal paint cans, spray paint cans and aerosol containers - bimetal containers with steel sides and aluminum ends - pet food, meat and wine cans |
| 21 | M2 | Major Appliances means discarded major appliances encased in metal, of any color. These items are often enamel-coated. This type does not include electronics, such as televisions and stereos. | - washing machines and dryers - hot water heater - stoves and refrigerators |
| 22 | M3 | Other Metal (ferrous, non-ferrous, and composite) means any metal item that does not fit in the Metal Containers or Appliances categories. This type includes items made mostly of metal but combined with other materials and items made of both ferrous metal and non-ferrous metal combined. | - structural steel beams - metal clothes hangers - metal pipes and brass pipes - metal cookware and reusable water bottles - aluminum foil - scrap ferrous items - aluminum window frames and siding - copper wire and insulated wire - shell casings - motors |
| 23 | SpW1 | Electronics means hard-to-handle items that are not defined elsewhere in the material types list, including furniture and large items that usually need electric currents or electromagnetic fields to operate. This also includes covered video display devices, consumer electronics and small equipment. Excludes major appliances that are generally not electronic. | - electronic musical equipment and exercise equipment - printers, computers, calculators, and mobile phones - toasters, irons, electric knives, sewing machines, and hair dryers - some toys and some sports equipment - hair care appliances |
| 24 | OR1 | Food – Packaged means any food item that is not easily separable from its packaging. This does not include packages with food residue only. | - half-full condiment jars - opened or unopened condiment packets - unopened soup can |
| 25 | OR2 | Food – Unpackaged means any food product, whole or partially consumed that is not in a container or is easily separated from its container. The container would then be sorted into one of the other material types. | - opened and unopened package of mushrooms, fruit salad, and salad greens - fruit and vegetable peels or trimmings - pits, shells, rinds, bones, and corn cobs - partially consumed burrito in foil - whole or partial fruits and vegetables - half eaten sandwich in original packaging - unfinished bag of chips - partially consumed frozen meals in tray |
| 26 | OR3 | Green Waste, Yard Waste and Manures means all woody and non-woody plant material of any diameter from public or private sources, or agricultural material. Also includes manure and soiled bedding items from large domestic, farm or ranch animals. Does not include feces from small household pets such as dogs and cats. | - leaves, grass clippings, plants, seaweed - pruning from shrubs, shrubs - branches, stumps - manure, soiled bedding from animal operations - agricultural crop residues |
| 27 | OR4 | Wood – Recyclable means clean dimensional lumber, clean engineered wood, clean pallets and crates, or other recyclable wood. This may include scrap from production of prefabricated wood products that have not been treated with paint, stain, or other chemical finish. Wood material should not be contaminated with another material (e.g., tar). Some trace contaminants and nails okay. | - 2 x 4s, 2 x 6s, 2 x 12s - residual materials from framing and related construction activities - plywood, particle board, wafer board - oriented strand board - residual materials used for sheathing and related construction uses - unpainted wood pallets and unpainted crates - lumber/engineered wood packaging - untreated scrap from production of prefabricated wood products (e.g. from cabinets or furniture) - untreated/unpainted fencing and recyclable demolition wood - untreated/unpainted wood roofing and siding |
| 28 | OR5 | Wood Waste (Nonrecyclable) – Treated/Painted/Stained Wood means wood that has been treated with a chemical preservative for purposes of protecting the wood against attacks from insects, microorganisms, fungi, and other environmental conditions that can lead to decay of the wood; and wood that has had an external coating such as paint, varnish, or other finish applied. | - handrails - finished furniture - other wood and wood products with paint, varnish, or other finish applied |
| 29 | OR6 | Remainder/Composite Organic means organic material that cannot be put in any other type. | - natural cork, hemp rope, straw baskets - small wood products (e.g., popsicle sticks, toothpicks) - sawdust and hair - animal carcasses - dryer sheets |
| 30 | InOth1 | Rock and Soil means rock pieces of any size and soil, dirt, and other matter. This type also includes nonhazardous contaminated soil. | - rock - stones - sand and clay - soil - compost |
| 31 | InOth2 | Remainder/Composite Inerts and Other means all inerts that are not rocks, soil or fines, including concrete, asphalt roofing, gypsum board and carpet. This type also may include items from different types combined, which would be very hard to separate. This type may also include demolition debris that is a mixture of items such as plate glass, wood, tiles, gypsum board, synthetic counter tops, fiber or composite acoustic ceiling tiles, and aluminum scrap. | - carpet - gypsum board, sheet rock, drywall, plasterboard - brick, ceramics, tiles - toilets and sinks - dried paint not attached to any materials - fiberglass and insulation - carpet padding - asphalt roofing, shingles, and paving - concrete paving, cinder blocks - pieces of building foundations |
| 32 | HHW1 | All Household Hazardous Waste & Special Waste Means household hazardous waste and special waste from other sectors that, if improperly put in the solid waste stream, may present handling problems or other hazards. Excludes dried paint, empty paint cans, or empty aerosol containers. | - paint and spent lubricating oil (e.g., crankcase and transmission oil, gear oil, hydraulic oil) - auto batteries, AA batteries, rechargeable batteries - asbestos-containing materials (e.g., certain pipes, insulation, floor tiles) - all propane gas cylinders - pills, liquid medications, creams and ointments - mercury-containing items such as thermostats or thermometers - treated medical waste and untreated medical waste (e.g., tubes, oxygen masks) |
| 33 | SW1 | Bulky Items Means bulky items like tires, furniture, and mattresses and foundations. | - automobile tires, bike tires, and lawn mower tires - mattresses and mattress foundations - couches and furniture - non-electronic musical equipment and exercise equipment |
| 34 | MISC1 | Textiles – Cloth and Clothing means cloth, clothing, sheets and towels, rope, and other textile items made of organic, synthetic, unknown, and mixed fibers. Textiles with zippers and buttons are included. | - cloth and rags - clothing - towels and sheets - rope |
| 35 | MISC2 | Textiles – Shoes, Belts and Bags means all shoes and boots, belts and bags whether made of leather, rubber, other materials, or a combination thereof. | - shoes and sandals - purses and backpacks - leather and cloth belts |
| 36 | MISC4 | Miscellaneous Residue means inorganic, organic or mixed material that cannot be put in any other type or category. | - kitchen ceramics - synthetic rubber products - diapers and feminine hygiene products - cosmetics |
| 37 | MISC5 | MRF Fines means material of small size that is too small to identify and sort and is ultimately sent to landfills for disposal. | - MRF residual fines - shredded paper pieces |

List B – Organics Facility Material List and Definitions by Category

| Total | Category Code | Material Type and Definition | Examples |
| --- | --- | --- | --- |
| 1 | P1 | Uncoated Corrugated Cardboard means a paper laminate usually composed of three layers. The center wavy layer is sandwiched between the two outer layers. This type does not include paperboard boxes such as cereal and tissue boxes. Excludes glossy and waxed cardboard. | - shipping and moving boxes - sheets and pieces used as dividers in boxes - very clean pizza boxes (no food residue and only lightly stained) |
| 2 | P2 | Coated Corrugated Cardboard means a paper laminate usually composed of three layers. The center wavy layer is sandwiched between the two outer layers. It has a glossy coating on the inside, outside or both sides. This type does not include paperboard boxes such as cereal and tissue boxes. Excludes non-glossy, uncoated cardboard. | - computer packaging cartons - boxes used for primary packaging of various consumer goods |
| 3 | P3 | Uncoated Paper means all non-corrugated paper that is not coated with another material. Can be bleached or colored. May be contaminated with food and/or moisture. | - paper grocery bags and other Kraft bags - lunch bags - pet food, rice, flour and sugar bags - white office type paper and mail - envelopes without plastic windows - newspapers and election guides - manila envelopes and index cards - toilet paper and paper towel tubes |
| 4 | P4 | Coated Paper means all non-corrugated paper that is coated with another material, making the item glossy or waxy. This includes most paperboard packaging. May be contaminated with food and/or moisture. | - magazines - newspaper ad inserts - glossy brochures and catalogs - wrapping paper - breakfast cereal and frozen food boxes - cigarette cartons |
| 5 | P5 | Paper/Fiber Food Service Ware means items made mostly of paper that are used to consume, contain, or transport prepared food items. Includes paper and molded fiber, including compostable and non- compostable items. May be contaminated with food and/or moisture. | - plates, bowls, cups, and utensils - straws and stirrers - take-out containers - pizza boxes - bakery/bread bags - condiment cups |
| 6 | P6 | Aseptic Containers and Gable-top Cartons means bleached polycoated paperboard containers or paper containers with a foil liner of various sizes and shapes that contain shelf-stable food products (i.e. aseptic containers) and paper-based cartons with a triangular top used for refrigerated and non-refrigerated items (i.e., gable-top cartons). Containers may include a plastic pour spout as part of the container. | - containers for apple juice, soup, and soy/rice milk - cartons used for milk, egg substitutes, and juice - gable-top containers used for snacks |
| 7 | P7 | Padded Envelopes – Paper means envelopes with a paper exterior, that may have plastic or other another material lining the interior of the envelope. Excludes envelopes with a plastic window. | - Kraft padded shipping envelopes - Kraft poly bubble mailers |
| 8 | P8 | Remainder/Composite Paper means items made mostly of paper that do not fit into any of the other paper types or are combined with large amounts of other materials. These are items that do not fit into any other categories and are not generally compostable or recyclable. | - blueprints - sepia and carbon paper - photographs - sheets of paper stick-on labels - chipboard - bagged shredded paper - envelope with plastic window |
| 9 | PL1 | Plastic Packaging. means CRV or non-CRV bottles, jars, containers, lids, and other packaging that are made of types of all plastic types (1-7). This includes beverages, food or household product containers. Excludes EPS, flexible plastic pouches, compostable bags and film. | - beverage containers for soda, juice, etc. - jars and containers for food - containers for household products (e.g. shampoo, cleaning products) - vitamin bottles - yogurt cups, microwave food trays and cookie trays - single-use plant containers |
| 10 | PL2 | Expanded Polystyrene means items made of expanded polystyrene. | - polystyrene cups, plates, bowls and clamshells - egg cartons - foam ice chests - polystyrene transport and other packaging for shipping |
| 11 | PL3 | Film Plastic means all film plastic used for plastic bags, sheeting, packaging and non-packaging uses. Excludes flexible plastic pouches and identifiable compostable plastic bags. | - garbage bags and can liners - grocery, merchandise and dry-cleaning bags - agricultural film, plastic sheeting and drop cloths - plastic food wrap, frozen vegetable bags and candy wrappers - sandwich bags, bread bags and zipper bags - newspaper and produce bags - mattress bags and furniture bags - film bubble wrap |
| 12 | PL4 | Compostable Plastic Bags means film plastic identifiable as compostable or biodegradable by the texture, color or labeling on the plastic. | - compostable trash bags and compostable bin liners - compostable pet poop bags |
| 13 | PL5 | Flexible Plastic Pouches means plastic pouches made of thicker, multi-layer flexible material. Material is thicker than potato chip bags and frozen vegetable bags. May have a flat bottom so that package would stand up on its own, but not always. May have plastic screw tops. | - child resistant pouch bags - plastic coffee bags - juice pouches and baby food pouches - food pouches for soup, salad, wine - backpacking meals - soap refill pouches |
| 14 | PL6 | Padded Envelopes – Plastic means envelopes with a plastic (any type) exterior with an interior lining of plastic or any other material. | - plastic poly bubble mailers - silver foil bubble bags |
| 15 | PL7 | Plastic Food Service Ware means items made partially or entirely of plastic that are used to consume, contain, or transport prepared food items. Includes all plastic types including compostable plastics. Excludes expanded polystyrene products. | - plates, bowls, and cups (and lids) - utensils, straws, and stirrers - take-out containers - bakery bags - condiment cups |
| 16 | PL8 | Durable Plastic Items means plastic items that are made to last for more than one use. These items may bear the numbers 1 through 7 in the triangular recycling symbol. | - crates, totes, buckets, and tubs - plastic garbage cans - flowerpots larger than one gallon - lawn furniture - plastic toys and sporting goods - CDs and cases plastic housewares including durable plates, cups, utensils - building materials such as house siding, housing for electronics, fan blades, plastic pipes and fittings |
| 17 | PL9 | Remainder/Composite Plastic means plastic that cannot be put in any other type. This type also includes items made mostly of plastic but combined with other materials. | - window blinds - insulating foam - imitation ceramics - handles and knobs, plastic lumber - rigid bubble/foil packaging (e.g. blister pack) and empty condiment packets - some toys, kitchenware and auto parts |
| 18 | G1 | All Glass means CRV and non-CRV glass of any color or type, whole or broken. This includes bottle and container glass, flat glass, curved glass, and items made mostly of glass but combined with other materials. | - CRV glass like soda, fruit juice, beer and wine cooler bottles - non-CRV wine and liquor bottles - food jars - windowpanes, door and tabletop glass - automotive glass and safety glass - Pyrex and kitchen glass - drinking glasses - mirrors - non-fluorescent light bulbs |
| 19 | M1 | All Metal means all metal containers and non-containers made from all metal types. May hold food, beverages, paint, and a variety of other household and consumer products. This also includes major appliances but not electronics. | - canned food and beverage containers - empty aerosol cans - pet food, meat and wine cans - bimetal containers with steel sides and aluminum ends - major appliances - metal hangers, scrap ferrous items - copper wire and insulated wire |
| 20 | OR1 | Food – Packaged means any food item that is not easily separable from its packaging. This does not include packages with food residue only. | - half-full condiment jars - opened or unopened condiment packets - unopened soup can |
| 21 | OR2 | Food – Unpackaged means any food product, whole or partially consumed that is not in a container or is easily separated from its container. The container would then be sorted into one of the other material types. | - opened and unopened package of mushrooms, fruit salad, and salad greens - fruit and vegetable peels or trimmings - pits, shells, rinds, bones, and corn cobs - partially consumed burrito in foil - whole or partial fruits and vegetables - half eaten sandwich in original packaging - unfinished bag of chips - partially consumed frozen meals in tray |
| 22 | OR3 | Green Waste, Yard Waste and Manures means all woody and non-woody plant material of any diameter from public or private sources, or agricultural material. Also includes manure and soiled bedding items from large domestic, farm or ranch animals. Does not include feces from small household pets such as dogs and cats. | - leaves, grass clippings, plants, seaweed - pruning from shrubs, shrubs - branches, stumps - manure, soiled bedding from animal operations - agricultural crop residues |
| 23 | OR4 | Sludge Means mixture of liquid and solid components that cannot be further sorted. | - Mud |
| 24 | OR5 | Wood – Recyclable means clean dimensional lumber, clean engineered wood, clean pallets and crates, or other recyclable wood. This may include scrap from production of prefabricated wood products that have not been treated with paint, stain, or other chemical finish. Wood material should not be contaminated with another material (e.g., tar). Some trace contaminants and nails okay. | - 2 x 4s, 2 x 6s, 2 x 12s - residual materials from framing and related construction activities - plywood, particle board, wafer board - oriented strand board - residual materials used for sheathing and related construction uses - unpainted wood pallets and unpainted crates - lumber/engineered wood packaging - untreated scrap from production of prefabricated wood products (e.g., from cabinets or furniture) - untreated/unpainted fencing and recyclable demolition wood - untreated/unpainted wood roofing and siding |
| 25 | OR6 | Wood Waste (Nonrecyclable) – Treated/Painted/Stained Wood means wood that has been treated with a chemical preservative for purposes of protecting the wood against attacks from insects, microorganisms, fungi, and other environmental conditions that can lead to decay of the wood; and wood that has had an external coating such as paint, varnish, or other finish applied. | - handrails - finished furniture - other wood and wood products with paint, varnish, or other finish applied |
| 26 | OR7 | Remainder/Composite Organic means organic material that cannot be put in any other type. | - natural cork, hemp rope, straw baskets - small wood products (e.g., popsicle sticks, toothpicks) - sawdust and hair - animal carcasses - dryer sheets |
| 27 | InOth1 | All Inerts means all inerts of any size, including rock, soil, dines, concrete, carpet, and items from different types combined which would be very difficult to separate. | - rock, stones, sand and clay - soil and compost - carpet, drywall, fiberglass and dried paint - toilets and sinks |
| 28 | MISC1 | All Textiles means cloth, clothing, sheets and towels, rope, and other textile items made of organic, synthetic, unknown, and mixed fiber as well as all shoes, purses, belts and other primarily-textile accessories. | - cloth and rags - clothing, towels, sheets and rope - shoes and sandals - purses and belts, bags, and backpacks |
| 29 | MISC2 | Miscellaneous Residue means bulky items, household hazardous waste, special wastes and inorganic items that cannot be put in any other type but could be sorted. | - diapers and feminine hygiene products - cosmetics - treated and untreated medical waste - paint - pills, liquid medications, creams and ointments - thermostats or thermometers - all propane gas cylinders |
| 30 | MISC3 | Fines means material of small size that is too small to identify and sort and is ultimately sent to landfills for disposal. | - clumping kitty litter - feces from household pets - MRF residual fines - shredded paper pieces - plastic nurdles |

Sample Weekly Report

Project Name:

Project Status Reporting Period: From: To:

Project Manager:

Report Prepared By:

Weekly Project Summary: Enter a brief summary of the project status, noting any key issues for the week. Comment on major deliverables completed; milestones reached and percent complete.

Current Task Summary

| Task or Deliverable | Scheduled Completion Date | Actual Completion Date | Issues? If yes, explain |
| --- | --- | --- | --- |
| Example: Sample Task 1 | 31 March 2020 | 1 April 2020 | No issues for Sample Task 1 |

Accomplished this week

Sites and samples

Sorting: Indicate number of hand-sorts completed per sector (and subsector), at which sites and day(s) and provide required attachments such as photos or site details

Attachments provided? (Such as copies of paper field sheets (if any), digital images, electronic files that contain data from the previous week) Yes/No If no, provide a reasonable explanation and a date when the attachments will be submitted.

Other items such as problems, contingency measures taken, significant findings encountered, recommendations:

Weekly look ahead - Planned/Scheduled Completion in Next Two Weeks

What sites and how many days per site?

Sample Plan (Confirm the Plan Provided by CalRecycle)

Deliverables Due:

Other items, concerns, issues:

Sample Data Collection Plan

Facility:

[Site Visit – if doing]:

Stream/line type:

Contact:

Confirmed Sort Dates:

Processing Overview:

Residual/reject management:

Residual/Reject Summary

| Residual Sources | Description | Estimated Contribution to Total Residual/Amount |
| --- | --- | --- |
| 1 | [ex. front of line rejects] |  |
| 2 | [ex. container residual] |  |
|  | Total |  |

Diverted Material Summary

|  | Description | Estimated Amount/% of residuals |
| --- | --- | --- |
| 1 |  |  |
| 2 |  |  |
|  | Total |  |

Inflows

|  | Description | Estimated % |
| --- | --- | --- |
| 1 | Residential |  |
| 2 | Commercial |  |
|  | Total |  |

Flow Diagram:

Residual Sampling Plan:

Origins of Preprocessed material that may be sampled?

Study 3 – Length of active phase?

Facility Support:

Proposed Work Area:

THIS PAGE INTENTIONALLY LEFT BLANK

| Sample Data Format for the Organics Recycling Characterization Study |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| For the Processing Facility-based Residual Characterization Study, at a minimum, the following fields are required: |  |  |  |  |  |  |  |  |  |  |  |
| Sample Date | Unique Sample ID Number | Name of Facility/Site Sample was Collected From | Stream | Sector | Total Sample Weight (pounds) | Material Type #1 (pounds) | Material Type #2 etc. (pounds) | General Information, Special Circumstances, etc. |  |  |  |  |
| For the Organics Recycling Inflow Characterization Study, at a minimum, the following fields are required: |  |  |  |  |  |  |  |  |  |  |
| Sample Date | Unique Sample ID Number | Name of Facility/Site Sample was Collected From | AD/ Compost Details | Sector | Unprocessed/ processed | Total Sample Weight (pounds) | Material Type #1 (pounds) | Material Type #2-etc. (pounds) | General Information, Special Circumstances, etc. |  |  |  |
| For the Organics Recycling Residual Characterization Study, at a minimum, the following fields are required: |  |  |  |  |  |  |  |  |  |  |  |
| Sample Date | Unique Sample ID Number | Name of Facility/Site Sample was Collected From | AD/ Compost Details | Sector | Total Sample Weight (pounds) | Material Type #1 (pounds) | Material Type #2-etc. (pounds) | General Information, Special Circumstances, etc. |  |  |  |  |

Table 1

| Food Waste Composting Facilities (Active Composting) |  |  |  |
| --- | --- | --- | --- |
| Facility | County | Type | SWIS Link |
| AgroThrive, Inc. | Monterey | Within - Vessel (tanks) | https://www2.calrecycle.ca.gov/swfacilities/Directory/27-AA-0119/ |
| B. Goodrow, Inc. Composting | San Luis Obispo | Windrow | https://www2.calrecycle.ca.gov/swfacilities/Directory/40-AA-0037/ |
| City Of Modesto Co-Compost Project | Stanislaus | Windrow | https://www2.calrecycle.ca.gov/swfacilities/Directory/50-AA-0018/ |
| City of Napa Composting Facility | Napa | ASP & Windrows | https://www2.calrecycle.ca.gov/swfacilities/Directory/28-AA-0030/ |
| Coachella Valley Composting Facility | Riverside | Windrow | https://www2.calrecycle.ca.gov/swfacilities/Directory/33-AA-0292/ |
| Cold Creek Compost, Inc. | Mendocino | ASP & Windrows | https://www2.calrecycle.ca.gov/swfacilities/Directory/23-AA-0029/ |
| El Corazon Compost Facility | San Diego | ASP - Biofilter | https://www2.calrecycle.ca.gov/swfacilities/Directory/37-AA-0907/ |
| Engel & Gray Inc | Santa Barbara | Windrows | https://www2.calrecycle.ca.gov/swfacilities/Directory/42-AA-0053/ |
| Feather River Organics | Yuba | Windrow | https://www2.calrecycle.ca.gov/swfacilities/Directory/58-AA-0015/ |
| Forward Resource Recovery Facility | San Joaquin | Windrow | https://www2.calrecycle.ca.gov/swfacilities/Directory/39-AA-0020/ |
| Gabilan Ag Services | Monterey | Windrow | https://www2.calrecycle.ca.gov/swfacilities/Directory/27-AA-0085/ |
| Harvest Power California, LLC | Tulare | Windrow | https://www2.calrecycle.ca.gov/swfacilities/Directory/54-AA-0026/ |
| Harvest-Lathrop | San Joaquin | Windrow | https://www2.calrecycle.ca.gov/swfacilities/Directory/39-AA-0051/ |
| Jepson Prairie Organics Composting Fac | Solano | Windrow / ASP | https://www2.calrecycle.ca.gov/swfacilities/Directory/48-AA-0083/ |
| Kochergen Farms Composting | Kings | Windrow | https://www2.calrecycle.ca.gov/swfacilities/Directory/16-AA-0022/ |
| Liberty Composting Inc. | Kern | Windrow | https://www2.calrecycle.ca.gov/swfacilities/Directory/15-AA-0287 |
| Mariposa Co. Composting Facility | Mariposa | In-Vessel | https://www2.calrecycle.ca.gov/swfacilities/Directory/22-AA-0013/ |
| MidValley Disposal Transfer Recycling St | Fresno | ASP | https://www2.calrecycle.ca.gov/swfacilities/Directory/10-AA-0201/ |
| Miramar Greenery | San Diego | Windrow | https://www2.calrecycle.ca.gov/swfacilities/Directory/37-AB-0003/ |
| Monterey Peninsula Landfill | Monterey | Windrow | https://www2.calrecycle.ca.gov/swfacilities/Directory/27-AA-0010/ |
| Mt Vernon Ave Recycling & Composting Fac | Kern | Windrow | https://www2.calrecycle.ca.gov/swfacilities/Directory/15-AA-0311/ |
| Newby Island Compost Facility | San Jose | Windrow | https://www2.calrecycle.ca.gov/swfacilities/Directory/43-AN-0017/ |
| Pebbly Beach (Avalon) Disposal Site | Los Angeles | Windrow | https://www2.calrecycle.ca.gov/swfacilities/Directory/19-AA-0061/ |
| Recology Blossom Valley Organics N Verna | San Joaquin | Windrow | https://www2.calrecycle.ca.gov/swfacilities/Directory/50-AA-0020/ |
| Recology Blossom Valley Organics- South | Kern | Windrow | https://www2.calrecycle.ca.gov/swfacilities/Directory/15-AA-0307/ |
| Robert A Nelson Transfer Station & MRF | Riverside | Covered ASP | https://www2.calrecycle.ca.gov/swfacilities/Directory/33-AA-0258/ |
| South Lake Resource Recovery and Compost | Lake | Windrow | https://www2.calrecycle.ca.gov/swfacilities/Directory/17-AA-0014/ |
| South Valley Organic Composting Facility | Santa Clara | Windrow | https://www2.calrecycle.ca.gov/swfacilities/Directory/43-AA-0017/ |
| Tierra Verde Industries EcoCentre | Orange | Windrow | https://www2.calrecycle.ca.gov/swfacilities/Directory/30-AB-0403/ |
| Victor Valley Regional Composting Fac. | San Bernardino | Windrow | https://www2.calrecycle.ca.gov/swfacilities/Directory/36-AA-0403/ |
| Waste Management Altamont | Alameda | ASP | https://www2.calrecycle.ca.gov/swfacilities/Directory/01-AA-0325/ |
| WCCSLF Organic Materials Processing | Contra Costa | Windrow | https://www2.calrecycle.ca.gov/swfacilities/Directory/07-AA-0044/ |
| West Valley Materials Recovery Facility | San Bernardino | Windrow | https://www2.calrecycle.ca.gov/swfacilities/Directory/36-AA-0341/ |
| WM Earthcare of Marin | Marin | ASP | https://www2.calrecycle.ca.gov/swfacilities/Directory/21-AA-0068/ |
| Z-Best Composting Facility | Santa Clara | Windrow/ AgBag | https://www2.calrecycle.ca.gov/swfacilities/Directory/43-AA-0015/ |

Table 2 - California Anaerobic Digestion Projects Accepting Organics from the Municipal Solid Waste Stream (November 2019)

| Project Name | Location | Site | Feedstocks | Diges--tion | Biogas Use | Status | Project Website |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Blue Line Biogenic CNG Facility | South San Francisco | Stand-Alone | Green Waste & Food Waste | Dry | CNG Transpor--tation Fuel | Operational | http://ssfscavenger.com/ad-facility/ |
| Central Marin Organic Waste Receiving Program | San Rafael | Co-Digestion | Food Waste, Fats, Oils, & Grease (FOG), & Sewage Sludge | Wet | Electricity | Operational | https://marinsanitaryservice.com/food2energy/ |
| CR&R Material Recovery Facility | Perris | Stand-Alone | Green Waste & Food Waste | High Solids | CNG Transport-ation Fuel & Pipeline Injection | Operational | http://crrwasteservices.com/sustainability/anaerobic-digestion/ |
| East Bay Municipal Utilities District – Wastewater Treatment Plant | Oakland | Co-Digestion | Food Waste, Sewage Sludge, & FOG | Wet | Electricity | Operational | http://www.ebmud.com/wastewater/recycling-water-and-energy/ |
| Los Angeles County Sanitation District – Joint Water Pollution Control Plant | Carson | Co-Digestion | Food Waste & Sewage Sludge | Wet | Electricity | Operational | https://www.lacsd.org/services/solidwasteprogram/food_waste_recycling.asp |
| North State Rendering | Oroville | Co-Digestion | Food Waste, FOG, & Sewage Sludge | Wet | Electricity & CNG Transport-ation Fuel | Operational | https://www.biocycle.net/2019/09/18/evolution-food-waste-digester/ |
| Ralphs Renewable Energy Facility – Compton Distribution Center | Compton | Stand-Alone | Food Waste | Wet | Electricity | Operational | https://www.greenbiz.com/news/2013/08/09/kroger-fuels-warehouse-food-waste |
| San Luis Obispo Kompogas AD Facility | San Luis Obispo | Stand-Alone | Green Waste & Food Waste | Dry | Electricity | Operational | https://www.sanluisgarbage.com/organics/dry-anaerobic-digestion/ |
| UC Davis Renewable Energy Anaerobic Digester (READ) | Davis | Stand-Alone | Food Waste | High Solids | Off-Site Boilers | Operational | https://facilities.ucdavis.edu/utilities/read |
| Victor Valley Wastewater Reclamation Authority – Wastewater Treatment Plant | Victorville | Co-Digestion | Food Waste, FOG, & Sewage Sludge | Wet | Electricity | Operational | https://www.vvwra.com/depts/human_resources/planning_and_development/projects.htm |
| Yolo County Anaerobic Composter | Woodland | Stand-Alone | Food Waste & Green Waste | High Solids | CNG Transport--ation Fuel & Electricity | Operational | https://www.calrecycle.ca.gov/blogs/in-the-loop/in-the-loop/2019/11/18/yolo-county-ad- composter |
| Zero Waste Energy Development (ZWED) | San Jose | Stand-Alone | Green Waste, Food Waste, & Manure | Dry | Electricity | Operational | http://zwedc.com/ |
| Incline Clean Energy (Formerly Clean World South Area Transfer Station) | Sacramento | Stand-Alone | Food Waste | High Solids | CNG Transport-ation Fuel & Electricity | Inactive | http://www.cleanworld.com/news/cleanworlds-sacramento-biodigester-named-international- bioenergy-project-of-the-year/ |
| Inland Empire Utilities Agency – Regional Water Recycling Plant No. 5 Solids Handling Facility | Chino | Co-Digestion | Food Waste, Sewage Sludge, & Manure | Wet | Electricity | Inactive | http://www.ieua.org/facilities/rp-5-shf/ |
| Monterey Zero Waste Energy | Marina | Stand-Alone | Green Waste & Food Waste | Dry | Electricity | Inactive | http://www.mrwmd.org/organics-to-energy/ |
| Agromin Zero Waste Energy | Oxnard | Stand-Alone | Green Waste & Food Waste | Dry |  | Pending | http://zerowasteenergy.com/wp-content/uploads/2013/11/ZWE-SmartfermOxnardFlyer.pdf |
| City of Manteca Wastewater Quality Control Facility Waste-to-Fuel Program | Manteca | Co-Digestion | Food Waste, Sewage Sludge, & FOG | Wet | CNG Transport-ation Fuel | Pending | https://www.ci.manteca.ca.us/PublicWorks/Pages/Waste-to-Fuel-Program.aspx |
| City of Napa Materials Diversion Facility | American Canyon | Stand-Alone | Green Waste & Food Waste | Dry | CNG Transportation Fuel | Pending | https://zerowasteenergy.com/our-projects/city-napa-napa-recycling-waste-services/ |
| Davis Street Anaerobic Digester | San Leandro | Stand-Alone | Green Waste & Food Waste | Dry |  | Pending | https://www2.calrecycle.ca.gov/swfacilities/Directory/01-AA-0007/ |
| East County Bioenergy Project | Antioch | Co-Digestion | Food Waste, Sewage Sludge, & FOG | Wet |  | Pending | https://www.deltadiablo.org/east-county-bioenergy-project |
| Escondido Resource Recovery | Escondido | Stand-Alone | Food Waste & Green Waste | Dry | CNG Transport- ation Fuel & Pipeline Injection | Pending | https://www.escondidodisposal.com/edco-recycling--transfer-in-signal-hill.htm |
| Lakeside Food-Scraps-to-Energy | Lakeside | Stand-Alone | Food Waste & FOG | Dry | Electricity | Pending | https://www.foodscraps2energy.com/ |
| Orange County Sanitation District Plant 2 | Huntington Beach | Co-Digestion | Food Waste & Sewage Sludge | Wet |  | Pending | https://www.ocsd.com/Home/ShowDocument?id=23427 |
| Renewable Sonoma Organics Processing Facility | Santa Rosa |  | Green Waste & Food Waste |  |  | Pending | https://zerowastesonoma.gov/organicsfacility |
| ReSource Center (Formerly Tajiguas Resource Recovery Project) | Santa Barbara County | Stand-Alone | Green Waste & Food Waste | Dry | Electricity | Pending | http://www.resourcerecoveryproject.com/ |
| Rialto Bioenergy Facility | Rialto | Stand-Alone | Food Waste & FOG | Wet | Electricity & RNG Pipeline Injection | Pending | https://www.waste360.com/anaerobic-digestion/anaergia-launches-rialto-calif-food-diversion- energy-recovery-plant |
| San Bernardino BioDigester | San Bernardino | Stand-Alone | Food Waste | Wet | Electricity | Pending | http://innovation.energy.ca.gov/SearchResultProject.aspx?p=30049&tks=637091531255109632 |
| Silicon Valley Clean Water – Wastewater Treatment Plant | Redwood City | Co-Digestion | Food Waste, FOG, & Sewage Sludge | Wet |  | Pending | http://www.svcw.org/innovation/SitePages/foodwastetoenergy.aspx |

- Contract/Task Time Frame

| Task | Start Date | End Date |
| --- | --- | --- |
| Contract must be signed and executed | Contract Execution Date | No later than June 30, 2020 |
| Task 1 Initial Meeting | Within 15 days of contract execution | January 1, 2021 |
| Task 2 Coordinate with Processing Facilities and Determine Field Schedule | Before January 1, 2021 | January 1, 2022 |
| Task 3 Fieldwork | Before January 1, 2021 | January 1, 2022 |
| Task 4 Data Entry and Data QA/QC | Concurrent with Task 3 | January 21, 2022 |
| Task 5 Submit Field Data and Summary Reports to CalRecycle | Concurrent with Task 3 | January 21, 2022 |

EXHIBIT B

BUDGET DETAIL AND PAYMENT PROVISIONS

- INVOICING AND PAYMENT:

- For services satisfactorily rendered and upon receipt and approval of the invoices, the State agrees to compensate the Contractor for completed deliverables in accordance with the rates specified herein.

- Itemized invoices shall be submitted in triplicate, with two sets of supporting documentation (i.e., receipts, timesheets, etc.), not more frequently than monthly in arrears to:

Accounts Payable

Department of Resources Recycling and Recovery

Fiscal Services Branch

U.S. Postal Correspondence:

P.O. Box 4025, MS-19A

Sacramento, CA 95812-4025

Federal Express Correspondence:

1001 I Street, MS-19A

Sacramento, CA 95814

- Each invoice submitted to CalRecycle shall include the following information:

  - Invoice Number

  - Contract Number

  - Description of Rendered Activities/Services

  - Submitting Contractor’s Address

  - Invoice Period

- BUDGET CONTINGENCY CLAUSE:

- It is mutually agreed that if the Budget Act of the current year and/or any subsequent years covered under this Agreement does not appropriate sufficient funds for the program, this Agreement shall be of no further force and effect.  In this event, the State shall have no liability to pay any funds whatsoever to the Contractor or to furnish any other considerations under this Agreement and the Contractor shall not be obligated to perform any provisions of this Agreement.

- If funding for any fiscal year is reduced or deleted by the Budget Act for purposes of this program, the State shall have the option to either: cancel this Agreement with no liability occurring to the State, or offer an Agreement Amendment to the Contractor to reflect the reduced amount.

- PROMPT PAYMENT CLAUSE: Payment will be made in accordance with and within the time specified in Government Code, Chapter 4.5 (commencing with Section 927).

- TAXES:  The State of California is exempt from Federal Excise Taxes, and no payment will be made for any taxes levied on employees' wages.  The State will pay for any applicable State of California or local sales or use taxes on the services rendered or equipment or parts supplied pursuant to this Agreement.  California may pay any applicable sales or use tax imposed by another state.

- COST BREAKDOWN:

<<Costs of winning Proposer will appear here>>

- TRAVEL CLAUSE: All travel will be reimbursed at the excluded employee travel rates in accordance with the California Code of Regulations Title 2, Division 1, Chapter 3, Subchapter 1, Article 2, Section 599.615.1 et seq.  The Contractor will be held to the State per diem rates in effect at the time of travel.  For specific per diem (lodging, meals and incidentals) reimbursement rates, see California Code of Regulations Title 2, Division 1, Chapter 3, Subchapter 1, Article 2, Section 599.619.  For this Agreement, the Contractor’s headquarters are located at (Contractor Address) Per diem will not be reimbursed for travel within 50 miles of Contractor’s headquarters.

- PAYMENT WITHHOLD:  The provisions for payment under this contract will be subject to a ten percent (10%) withholding per invoice.  The withheld payment amount will be included in the final payment to the Contractor and will only be released when all required work has been completed to the satisfaction of CalRecycle.  The Contractor agrees to comply with the requirements of PCC section 10346.

EXHIBIT D

SPECIAL TERMS AND CONDITIONS

    - AGENCY LIABILITY: The Contractor warrants by execution of this Agreement, that no person or selling agency has been employed or retained to solicit or secure this Agreement upon Agreement or understanding for a commission, percentage, brokerage, or contingent fee, excepting bona fide employees or bona fide established commercial or selling agencies maintained by the Contractor for the purpose of securing business. For breach or violation of this warranty, CalRecycle shall, in addition to other remedies provided by law, have the right to annul this Agreement without liability, paying only for the value of the work actually performed, or otherwise recover the full amount of such commission, percentage, brokerage, or contingent fee.

    - AMENDMENT: No amendment or variation of the terms of this Agreement shall be valid unless made in writing, signed by the parties and approved as required.  No oral understanding or Agreement not incorporated in this Agreement is binding on any of the parties.  CalRecycle reserves the right to amend this Agreement through a formal written amendment signed by both parties, for additional time and/or funding.

    - CALIFORNIA WASTE TIRES: Unless otherwise provided for in this contract, in the event the Contractor and/or Subcontractor(s) purchases waste tires or waste-tire derived products for the performance of this Agreement, only California waste tires and California waste tire-derived products shall be used. As a condition of payment under this Agreement, the Contractor must provide documentation substantiating the source of the tire materials used during the performance of this Agreement to the Contract Manager.

All formal notices required by this Agreement shall be given in writing and sent by prepaid certified mail, fax, personal delivery or telex.

    - CONTRACT MANAGEMENT: The Contractor and the agents and employees of the Contractor, in the performance of this Agreement, shall act in an independent capacity and not as officers or employees or agents of the State of California. The Contractor may change the designated Project Director, but CalRecycle reserves the right to approve any substitution of the Project Director. Contractor’s key personnel may not be substituted without CalRecycle’s Contract Manager’s prior written approval. CalRecycle may change the Contract Manager by notice given to the Contractor at any time. CalRecycle staff will be permitted to work side by side with the Contractor’s staff to the extent and under conditions that may be directed by the Contract Manager. In this connection, CalRecycle’s staff will be given access to all required data, working papers, etc. The Contractor will not be permitted to utilize the CalRecycle’s staff for the performance of services, which are the responsibility of the Contractor unless the Contract Manager previously agreed to such utilization in writing, and any appropriate adjustment in price is made. No charge will be made to the Contractor for the services of CalRecycle’s staff for coordination or monitoring functions.

    - CONTRACTOR EVALUATIONS: CalRecycle will evaluate the Contractor’s performance within sixty days of the completion of this Agreement and shall remain on file by CalRecycle for a period of thirty-six months. If the Contractor does not satisfactorily perform the work or service specified in this Agreement, CalRecycle will submit a copy of the negative evaluation to the Department of General Services (DGS), Office of Legal Services, within five (5) working days of the completion of the evaluation. Upon filing an unsatisfactory evaluation with the DGS, CalRecycle shall notify and send a copy of the evaluation to the Contractor within fifteen days. The Contractor shall have thirty days to prepare and send a written response to CalRecycle and the DGS. CalRecycle and the DGS shall file the Contractor's statement with the evaluation.  (PCC § 10369).

    - CONFIDENTIALITY/PUBLIC RECORDS: The Contractor and CalRecycle understand that each party may come into possession of information and/or data, which may be deemed confidential or proprietary by the person or organization furnishing the information or data. Such information or data may be subject to disclosure under the California Public Records Act, commencing with Government Code section 6250, or the PCC. CalRecycle agrees not to disclose such information or data furnished by Contractor and to maintain such information or data as confidential when so designated by Contractor in writing at the time it is furnished to CalRecycle, only to the extent that such information or data is exempt from disclosure under the California Public Records Act and the PCC.

    - CONFLICT-FUTURE BIDDING LIMITATION: Pursuant to Public Contracts Code Section 10365.5:

      - No person, firm, or subsidiary therefore who has been awarded a consulting services contract may submit a bid for, nor be awarded a contract for, the provision of services, procurement of goods or supplies, or any other related action that is required, suggested, or otherwise deemed appropriate in the end product of the consulting services contract.

      - Subdivision (a) does not apply to any person, firm, or subsidiary thereof who is awarded a subcontract of a consulting services contract that amounts to no more than ten (10) percent of the total monetary value of the consulting services contract.

      - Subdivisions (a) and (b) do not apply to consulting services contracts subject to Chapter 10 (commencing with Section 4525) of Division 5 of Title 1 of the Government Code.

    - CONSULTING SERVICES: If this Agreement is for consulting services, the Contractor is hereby advised of its duties, obligations and rights under PCC sections 10335 through 10381.

    - COPYRIGHTS AND TRADEMARKS: The Contractor shall assign to CalRecycle any and all rights, title and interests to any copyrightable material or trademarkable material created or developed in whole or in any Study as a result of this Agreement, including the right to register for copyright or trademark of such materials. The Contractor shall require that its Subcontractors agree that all such materials shall be the property of CalRecycle. Such title will include exclusive copyrights and trademarks in the name of CalRecycle.

For contracts of $5,000 or more, any document or written report prepared for or under the direction of CalRecycle, shall include a notation on the inside cover as follows:

“Prepared as Study of CalRecycle contract number DRR19070, Total Contract Amount $(TBD), pursuant to Government Code section 7550.”

    - DELIVERABLES: All documents and/or reports drafted for publication by or for CalRecycle in accordance with this contract shall adhere to CalRecycle’s Contractor Publications Guide at www.calrecycle.ca.gov/CONTRACTS/PubGuide/ and shall be reviewed by CalRecycle’s Contract Manager in consultation with CalRecycle editor.

    - ENTIRE AGREEMENT: This Agreement supersedes all prior Agreements, oral or written, made with respect to the subject hereof and, together with the Attachments and/or Exhibits hereto, contains the entire Agreement of the parties.

    - ENVIRONMENTAL JUSTICE: In the performance of this Agreement, the Contractor shall conduct its programs, policies, and activities that substantially affect human health or the environment in a manner that ensures the fair treatment of people of all races, cultures, and income levels, including minority populations and low income populations of the State.  (Gov. Code, § 65040.12(e)).

    - FORCE MAJEURE: Neither CalRecycle nor the Contractor, including the Contractor's Subcontractor(s), if any, will be responsible hereunder for any delay, default or nonperformance of this Agreement, to the extent that such delay, default or nonperformance is caused by an act of God, weather, accident, labor strike, fire, explosion, riot, war, rebellion, sabotage, or flood, or any other cause beyond the reasonable control of such party.

    - GRATUITIES: CalRecycle may terminate this Agreement if gratuities were offered or given by the Contractor, or any agent or representative of the Contractor, to any employee of CalRecycle, with a view toward securing a contract or securing favorable treatment with respect to awarding or amending or making a determination with respect to performance of this Agreement.

    - IMPRACTICABILITY OF PERFORMANCE: This Agreement may be suspended or cancelled, without notice at the option of the Contractor, if the Contractor’s or CalRecycle premises or equipment is destroyed by fire or other catastrophe, or so substantially damaged that it is impractical to continue service or in the event the Contractor is unable to render service as a result of any action by any governmental authority.

    - INSURANCE: When required, the Contractor shall provide: 1) a Certificate of Insurance insuring CalRecycle, and/or 2) verification of Worker’s Compensation insurance. The Contractor shall provide said Certificate of Insurance and/or verification to CalRecycle within ten (10) days after notification of CalRecycle’s intent to award the Agreement. The Agreement will not be executed nor can work begin unless said Certificate of Insurance and/or verification is provided to CalRecycle.

The Certificate of Insurance shall be in effect and shall include the following terms and conditions:

      - CalRecycle, its officers, agents, employees, and servants shall be included as additional insured.

      - The dates of inception and expiration of coverage shall be specified.

      - A minimum liability coverage of not less than $1,000,000 per occurrence for bodily injury and property damage liability combined shall be specified. The coverage shall not include a deductible feature.

      - The insurer will not cancel the insured’s coverage without thirty days prior written notice to CalRecycle.

      - CalRecycle is not liable for the payment of premiums or assessments on said policy.

      - The insurance coverage shall be on an occurrence basis only.

In the event the Certificate of Insurance should expire or be cancelled during the term of this Agreement, the Contractor agrees to provide, at least thirty days prior to said expiration or cancellation, a new Certificate of Insurance evidencing coverage, as provided for herein, for not less than one (1) year or for the remainder of the contractual Agreement, whichever is greater. In the event the Contractor fails to keep in effect at all times insurance coverage as herein provided, CalRecycle may, in addition to any other remedies it may have, terminate this Agreement upon occurrence of such event.

    - LIABILITY FOR NONCONFORMING WORK: The Contractor will be fully responsible for ensuring the completed work conforms to the agreed upon terms. If nonconformity is discovered prior to the Contractor’s deadline, the Contractor will be given a reasonable opportunity to cure the nonconformity. If the nonconformity is discovered after the deadline for the completion of the project, CalRecycle, in its sole discretion, may use any reasonable means to cure the nonconformity. The Contractor shall be responsible for reimbursing CalRecycle for any additional expenses incurred to cure such defects.

    - LICENSE OR PERMITS: The Contractor shall be an individual or firm licensed to do business in California and shall obtain at his/her expense all license(s) and permit(s) required by law for accomplishing any work required in connection with this Agreement.

In the event the Contractor fails to keep in effect at all times all required license(s) and permit(s), CalRecycle may, in addition to other remedies it may have, terminate this Agreement upon occurrence of such event.

    - ORDER OF PRECEDENCE: In the event of conflict or inconsistency between the articles, exhibits, attachments, specifications or provisions that constitute this Agreement, the following order of precedence shall apply: STD 213; GTC 04/2017 - General Terms and Conditions (incorporated by reference); Exhibit A – Scope of Work; Exhibit B – Budget Detail and Payment Provisions; Exhibit D – Special Terms and Conditions; Other exhibits in alphabetical order, beginning with E; Attachments in numerical order, beginning with 1.

    - OWNERSHIP OF DRAWINGS, PLANS AND SPECIFICATIONS: CalRecycle will have separate and independent ownership of all drawings, design plans, specifications, notebooks, tracings, photographs, negatives, reports, findings, recommendations, data and memoranda of every description or any Study thereof, prepared under this Agreement. The originals and all copies thereof will be delivered to CalRecycle upon request. CalRecycle will have the full right to use said originals and copies in any manner when and where it may determine without any claim on the Study of the Contractor, its vendors or Subcontractors to additional compensation.

    - PATENTS: The Contractor assigns to CalRecycle all rights, title, and interest in and to each invention or discovery that may be capable of being patented, that is conceived of or first actually reduced to practice in the course of or under this Agreement.

    - PUBLICITY AND ACKNOWLEDGEMENT: The Contractor agrees that it will acknowledge CalRecycle’s support whenever projects funded, in whole or in part, by this Agreement are publicized in any news media, brochures, or other type of promotional material.

    - RECYCLED-CONTENT PRODUCT PURCHASING: In the performance of this Agreement, the Contractor shall purchase used and/or recycled-content products as set forth on the back of the Recycled-Content Certification Form (Exhibit D, Attachment 1). For assistance in locating recycled-content products, please search the recycled-content product database available at: www.calrecycle.ca.gov/rcpm . If after searching the database, Contractors are unable to find the recycled-content products they are looking for, please notify CalRecycle’s Contract Manager. All recycled content products purchased or charged/billed to CalRecycle that are printed upon such as promotional items, publications, written materials, and other educational brochures shall have both the total recycled content (TRC) and the post-consumer (PC) content clearly printed on them.

In addition, any written documents such as, publications, letters, brochures, and/or reports shall be printed double-sided on 100% post-consumer (PC) paper. Specific pages containing full-color photographs or other ink-intensive graphics may be printed on photographic paper. The paper should identify the post-consumer recycled content of the paper (i.e., “printed on 100% post-consumer paper”). When applicable, the Contractor shall provide the Contract Manager with an electronic copy of the document and/or report for CalRecycle’s uses. When appropriate, only an electronic copy of the document and/or report shall be submitted and no hard copy shall be provided.

    - REMEDIES: Unless otherwise expressly provided herein, the rights and remedies hereunder are in addition to, and not in limitation of, other rights and remedies under the Agreement, at law or in equity, and exercise of one right or remedy will not be deemed a waiver of any other right or remedy.

    - SETTLEMENT OF DISPUTES: In the event of a dispute, the Contractor shall file a “Notice of Dispute” with CalRecycle’s Director or his/her designee with ten (10) days of discovery of the problem. Within ten (10) days, the Director or his/her designee shall meet with the Contractor and CalRecycle Project Manager for the purpose of solving the dispute.

    - STOP WORK NOTICE: Immediately, upon receiving a written notice to stop work, the Contractor shall cease all work under this Agreement.

    - SUBCONTRACTORS: All Subcontractors previously identified in the bid/proposal submitted are considered to be acceptable to CalRecycle. Any change or addition of Subcontractors will be subject to the prior written approval of the Contract Manager or the Director or his/her designee. Upon termination of any Subcontract, the Contractor shall notify the Contract Manager or the Executive Director immediately. If CalRecycle or the Contractor determines that the level of expertise or the services required are beyond that provided by the Contractor or its routine Subcontractors, The Contractor will be required to employ additional Subcontractors. Nothing contained in this Agreement or otherwise, shall create any contractual relation between CalRecycle and any Subcontractors, and no Subcontract shall relieve the Contractor of its responsibilities and obligations hereunder. The Contractor agrees to be as fully responsible to CalRecycle for the acts and omissions of its Subcontractors and of persons either directly or indirectly employed by any of them as it is for the acts and omissions of persons directly employed by the Contractor. The Contractor's obligation to pay its Subcontractors is an independent obligation from CalRecycle obligation to make payments to the Contractor. As a result, CalRecycle shall have no obligation to pay or to enforce the payment of any moneys to any Subcontractor.

    - SUCCESSORS: The provisions of this Agreement will be binding upon and inure to the benefit of CalRecycle, the Contractor, and their respective successors.

    - TERMINATION: CalRecycle shall have the right to terminate this Agreement at its sole discretion at any time upon thirty days written notice given to the Contractor. In the case of early termination, a final payment will be made to the Contractor upon approval by the Contract Manager of a financial report, invoices for costs incurred to date of termination and a written report describing all work performed by the Contractor to date of termination.

    - UNRELIABLE LIST: Prior to authorizing a Subcontractor(s) to commence work under this Agreement, the Contractor shall submit to CalRecycle a declaration from the Subcontractor(s), signed under penalty of perjury, stating that within the preceding three years, none of the events listed in Section 17050 of Title 14, California Code of Regulations, Natural Resources, Division 7, have occurred with respect to the Subcontractor(s).

Placement of Contractor on CalRecycle Unreliable List anytime after award of this Agreement may be grounds for termination of Agreement. If a Subcontractor is placed on CalRecycle Unreliable List after award of this Agreement, the Contractor may be required to terminate the Subcontract.

    - WASTE REDUCTION: In the performance of this Agreement, the Contractor shall take all reasonable steps to ensure that materials purchased or consumed in the course of the project are utilized both effectively and efficiently to minimize the generation of waste. The steps should include, but not necessarily be limited to, the use of reusable products, the use of recyclable and compostable products, discretion in the amount of materials used, the provision of alternatives to disposal for materials consumed, and the practice of other waste reduction measures where feasible and appropriate.

THIS PAGE INTENTIONALLY LEFT BLANK

Recycled-Content Certification

| STATE OF CALIFORNIA | To be completed by Contractor |  |
| --- | --- | --- |
| Department of Resources Recycling and Recovery (CalRecycle) | Name of Contractor: |  |
| CalRecycle 74C (Rev. 06/10 for Contracts) | Contract #: | Work Order #: |

Recycled Content Certification

Check this box if no products, materials, goods, or supplies were purchased with contract dollars and submit to the CalRecycle Contract Manager.

This form to be completed by contractor. The form must be completed and returned to CalRecycle

with a row completed for each product purchased with contract dollars. Attach additional sheets if

necessary. Information must be included, even if the product does not contain recycled-content material. Product labels, catalog/website descriptions, or bid specifications may be attached to this form as a method of providing that information.  Add additional rows as needed.

| Contractor’s Name |  |  |  |  |  |  |  |  | Date |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Address |  |  |  |  |  |  |  |  |  |  |
| Fax |  |  |  |  | Phone |  |  |  |  |  |
| E-mail |  |  |  |  |  | Website |  |  |  |  |

| Product Manufacturer | Product Description / Brand | Purchase Amount ($) | 1Percent Postconsumer Material | 2SABRC Product Category Code | Meets SABRC |
| --- | --- | --- | --- | --- | --- |

Public Contract Code sections 12205(a)(1)-(3); (b)(1)-(3).

I certify that the above information is true. I further certify that these environmental claims for recycled content regarding these products are consistent with the Federal Trade Commission’s Environmental Marketing Guidelines in accordance with PCC section 12205.

| Print name |  | Signature |  | Company |  | Date |
| --- | --- | --- | --- | --- | --- | --- |

(See footnotes on the back of this page.) 
1. Postconsumer material comes from products that were bought by consumers, used, then recycled. For example: a newspaper that has been purchased and read, next recycled, and then used to make another product would be postconsumer material.

If the product does not fit into any of the product categories, enter “N/A.”  Common N/A products include wood products, natural textiles, aggregate, concrete, electronics such as computers, TV, software on a disk or CD, telephone

2.Product category refers to one of the product categories listed below, into which the reportable purchase falls. For products made from multiple materials, choose the category that comprises most of the product by weight, or volume.

Note: For reused or refurbished products, there is no minimum content requirement.

For additional information visit www.calrecycle.ca.gov/BuyRecycled/.

| Code | Description | Minimum content requirement |
| --- | --- | --- |
|  | Product Categories (11) |  |
| 1 | Paper Products - Recycled | 30 percent postconsumer fiber, by fiber weight |
| 2 | Printing and Writing - Recycled | 30 percent postconsumer fiber, by fiber weight |
| 3 | Compost, Co-compost, and Mulch - Recycled | 80 percent recovered materials, i.e., material that would otherwise be normally disposed of in a landfill |
| 4 | Glass - Recycled | 10 percent postconsumer, by weight |
| 5 | Rerefined Lubricating Oil - Recycled | 70 percent re-refined base oil |
| 6a | Plastic - Recycled | 10 percent postconsumer, by weight |
| 6b | Printer or duplication cartridges | - Have 10 percent postconsumer material, or - Are purchased as remanufactured, or - Are backed by a vendor-offered program that will take back the printer cartridges after their useful life and ensure that the cartridges are recycled and comply with the definition of recycled as set forth in Section 12156 of the Public Contract Code. |
| 7 | Paint - Recycled | 50 percent postconsumer paint (exceptions when 50 % postconsumer content is not available or is restricted by a local air quality management district, then 10% postconsumer content may be substituted) |
| 8 | Antifreeze - Recycled | 70 percent postconsumer material |
| 9 | Retreated Tires - Recycled | Use existing casing that has undergone retreading or recapping process in accordance with Public Resource Code (commencing with section 42400). |
| 10 | Tire- Derived - Recycled | 50 percent postconsumer tires |
| 11 | Metals - Recycled | 10 percent postconsumer, by weight |

## Proposal Completion Checklist

Please use this checklist to assist in the preparation of your Proposal package to ensure that all required items are included.

|  | Cover Letter with contact information and statements as required in the RFP. |
| --- | --- |
|  | Organizational information and Personnel Information (Resumes) |
|  | Proposal (detailed Work Plan) |
|  | Samples of Written Work |
|  | Copy of Required License(s) (Secretary of State) |
|  | Cost Proposal Sheet (Attachment A) |
|  | Bidder Declaration Form shall be submitted even if participation levels are zero (write zero participation on form). (Attachment C) |
|  | Iran Contracting Act Certification (Attachment E) |
|  | Darfur Contracting Act Certification (Attachment F) |
|  | California Civil Rights Laws Certification (Attachment G) |
|  | Contractor Status Form (Attachment H) |
|  | Client References (Attachment I) |

The following number of PROPOSAL packages shall be submitted as the Contractor’s response to this RFP:

|  | One (1) unbound reproducible original Proposal package marked “Original” AND One (1) original, signed bid sheet in a separate sealed envelope marked “Cost Proposal-Do Not Open”. |
| --- | --- |
|  | Three (3) bound copies of the Proposal package marked “Copy”. Do not include the bid sheet in these copies. |
|  | One (1) Electronic copy of Proposal Package in Adobe Acrobat format with all documents in a single file, including the bid sheet and all other attachments. |  |

The following form is only required upon submittal as applicable pursuant to the provisions outlined in Section III, Submittal Requirements:

|  | Certification of Target Area Contract Preference Act |
| --- | --- |

The following forms are not required at the time of the Proposal submission but will be required by the successful Contractor during the contract period:

|  | Recycled Content Certification (end of Attachment J) |
| --- | --- |
|  | Small Business (SB) and Disabled Veteran Business Enterprise (DVBE) Subcontractor Payment Certification (Attachment D) |  |
|  | Payee Data Record (Standard Form 204) |  |

Please note that if any of the items are missing from the Proposal package, the package will be considered incomplete and will be disqualified from the process.