Department of Resources Recycling and Recovery

Notice to Prospective Proposers

March 6, 2020

You are invited to review and respond to this Request for Proposal (RFP) Secondary, entitled “2020 Statewide Disposal-based Waste Characterization Study, DRR19079”.  In submitting your Proposal, you must comply with the instructions herein.

Note that all Contracts entered into with the State of California will incorporate by reference General Terms and Conditions, Special Terms and Conditions and Contractor Certification Clauses which are referenced in this package.  If you do not have internet access, a hard copy can be provided by contacting the person listed below.

In the opinion of the Department of Resources Recycling and Recovery (CalRecycle) this RFP is complete and without need of explanation.  However, if you have questions, or should you need any clarifying information, the contact person for this RFP is:

Melissa Mojonnier

contracts@calrecycle.ca.gov

Phone: (916) 341-6048

Fax: (916) 319-7345

Please note that no verbal information given will be binding upon the State unless such information is issued in writing as an official addendum.

Melissa Mojonnier

Contract Administrator

Table of Contents

Section 1	Overview	1

General Information	1

CalRecycle Contact Information	1

Service Needed	1

Contract Budget	1

Payment Withhold	2

Contract Term	2

Process Type	2

Process Schedule	2

Section II	Rules and Conditions	3

Introduction	3

Commitment	3

Antitrust Claims	3

Contractor’s Cost	4

Information	4

Written Questions	4

Addenda	4

Modification of Submittals	5

Errors in Submittals	5

Unreliable List	5

Electronic Waste Recycling	5

Use Tax	5

Subcontractors	5

Payments to the Contractor	6

Equipment and Software Purchases	6

Section III	Proposal Submittal Requirements	7

Introduction	7

Deadline	7

Addressing	7

Number of Copies	7

Document Printing	7

Cover Letter	7

Table of Contents	8

Summary	8

Methodology	8

Organization	8

Qualifications and Resources	9

References	9

Samples of Written Work	9

Contractor Eligibility	10

Qualification/Licenses	10

Small Business (SB) Participation	10

Disabled Veteran Business Enterprise (DVBE) Participation	10

Disabled Veteran Business Enterprise (DVBE) Incentive Application	10

Target Area Contract Preference Act (TACPA)	12

Maximum Combined Preferences and Rules for Award	12

Section IV	Cost Proposal Submittal	13

Evaluation	13

Cost Breakdown	13

Travel and Per Diem	13

Section V	Evaluation and Selection	16

Introduction	16

Selection Process	16

Cost Points	18

Grounds for Rejection	18

Award of Contract	18

Notice of Intent to Award	19

Rejection of Award	19

Protest of Award	19

Section VI	Description of Work	21

Work to be Performed	21

Tasks Identified	21

Contract/Task Time Frame	38

Location of Services	39

Control of Work	39

Appendix	40

Section VII 	Definition and Terms	65

Attachments	67

Cost Proposal Sheet	68

RFP (S) Proposal Scoring Sheet	70

Bidder Declaration	74

Small Business (SB) and Disabled Veteran Business Enterprise (DVBE) Subcontractor Payment Certification	76

Iran Contracting Act	78

Darfur Contracting Act	79

California Civil Rights Laws Certification	80

Contractor Status Form	81

Client References	82

Sample Agreement	83

Proposal Completion Checklist	137

# Section 1	Overview

## General Information

CalRecycle promotes a zero waste California in partnership with local government, industry, and the public. This means managing the estimated 76 million tons of waste generated each year by reducing waste whenever possible, promoting the management of all materials to their highest and best use, and protecting public health and safety and the environment.

## CalRecycle Contact Information

Department of Resources Recycling and Recovery

Physical Address: 	1001 I Street

Sacramento, CA 95814

CalRecycle Contracts Unit, MS-19A

Mailing Address:   	P.O. Box 4025

Sacramento, CA 95812-4025

Attn: Contracts Unit, MS-19A

Phone:     (916) 341-6048

Fax:       (916) 319-7345

Email:  contracts@calrecycle.ca.gov

Any documents delivered in person must be received by 2:00 p.m. on April 16, 2020 in the Visitor’s & Environmental Service Center located in the lobby of the CalEPA Headquarters Building at 1001 I Street, Sacramento, CA 95814.

## Service Needed

The Contractor shall conduct waste characterization research, consisting of three parts to be conducted concurrently.  They are:

- Part 1. A Disposal Facility-Based Waste Characterization Study to determine the statewide waste disposal composition;

- Part 2. A Multi-Family Generator-Based Waste Characterization Study to determine the disposed waste composition and disposal rate for multi-family residences; and

- Part 3. A Moisture Analysis Study to analyze moisture absorbed by specific paper types collected for Part 1 of the study.

## Contract Budget

This Contract is valid and enforceable only if sufficient funds are made available by the Budget Act of the appropriate fiscal year for the purposes of this program.  In addition, this Contract is subject to any additional restriction, limitations or conditions enacted by the Legislature, which may affect the provisions, terms, or funding of this Contract in any manner.

Subject to availability of funds and approval by CalRecycle, there is a current maximum budget of $685,000 (six hundred eighty-five thousand dollars).  CalRecycle reserves the right to amend the budget for this Contract as needs arise.

## Payment Withhold

The provisions for payment under this contract shall be subject to a ten percent (10%) withholding per task. The withheld payment amount will be included in the final payment to the Contractor and will only be released when all required work has been completed to the satisfaction of CalRecycle.

## Contract Term

The term of this Agreement will span approximately 15 months and is expected to begin in June 2020.  CalRecycle reserves the right to amend the term of this Contract as needs arise.

## Process Type

Request for Proposal (RFP) (Secondary Method).

## Process Schedule

This process will be conducted according to the following tentative schedule where all times are Pacific Standard Time.

| Advertisement Date | March 6, 2020 |
| --- | --- |
| Written Questions Due by 5:00 pm | March 26, 2020 |
| Submittals Due by 2:00 pm | April 16, 2020 |
| Post Notice of Intent to Award | May 1, 2020 |

# Section II	Rules and Conditions

## Introduction

There are conditions that this RFP, submitting Proposers, Proposals and resulting Contracts are subject to and/or with which they are required to comply.

## Commitment

Upon submittal of a Proposal, the Contractor has committed to comply with the following requirements:

- All items noted in RFP documents

- Special Terms and Conditions, which are included in the attached sample Standard Agreement.

- General Terms and Conditions (GTCs) and Contractor Certification Clauses (CCCs) are both available for viewing at https://www.dgs.ca.gov/OLS/Resources/Page-Content/Office-of-Legal-Services-Resources-List-Folder/Standard-Contract-Language

The above terms, conditions, and requirements are not subject to negotiation.  Any Proposal that reserves a right to negotiate or expresses any exception to the above terms, conditions, and requirements will be disqualified.  However, requests to revise any of the above terms, conditions, and requirements may be submitted during the formal question and answer period.  Any such requests must include the current language, the proposed revised language, and the justification for the proposed revision.  Any revisions are at the sole discretion of CalRecycle and will only be made under very limited circumstances in which the revisions apply to all Proposers and benefit or enhance the Contract.

If the Proposer fails to meet any of the requirements or comply with CalRecycle requests, CalRecycle can reject, disqualify, or remove the firm from the process. CalRecycle is not committed to awarding a Contract resulting from this RFP.

## Antitrust Claims

In submitting a Proposal Package to a public purchasing body, the Proposer offers and agrees that if the Proposal Package is accepted, it will assign to the purchasing body all rights, title, and interest in and to all causes of action it may have under Section 4 of the Clayton Act (15 U.S.C. Sec. 15) or under the Cartwright Act (Chapter 2 [commencing with Section 16700] of Part 2 of Division 7 of the Business and Professions Code), arising from purchases of goods, materials, or services by the Proposer for sale to the purchasing body pursuant to the Proposal Package.  Such assignment shall be made and become effective at the time the purchasing body tenders final payment to the Proposer.  (See Government Code Section 4552.)

If an awarding body or public purchasing body receives, either through judgment or settlement, a monetary recovery for a cause of action assigned under this chapter, the assignor shall be entitled to receive reimbursement for actual legal costs incurred and may, upon demand, recover from the public body any portion of the recovery, including treble damages, attributable to overcharges that were paid by the assignor but were not paid by the public body as part of the Proposal Package price, less the expenses incurred in obtaining that portion of the recovery.  (See Government Code section 4553.)

Upon demand in writing by the assignor, the assignee shall, within one year from such demand, reassign the cause of action assigned under this part if the assignor has been or may have been injured by the violation of law for which the cause of action arose and (a) the assignee has not been injured thereby, or (b) the assignee declines to file a court action for the cause of action.  (See Government Code section 4554.)

## Contractor’s Cost

All costs resulting from the Contractor’s participation in the RFP process are at the firm’s expense. No costs incurred by the Contractor participating in the RFP process will be reimbursed by CalRecycle.

## Information

All materials submitted in response to this RFP will become the property of CalRecycle and, as such, are subject to the Public Records Act (Government Code Sections 6250 et seq.).  CalRecycle will disregard any language purporting to render all or portions of the RFP package confidential.

All information obtained or produced during the course of the Agreement will be made available to CalRecycle.

Any information obtained or produced during the course of the Agreement that qualifies as confidential or a trade secret(s) under the Public Records Act (PRA) or the Public Contract Code (PCC) and is thus exempt from disclosure under those statutes shall be so marked by the firm prior to submission to CalRecycle.  Any claims of confidentiality or trade secret(s) except as to information that qualifies as such under the PRA or PCC may result in disqualification.

CalRecycle will hold information obtained or produced during the course of the Agreement deemed confidential or trade secret(s) by the firm to the extent allowable by the California PRA and the PCC.

## Written Questions

The RFP includes a formal question and answer period in which Proposers have the opportunity to submit questions regarding the RFP.  All questions must be submitted in writing either by mail, fax, or e-mail to the CalRecycle Contact as listed in Section I, Overview.  The questions and answers will be published in an Addendum to the RFP (see below, Addenda).

## Addenda

CalRecycle reserves the right to amend, alter, or change the rules and conditions of this RFP.

Any ambiguity, conflict, discrepancy, omission, or other error discovered in the RFP should immediately be reported to CalRecycle prior to the deadline for submission of written questions.  CalRecycle will issue addenda to address such issues.

## Modification of Submittals

A Proposal submitted prior to the submittal deadline can be withdrawn or modified by the submitting Proposer.  The Proposer must:

- Provide a written request

- Identify the requesting individual and their association to the Proposer

A Proposal cannot be withdrawn for modification after the submittal deadline has passed.

## Errors in Submittals

An error in a Proposal package may be cause for rejection of that Proposal.

CalRecycle may make certain corrections, if the Proposer’s intent is clearly established based on review of the complete Proposal.

## Unreliable List

Any Contractor or subcontractor currently on CalRecycle’s Unreliable List is ineligible to apply for or participate in this contract.

## Electronic Waste Recycling

If the Contractor or any subcontractors participate in activities that result in the disposition of electronic components, they will comply with the provisions of PRC Chapter 8.5.

## Use Tax

If, during the course of the Contract, the Contractor will be involved in the re-sale of goods to the State, they must comply with the requirements of Sections 6452.1, 6487, 6487.3, 7101, and 18510 of the Revenue and Taxation Code, in addition to Section 10295.1 of the Public Contract Code.

## Subcontractors

All Subcontractors identified in the Proposal, must be experts in their respective disciplines and capable of performing the tasks for which they are hired.

The Department of General Services (DGS), Office of Small Business and Disabled Veteran Business Enterprise Services (OSDS) oversees the Small Business (SB) and Disabled Veteran Business Enterprise (DVBE) certification programs. If awarded the Contract, the Contractor must use all of the SB and DVBE firms identified on the Bidder Declaration form.

Contractor understands and agrees that should award of this contract be based in part on their commitment to use the DVBE subcontractor(s) identified in their Proposal, per Military and Veterans Code 999.5(e), a DVBE subcontractor may only be replaced by another DVBE subcontractor and must be approved by the DGS. Changes to the scope of work that impact the DVBE subcontractor(s) identified in the Proposal and approved DVBE substitutions will be documented by contract amendment.

Failure of Contractor to seek substitution and adhere to the DVBE participation level identified in the Proposal may be cause for contract termination, recovery of damages under rights and remedies due to the State, and penalties as outlined in M&VC § 999.9; Public Contract Code (PCC) section 10115.10, or PCC section 4110 (applies to public works only).

CalRecycle reserves the right to approve substitutions of subcontractors, as long as, certified business participation levels remain unchanged.

## Payments to the Contractor

Payments to the Contractor by CalRecycle will be made in arrears.  Services rendered by the Contractors must be identified on an invoice, to be billed monthly in arrears.

## Equipment and Software Purchases

Although equipment or software purchases are not anticipated in this contract, any equipment or software purchased to perform the responsibilities under the contract are considered state property and shall be returned to CalRecycle at the end of the contract or upon request of the CalRecycle Contract Manager (Contract Manager).

# Section III	Proposal Submittal Requirements

## Introduction

Failure to follow the instructions contained in this document may be grounds for rejection of a Proposal.

CalRecycle may reject any Proposal if it is conditional, incomplete or contains irregularities.

CalRecycle may waive an immaterial deviation in a Proposal, if deemed in the best interest of CalRecycle.

## Deadline

The proposal package must be received by CalRecycle, at the address listed in Section I, Overview by 2:00 p.m. on April 16, 2020.

Proposals received after the deadline will be considered late and returned to the Proposer unopened.

## Addressing

The Proposal package must clearly state that it is in response to this RFP and note the RFP number listed with the direction of “Mailroom – do not open.”

## Number of Copies

The Proposer is required to submit all required documents in the following format:

- One original, non-bound hard copy marked “Original”

- Three (3) bound, hard copies marked “Copy”

- One electronic copy on USB flash drive viewable by Adobe Acrobat Reader.  The entire Proposal, including any attachments, must be saved as a single document.

It is the submitting Proposer’s responsibility to ensure that the electronic copy is formatted in Adobe Acrobat Reader and viewable by CalRecycle.

## Document Printing

All documents must be submitted double-sided on paper with a minimum of 100% post-consumer recycled content fiber.

## Cover Letter

The cover letter shall be signed by an individual who is authorized to bind the Proposer and shall indicate that person's title or position.  The cover letter must be on the Proposer's company letterhead and contain the following information:

- Name and address of the Proposer submitting qualifications;

- Proposer’s Headquarters for purposes of this Contract, if awarded;

- Name, telephone number, and e-mail address of a person who can be contacted if further information is required;

- Name, title, address, telephone number, and e-mail address of individual(s) with authority to negotiate and execute a binding Contract on behalf of the Proposer;

- Statement that personnel who will provide services under the Contract will have the required certifications and that the Proposer will have qualified personnel available to meet the service needs;

- Statement attesting to the fact of the percentage of post-consumer recycled content fiber paper used in the compilation of the Proposal package.

- Statement stating that the Contractor and any Subcontractors to be used during the performance of the contract are eligible to contract with the State of California, pursuant to PCC 10286; and

- List of Contractor’s and any subcontractor(s’) business names, identification of certified Small Business (SB) or Disabled Veteran Business Enterprise (DVBE) status, if applicable, and corresponding Office of Small Business and Disabled Veteran Business Enterprise Services (OSDS) Reference number(s) issued by DGS.

## Table of Contents

The information must be organized as presented with corresponding page references.

## Summary

The Proposer shall include a brief overview of the project and summarize the Proposer’s approach to the work.

## Methodology

The Proposal should include a Work Plan describing the methods to be employed to accomplish the contract activities described in Section VI Description of Work.

The methodology must be described in sufficient detail to allow CalRecycle staff to evaluate the methods and must address all tasks and items in the Scope of Work.  The description should include not only what work will be performed, but how it will be performed.

The tasks described in the Scope of Work outline a general approach for meeting the requirements; detailed approaches for the tasks must be proposed that meet or exceed the requirements in meeting the project objectives.

Proposals must describe in detail how project objectives will be met and the methods the Contractor will use to achieve project objectives outlined in the Scope of Work.

## Organization

Provide a brief description of the organization’s services and activities, including:

- Date of establishment

- History

- Location

- Any known conflicts of interest

## Qualifications and Resources

The prospective contractor must have the experience, qualifications, and resources to perform the required tasks of the project. Because of the comprehensive nature and complexity of this study, Proposers shall demonstrate their experience in the following areas:

- Conducting large-scale (regional or statewide) waste characterization studies including the development of a statistically representative sampling plan and a plan for collecting samples from facilities with various delivery mechanisms (transfer trucks, route trucks, self-haul vehicles, etc.);

- The collection of detailed field sorting data;

- Working with disposal facilities including coordinating field work and following health and safety plans; and

- Ensuring data integrity through appropriate quality assurance and quality control (QA/QC) processes and data entry procedures.

Each Proposal must include a description of the resources to be used on the project while demonstrating an individual or team members’ abilities to perform the work. The Proposals must include resumes for the Project Manager, Personnel and Subcontractors, that include:

  - Experience

  - Knowledge

  - Educational Background

  - Professional Licenses where required by law or industry standards

## References

The Proposer’s team must provide a minimum of three (3) verifiable references, for the Proposer and for each proposed Subcontractor, which supports the above qualifications.

If a reference or project experience is unable to be verified, it will be disregarded.

## Samples of Written Work

The Proposer’s team shall include a copy of a verifiable written work that is similar in nature to the proposed project and deliverables.

At least one example should demonstrate each of the following:

- Knowledge of and understanding of California’s solid waste management system in various parts of the state;

- Experience in implementing a large-scale facility-based waste disposal characterization study including initial project set-up, site coordination, fieldwork, identifying when contingency plans have been implemented and steps taken, data preparation, and project deliverables;

- Knowledge of and understanding of conducting analysis of waste materials;

- Experience in implementing and adjusting a pre-determined work plan for characterization of waste materials including steps taken for analysis.

## Contractor Eligibility

The Proposer must include a written declaration stating that the Contractor and any Subcontractors to be used during the performance of the contract are eligible to contract with the State of California, pursuant to PCC section 10286.1.  Statement may be included in the cover letter.

## Qualification/Licenses

The Contractor shall be an individual or firm qualified to do business in California.  Required documentation includes the following as applicable:

- A copy of the Proposer’s registration with the Secretary of State.

- Additionally, pursuant to the California Business and Professions Code, for services of a “professional” nature requiring a professional license issued by the CA Department of Consumer Affairs, Proposers must submit a copy of the appropriate license(s) for each team member who will provide “professional” services under the contract.

## Small Business (SB) Participation

CalRecycle requires a minimum of twenty-five percent (25%) of the project services to be contracted to a California OSDS certified SB that performs a commercially useful function.

This goal can be achieved by a combined effort of the prime and/or any Subcontractors, which includes:

- If the Proposer is a certified OSDS SB, as defined in Section V Definitions and Terms, the Bidder Declaration form (Attachment C) shall be completed and submitted with the Proposal.

- If the Proposer has identified Subcontractors to be utilized to meet this goal, the Bidder Declaration form (Attachment C) shall be completed and submitted with the Proposal.

SB and non-SB may receive preference as set forth below.

For purposes of this RFP, references to “Small Business” or “SB” include “Microbusiness” unless contrary to law.

## Disabled Veteran Business Enterprise (DVBE) Participation

The DVBE participation requirement is being waived for this solicitation, however the DVBE incentive is available to those bidders meeting participation goals.

## Disabled Veteran Business Enterprise (DVBE) Incentive Application

Any Proposer competing in this process as a California certified DVBE, or as a non-DVBE certifying to subcontract a minimum of 3% of the total contract services to a California certified DVBE, will receive an incentive.  The incentive amounts for DVBE participation percent are as shown below:

- Five percent (5%) or more participation will receive five percent (5%) incentive calculation.

- Four percent (4%) participation will receive two percent (2%) incentive calculation.

- Three percent (3%) participation will receive one percent (1%) incentive calculation.

Certification must be provided by DGS, OSDS. The incentive is available to a non-DVBE claiming a minimum of three percent (3%) California certified DVBE subcontractor participation. If claiming the non-DVBE subcontractor incentive, the bid response must include a list of the DVBE(s) with which you commit to subcontract in an amount of at least three percent (3%) of the net bid price with one of more California certified DVBEs. Each listed certified DVBE must perform a "commercially useful function" in the performance of the contract as defined in Government Code section 14837(d)(4).

The required list of California certified DVBE subcontracts must be attached to the bid response and must include the following: (1) subcontractor name, (2) address, (3) phone number, (4) a description of the work to be performed and/or products supplied, and (5) the dollar amount or percentage of the net bid price (as specified in the solicitation) per subcontractor.  Use the Bidder Declaration form to report this information.

Questions regarding certification should be directed to OSDC at (916) 375-4940.

CalRecycle will apply the incentive as follows:

The incentive is applied during the evaluation process and is only applied for responsive bids from responsible bidders proposing the percentage(s) of DVBE participation for the incentive(s) specified above.

For award based on high score, the incentive is applied by calculating the "earned" score for all bidders.  If the highest scored Proposal is from a non-certified DVBE then:

      - Calculate five percent (5%) of the highest responsible Proposer's total score.

      - Add the amount calculated above to the score of each of the Proposals eligible for the DVBE incentive according to the participation levels to obtain the new total scores for the eligible Proposals.

Application of the incentive shall not displace an award to a DVBE with a non-DVBE.

A copy of the Proposer’s DVBE certification should be included with the Proposal Package.

If awarded, the Proposer who has made a commitment to achieve disabled veteran business enterprise (DVBE) participation, must within 60 days of receiving final payment under this Agreement (or within such other time period as may be specified elsewhere in this Agreement) certify in a report to the awarding department: (1) the total amount the prime Contractor received under the contract; (2) the name and address of the DVBE(s) that participated in the performance of the contract; (3) the amount each DVBE received from the prime Contractor; (4) that all payments under the contract have been made to the DVBE(s); and (5) the actual percentage of DVBE participation that was achieved. A person or entity that knowingly provides false information shall be subject to a civil penalty for each violation (Military & Veterans Code (M&VC) § 999.5(d)).  Refer to the Small Business and Disabled Veteran Business Enterprise Subcontractor Payment Certification form (Attachment H) to fulfill this requirement.

## Target Area Contract Preference Act (TACPA)

If the budget for services outlined in this announcement, exceeds $100,000, CalRecycle will grant a preference for TACPA qualified Proposers.

The Proposer must provide reasonable demonstration of contract labor hours and certify that they will comply with the requirements of the TACPA.

If the Proposer is qualified for this preference, the TACPA Preference Request Form must be included in the Proposal submittal.

The form may be downloaded at https://www.calrecycle.ca.gov/contracts/forms.

## Maximum Combined Preferences and Rules for Award

In combination with any other preferences (TACPA, SB or DVBE participation, etc), the maximum limit of the combined preferences is 15% of the bid amount and, in no case, more than $100,000.00 per solicitation.

Preference programs for TACPA or the non-SB subcontracting preference cannot displace a direct award to a certified SB. In the event of a tie between a SB and a firm that is SB and DVBE, the award shall be made to the firm that is SB and DVBE.

# Section IV	Cost Proposal Submittal

## Evaluation

The Contractors Cost Proposal submittal will be evaluated based on whether the cost breakdown is sufficiently detailed to determine if the proposed expenses are reasonable.

## Cost Breakdown

Attachment A, Cost Proposal Sheet, must be completed, specifying the total cost and including detailed project costs and subcontractor commitments, identified by each task and dollar amount. The awarded Proposer’s invoices must be itemized as shown in the submitted Cost Proposal Sheet.

All travel must be itemized in the Attachment A, under Column 6.  Travel expenses and per diem cannot exceed the rates established by CalHR. For further travel information read the following section, Travel and Per Diem.

The costs identified in the Attachment A, should take into consideration the length of the contract, rise in salaries and overhead costs.

If fringe benefits and/or overhead are not specifically itemized in Attachment A and if the Proposer inserts a $0, the Proposer must explain on Attachment A why these line items are not itemized.  A blank space for either fringe benefits or overhead will be grounds for immediate disqualification.

Failure to include on the Cost Proposal Sheet budgeted costs for all tasks included in the Scope of Work will be grounds for disqualification.

The Cost Proposal Sheet is a self-contained document for the purpose of calculating cost points and evaluating whether all information required by the RFP has been submitted. Therefore, all information (such as explanations of $0 instead of itemized costs) must be included.  Reference by incorporation to the Proposal is not acceptable.

The amount identified in Attachment A may not be changed and will remain in effect for the life of the Contract.

## Travel and Per Diem

All travel must be pre-approved by the Contract Manager.  When determining the least costly travel method, the Contractor should take into consideration not only direct expenses, but also the time billed.  If the Contractor is unsure what least costly method may be, he or she shall consult with the Contract Manager.  All travel will be reimbursed at the excluded employee travel rates in accordance with the California Code of Regulations Title 2, Division 1, Chapter 3, Subchapter 1, Article 2, Section 599.615.1 et seq.  At the time of the RFP release, the rates listed below apply.  However, they are subject to change and the Contractor will be held to the State per diem rates in effect at the time of travel.  Per diem (lodging, meals and incidentals) will not be reimbursed for travel within 50 miles of Contractor’s headquarters.

- Lodging (receipts required) per day:

All counties/cities located in California (except as noted below):

Actual lodging expense, supported by a receipt, up to $90 per night, plus tax and mandatory fees.

Napa, Riverside, and Sacramento Counties:

Actual lodging expense, supported by a receipt, up to $95 per night, plus tax and mandatory fees.

Marin:

Actual lodging expense, supported by a receipt, up to $110 per night, plus tax and mandatory fees.

Los Angeles, Orange, and Ventura Counties and Edwards AFB, excluding the City of Santa Monica:

Actual lodging expense, supported by a receipt, up to $120 per night, plus tax and mandatory fees.

Monterey, San Diego Counties:

Actual lodging expense, supported by a receipt, up to $125 per night, plus tax and mandatory fees.

Alameda, San Mateo, and Santa Clara Counties:

Actual lodging expense, supported by a receipt, up to $140 per night, plus tax and mandatory fees.

City of Santa Monica:

Actual lodging expense, supported by a receipt, up to $150 per night, plus tax and mandatory fees.

San Francisco:

Actual lodging expense, supported by a receipt, up to $250 per night, plus tax and mandatory fees.

- Meals (actual expense) (up to $7 for breakfast, $11 for lunch and $23 for dinner) – up to a maximum of $41 per day

- Incidentals – up to a maximum of $5 per day.

- Coach airfare, mid-size/economy rental cars, parking and fuel – actual costs verified by bills or receipts.  Expenses for rental car insurance, fuel for rental cars purchased from the rental car company, and additional air travel expenses such as preferred boarding, will not be reimbursed.  First Class or Business Class air travel is not allowed.  Airport parking must be at the most economical rate.  Expenses for one way rental car expense (i.e. charges for returning a rental car to a location other than that from which it was rented) will only be reimbursed if preapproval is given by the Contract Manager prior to the expense being incurred.

- Personal Vehicle Use for travel is reimbursed at $0.575 per mile; however fuel will not be reimbursed if a personal vehicle is used.

# Section V	Evaluation and Selection

## Introduction

CalRecycle will perform a Pre-Qualification Evaluation process to ensure that the Proposer has included all required documentation in the Proposal submittal.  Each Proposal will first be reviewed to ensure the following items: Proposal is received by date and time specified; Proposal contains all the required documents (see Proposal Completion Checklist); and that the Proposal meets the format requirements specified.

If a Proposal package does not meet all of the requirements set forth in this RFP, it will be considered non-responsive and rejected from further competition.

Those Proposer’s submittals that pass this review will be forwarded to the evaluation team.

## Selection Process

The evaluation team will individually and/or as a team review, evaluate and numerically score all Proposals passing the Pre-Qualification Evaluation, utilizing the following scoring system to assign points.  Following this chart is a list of the considerations that the evaluation team may take into account when assigning individual points to a technical Proposal.

| Points | Interpretation | General Basis for Point Assignment |
| --- | --- | --- |
| 0 | Inadequate | Proposal response (i.e., content and/or explanation offered) is inadequate or does not meet CalRecycle’s needs/requirements or expectations. The omission(s), flaw(s), or defect(s) are significant and unacceptable. |
| 1 | Barely Adequate | Proposal response (i.e., content and/or explanation offered) is barely adequate or barely meets CalRecycle’s needs/requirements or expectations. The omission(s), flaw(s), or defect(s) are inconsequential and acceptable. |
| 2 | Fully Adequate | Proposal response (i.e. content and/or explanation offered) is fully adequate or fully meets CalRecycle’s needs/ requirements or expectations. The omission(s), flaw(s), or defect(s), are inconsequential and acceptable. |
| 3 | Excellent or Outstanding | Proposal response (i.e. content and/or explanation offered) is above average or exceeds CalRecycle’s needs/requirements or expectations. Minimal weaknesses are acceptable. Proposer offers one or more enhancing feature, method or approach that will enable performance to exceed our basic expectations. |

In assigning points for individual rating factors, the evaluation team may consider issues including, but not limited to, the extent to which a Proposal response:

- Is lacking information, lacking depth or breadth or lacking significant facts and /or details, and or;

- Is fully developed, comprehensive and has few, if any, weaknesses, defects or deficiencies, and or;

- Demonstrates that the Proposer understands CalRecycle’s needs, the services sought, and/or the Contractor’s responsibilities, and/or;

- Illustrates the Proposer’s capability to perform all services and meet all scope of work requirements, and/or;

- If implemented, will contribute to the achievement of CalRecycle’s goals and objectives, and/or;

- Demonstrates the Proposer’s capacity and/or commitment to exceed regular services.

Responses which only restate or paraphrase information found in the RFP will receive 0 or 1 points.

Below are the point values for each rating category that will be scored.

- Each subcategory of a proposal, excluding the Cost section, will be scored on a scale of 0 to 3.  The overall rating categories and their point values are shown below.  Some subcategories are weighted, and the scores for those subcategories will be multiplied by a weighting factor shown in Attachment B.  For individual subcategory descriptions refer to Attachment B.

| Rating Category | Maximum Points |
| --- | --- |
| Experience | 36 |
| Methodology | 114 |
| Rating Total | 150 |
| Cost Points | 66 |
| Maximum Total | 216 |

- CalRecycle will consider a proposal technically deficient and non-responsive if the proposal earns a score that is less than 25 points in the Experience Category or less than 80 points in the Methodology Category.

The Proposal Evaluation criteria listed specifies the total number of points available for each requirement.  Using the Scoring Methodology, the evaluation team will determine the number of points to be awarded to each requirement, and multiply that by the multiplier for that requirement to determine the score.

Only those Proposals that receive a score of at least the minimum requirement identified on the Scoring Sheet will be ranked.

## Cost Points

Cost points account for approximately 30% of the total points available (see Proposal Scoring Sheet).  Proposers will be awarded Cost Points as follows:

1) Lowest cost Proposal is awarded the maximum cost points.

2) Other Proposals are awarded cost points based on the following calculation:

Other Proposer’s Cost Points = (factor*) X maximum cost points

* factor is the Lowest Proposer’s cost divided by Other Proposer’s cost

EXAMPLE

Lowest Proposer’s cost = $10

Other Proposer’s cost = $12

Maximum cost points = 30 cost points

factor = $10 ÷ $12 = .83

Cost Points Calculation for Other Proposer’s Cost

.83  X  30 cost points = 25 cost points

Final Cost Points Awarded

Lowest cost Proposal receives 30 cost points

Other cost Proposal receives 25 cost points

## Grounds for Rejection

All Proposals may be rejected whenever the determination is made that the Proposals received are not really competitive, when the cost is not reasonable, or when the cost exceeds the amount expected.

Additionally, a Proposal may be rejected if any of the following apply:

- It is received after the due date and time for submittal

- The cost submittal is unsigned

- The proposal cost is not prepared as required by the RFP

- The Proposer has been prohibited from contracting with the State by the Department of Fair Employment and Housing

- The Proposer has received a substantive negative contract performance report from the State

- Any items required by the RFP are not included with the submittal

No Proposal may be rejected arbitrarily or without reasonable cause.

## Award of Contract

Award of this Contract will be to the highest ranking responsible Proposer meeting all of the RFP requirements.

In the event of a tie, CalRecycle may utilize a tiebreaker to determine the winning Proposer.  The tiebreaker will be determined based on which Proposer has the most SB and DVBE participation identified in the Proposal package.

CalRecycle reserves the right not to award a Contract.

## Notice of Intent to Award

CalRecycle will post a notice of intent to award this Contract five (5) working days prior to the award being made.

Notice of the intent to award will be posted on CalRecycle’s website at https://www.calrecycle.ca.gov/contracts/forms and at the headquarters building noted in Section I.  It is the Proposer’s responsibility to check one of these locations for a copy of the Notice of Intent to Award.

## Rejection of Award

If the Proposer fails to enter into a satisfactory Contract within a reasonable timeframe after the award is made CalRecycle may deem that the Proposer has rejected the award.

CalRecycle reserves the right to disqualify the awardee and award the Contract to the next highest ranked Proposer.

## Protest of Award

A Proposer may protest the proposed award by filing an official protest with the Department of General Services.  The protest must be filed after the notice of intent to award the contract, but before the actual award.

Within five (5) working days of the initial protest filing, the Proposer must submit a detailed written statement with information that supports that the Proposer would have been awarded the contract and the grounds for that position.

The Contract will not be awarded until a decision has been made on the filed protest.

The protest documents should be sent via registered mail to the following parties:

Department of General Services

Office of Legal Services

Attn: Protest Coordinator

707 Third Street, Suite 7-330

Sacramento, CA  95605

Fax (916) 376-5088

CalRecycle

Attn: Contracts Unit

1001 I Street, MS-19A

Sacramento, CA  95814

Fax (916) 319-7545

Email contracts@CalRecycle.ca.gov

# Section VI	Description of Work

## Work to be Performed

The Contractor shall conduct waste characterization research, consisting of the following three parts to be conducted concurrently:

- Part 1. A Disposal Facility-Based Waste Characterization Study to determine the statewide waste disposal composition.  The Contractor shall propose and justify the quantity of samples to be taken to accurately represent California’s complex waste stream.

- Part 2. A Multi-Family Generator-Based Waste Characterization Study to determine the disposed waste composition and disposal rate for multi-family residences; and

- Part 3. A Moisture Analysis Study to analyze moisture absorbed by specific paper types collected for Part 1 of the study. The Contractor shall propose the methodology and quantity of samples and justify how the quantity of samples will be sufficient to meet the goals of the study, while remaining within the specified budget of $37,000 for Part 3..

## Tasks Identified

Task 1 – Initial Meeting to refine the Proposed Study Design (Work Plan)

- Within 10 calendar days of contract approval, the Contractor shall meet in-person with CalRecycle’s Contract Manager (Contract Manager) at the CalRecycle office in Sacramento to identify logistical details and fine-tune the proposed methodologies, including:

  - The timeline and logistics for sampling collection and analysis.

  - The potential sampling sites (based on recruitment success) and sample distributions per site. The Contract Manager will provide an updated list of sampling sites and re-distribute the quantity of samples at each site if necessary.

- For PART 3-the Moisture Analysis Study, this includes the proposed method.

  - The specific materials to be used to characterize the waste samples.

- For PART 3-the Moisture Analysis Study, this refers to the specific material list to be included in this part of the study.

- Within 15 calendar days of the initial meeting with the Contract Manager, the Contractor shall submit any proposed revisions to the plan resulting from the initial meeting.

- The Contract Manager will respond in writing within 15 calendar days with any final edits to the plan.

- The Contractor shall make required changes, if any, and submit them to the Contract Manager within 15 calendar days of receiving the edits.

- The Contract Manager will provide the Contractor with final written approval confirming that all required revisions have been completed and are satisfactory to the Contract Manager.

- No work shall begin on Tasks 2 or 3 without the Contract Manager’s written approval.

Task 2 – Coordinate with Facilities and Determine Field Schedule

- The Contractor shall promptly establish contact with the Contract Manager and confirm logistics (e.g., sample collection date(s), and health and safety requirements). For PART 1- Disposal Facility-Based Waste Characterization Study, the Contractor shall also confirm the availability of a loader/skid steer loader and an equipment operator/driver).

- The Contractor shall coordinate with the Contract Manager to minimize impacts to the field schedule and request replacement sampling sites if needed.

- The Contractor shall, when scheduling sampling activities at each site, ensure accurate and representative sampling by including on the sample collection data form information on variations in site operations, waste flows, on-site processing/handling and other relevant information as determined by the Contractor.  For PART 2- Multi-Family Generator-Based Waste Characterization Study, waste storage, on-site processing and handling, and other relevant information as determined by the Contractor.

- The Contractor shall provide the Contract Manager with a tentative schedule for sampling site order for Parts 1 and 2 at least 20 calendar days before each sampling period begins.

- The Contractor shall provide the Contract Manager with an overall schedule for fieldwork, travel, site set-up, and sorting days. For PART 3- Moisture Analysis Study, the Contractor shall provide an overall schedule for sample collection, handling, transport, and analysis at least 20 calendar days before each sampling period, including the sorting schedule for Part 1.

- The Contractor shall provide the Contract Manager with a written description of start-up tasks, and confirmation of the number of samples at each site and from each source.

- For PART 2- Multi-Family Generator-Based Waste Characterization Study, the Contractor shall confirm the number of multi-family residences to be sampled and the nodes to be used for sorting (if applicable).

- For PART 3- Moisture Analysis Study, The Contractor shall be responsible for the adhering to the agreed upon coordination schedule and logistical arrangements with each site and/or off-site location used for the analyses.

Task 3 – Perform Fieldwork-Field Sampling and Sorting

- Task 3 Fieldwork-Field Sampling and Sorting for ALL THREE PARTS of the study

  - SAMPLING PERIODS: The Contractor shall conduct sampling for all three parts of the study during two 4-month sampling periods, no less than two months apart. CalRecycle anticipates that the two seasons will span calendar year 2020 and early 2021.

  - HEALTH AND SAFETY: The Contractor shall have a written health and safety plan, implement health and safety measures, conduct training and monitor effectiveness. The Contractor shall comply with all local, state, and federal health and safety codes, regulations, and laws.

  - FIELD OBSERVATIONS: The Contractor shall accommodate observation by the Contract Manager, other CalRecycle staff, and other interested parties, at the sampling sites.

- Task 3: For PART 1- Disposal Facility-Based Waste Characterization Study

      - SAMPLE COLLECTION: The Contractor shall collect samples of waste from selected vehicles at sampling sites. If a transfer station is substituted for a landfill, the Contractor shall collect samples only of materials destined for disposal after any processing.

      - EQUIPMENT: The Contractor shall provide all equipment needed for fieldwork, including health and safety equipment. During the initial site recruitment, CalRecycle will determine if a loader/skid steer loader and an equipment operator/driver are available on-site. If a loader/skid steer loader or similar equipment and an equipment operator/driver are not available, the Contractor shall arrange to rent a loader/ skid steer loader or similar equipment and provide a certified/trained operator/driver.

      - VEHICLE SELECTION: The Contractor shall select vehicles from which to collect samples to comply with the sample source sector allocations provided by the Contract Manager. The source sector allocations shall specify the number of samples to be taken from vehicles delivering single-family residential route loads, commercial/multi-family route loads, transfer truck loads, and self-haul loads. The Contractor shall select vehicles from which to sample in a manner that is representative of the loads delivered to the sampling site and does not introduce bias.

      - VEHICLE DATA COLLECTION: For each load sampled at a facility, the Contractor shall obtain and record:

    - A unique identification (ID) number for each sample taken.

    - The date of collection.

    - The name of the sampling site.

    - Local weather conditions.

    - Any notes or unusual circumstances.

    - The jurisdiction (city or unincorporated county area) and county of origin.

    - Vehicle type and the source sector including (1) single-family residential route load, (2) commercial/multi-family route load, (3) transfer truck loads, and (4) self-haul loads.

    - For each commercial/multi-family load, the estimated percentage of multi-family waste.

    - For each self-haul load, the subsector of origin: (1) residential, (2) general commercial/industrial, (3) construction and demolition, (4) roofing, (5) landscaper, (6) disaster debris, (7) designated waste, or (8) other (specify subsector).

    - For each transfer truck, the total weight delivered, the name of the originating facility, the number of samples collected from the load, and any other pertinent information.

    - For each route-truck and self-haul vehicle, load weight, specifically the exact weight of the load as per the scale before entering the facility minus the unladen vehicle weight. In the absence of a scale, the Contractor shall use the methodology proposed in the RFP to estimate the load weight.

      - SAMPLE WEIGHT: The Contractor shall collect samples that weigh at least 200 pounds for each load sampled from all vehicle types. The Contract Manager shall reject each underweight sample and the Contractor shall substitute underweight samples with additional samples that meet the weight requirement. If a self-haul load weighs less than 200 pounds (as do many passenger carloads), the Contractor shall collect additional loads from the same class of vehicle and subsector of origin until the total weight exceeds 200 pounds. After combining these subsamples, the Contractor shall handle and count the aggregate as one sample. If submitted sample data is below the agreed upon weight, the samples shall not be accepted as fulfilling the terms of the contract, and the Contract Manager will have the discretion to withhold the payment for each underweight sample.

      - NUMBER OF SAMPLES PER LOAD: The Contractor shall collect samples in a manner that is representative of the selected load and does not introduce bias.

          - The Contractor shall collect only one sample from each selected route truck or self-haul vehicle.

          - For each selected transfer truck, the Contractor shall collect two samples, each composed of three subsamples from distinct locations in the load.

          - If a transfer/processor is substituted for a landfill as a sampling site, the Contractor shall collect samples from route trucks and self-haul vehicles, and distinct samples from the tipping floor representative of waste outflows destined for disposal.

      - CHARACTERIZING THE MATERIAL:  After a load is selected, the Contractor shall determine if hand-sorting is impractical and/or unsafe.

      - HAND-SORTING:

- If hand-sorting is acceptable:

        - the Contractor shall hand-sort samples of solid waste into individual material types listed in Table 2 of the Appendix.

        - The Contractor shall sort all materials with a particle size of 2 inches or larger. If it is practical to sort distinct, easily identifiable and sortable objects (such as plastic bottle caps) that are smaller than 2 inches, the Contractor shall do so. For materials smaller than 2 inches that are not distinct, easily identifiable and sortable objects, the Contactor shall classify this material as “mixed residue.”

        - For material that is difficult to sort due to adhesion, wetness, or partial decomposition, the Contractor shall make their best judgement to categorize the material. If it is practical to separate joined materials (such as a zip lock bag with metal screws in it), the Contractor shall do so.

- If hand-sorting has been determined to be impractical and/or unsafe:

- The Contractor shall document the reasons that hand-sorting is not safe or practical.

- The Contractor shall be permitted to conduct visual characterization only on loads that:

- Are composed of no more than ten different, clearly distinct material types,

- Do not contain bagged materials, and

- Do not contain heterogeneous mixtures of materials.

- The Contractor shall visually characterize the entire load, not just a 200-pound sample.

- The Contractor shall characterize the material into the individual material types listen in Table 2 of the Appendix.

- The Contractor shall have two staff independently conduct the visual characterization. These staff shall then discuss and agree on a final characterization result that gives the percentage of each material in the entire load.

- The Contractor shall use volume-to-weight conversion factors to estimate the individual weights of each material type identified in the visual characterization. The Contractor shall provide the conversion factors to the Contract Manager for review and approval prior to conducting visual characterizations.

- The Contractor shall clearly identify each sample that is visually characterized to distinguish it from hand-sort data.

- The Contractor shall provide a narrative description for why a visual characterization was appropriate for each specific load.

- The Contract Manager will reject samples that do not meet the criteria for visual characterization as identified above and the Contractor shall substitute the rejected samples with additional samples that do meet the criteria. If the substituted samples do not meet the above criteria, the Contract Manager will have the discretion to withhold payment for each rejected sample, not to exceed the marginal sample cost for this task.

      - IMPACT OF VISUAL CHARACTERIZATIONS ON OVERALL SAMPLE NUMBERS:

  - When used as described above, a visual characterization may substitute for a hand-sort. However, visual characterizations are substantially faster and cheaper than hand-sorts. The Contractor shall substitute a hand-sort sample with visual characterizations, but there shall be five visual characterizations assessed for each hand-sort that is substituted/removed. The Contractor shall evaluate each sample-by-sample case whether a load is appropriate for hand-sort or visual characterization.

  - If the Contractor does not conform to the requirements for visual characterizations, the Contract Manager may place a cap on the number of visual characterizations or prohibit additional visual characterization.

      - DIGITAL IMAGES: The Contractor shall provide a photography plan that will address the specifications described below:

      - When taking digital images of each load/sample, the Contractor shall place a placard on, adjacent, or near the load/sample clearly identifying the unique load/sample ID number, location, and date.

      - The Contractor shall name each digital image file so it correlates to the unique load/sample ID.

      - The Contractor shall provide images with a minimum resolution of 12-megapixels. If the digital image requirements are not met as previously described, such as, but not limited to, blurry images, the load is not clearly identified, and/or improper file naming, the digital images shall not be accepted as fulfilling the contract, and the Contract Manager will have the discretion to withhold payment for each mishandled sample.

      - SAMPLE SELECTION IMAGES:

- For each selected route truck, self-haul vehicle and transfer truck, the Contractor shall take image(s) that clearly allow for visualization of the entire waste load, after being dumped by the truck/vehicle and before removal of waste sample.

      - CHARACTERIZATION IMAGES:

- For hand-sorts, the Contractor shall meet the following specific photography requirements in their plan:

    - At least 2 images taken from different angles of the waste sample that clearly shows the entire content of the waste sample. If needed, the Contractor shall break open garbage bags and/or spread out the sample to obtain adequate digital images. If digital images are submitted and garbage bags are not broken open and/or the sample is not spread out to adequately show the contents of the sample, the Contract Manager will have the discretion to withhold payment for each unsatisfactory digital image.

- For visual characterizations, the Contractor shall take the following digital images of the waste load to demonstrate the visual characterization criteria are met:

          - The Contractor shall take image(s) that clearly allow for visualization of the entire waste load, after being dumped by the truck/vehicle and before removal of waste sample. This is critical for allowing the Contract Manager to assess if the selected load qualified for visual characterization.

          - At least 2 images of the waste load that clearly shows the entire content of the load. If needed, the Contractor shall break open garbage bags and/or spread out the load to obtain adequate digital images. If digital images are submitted and garbage bags are not broken open and/or the load is not spread out to adequately show the contents of the load, the Contract Manager will have the discretion to withhold payment for each unsatisfactory digital image. If an image is not in focus/clear or lacks to show the entire content of the load, then it cannot be confirmed if the load has qualified for a visual characterization. In this case, the sample cannot be counted, and the Contractor must re-sample accordingly. The Contract Manager will have 7 calendar days to review the previous week’s visual characterization pictures, if any, and determine if any samples need to be re-collected. If the Contractor has left the area and re-sampling at the same site is no longer logistically feasible, the Contract Manager, in consultation with the Contractor, will decide how to re-allocate that sample.

      - SORTED MATERIAL TYPES IMAGES: For each remainder composite category and mixed residue (a total of 10 material types), the Contractor shall take a digital image showing the individual items in sorted material types (i.e., a picture of the contents spread out on the ground) from 10 distinct samples each. The Contractor shall take digital images on different sample days.

- Task 3 Fieldwork-Field Sampling and Sorting for PART 2- Multi-Family Generator-Based Waste Characterization Study

- SAMPLE COLLECTION: The Contractor shall collect multi-family samples at the site of generation (e.g. apartment buildings) from waste destined for disposal.

- EQUIPMENT: The Contractor shall provide all equipment needed for fieldwork, including health and safety equipment

- MULTIPLE BINS: If there are multiple bins, the Contractor shall take subsamples from the bins to be representative of waste on-site and combine the subsamples into one representative sample.

- SAMPLE WEIGHT: The Contractor shall collect samples that weigh at least 200 pounds. If a multi-family residence has less than 200 pounds of waste to sample, the Contractor shall collect additional waste on subsequent days until the total weight exceeds 200 pounds. After combining these subsamples, the Contractor shall handle and count the aggregate as one sample. The Contract Manager shall reject each underweight sample and the Contractor shall substitute additional samples that meet the weight requirement. If submitted sample data is below the agreed upon weight, the samples shall not be accepted as fulfilling the contract, and the Contract Manager shall have the discretion to withhold payment for each underweight sample.

- SAMPLE VOLUME: The Contractor shall determine the combined bin volume of the waste bins on-site and estimate total volume of all on-site waste at the time of collection. The Contractor shall estimate the in-place sample volume at the time of collection.

- CHARACTERIZING THE MATERIAL: The Contractor shall hand-sort all multi-family samples.

- The Contractor shall hand-sort samples of solid waste into individual material types listen in Table 2 of the Appendix.

- The Contractor shall sort all materials with a particle size of 2 inches or larger. If it is practical to sort distinct, easily identifiable objects (such as plastic bottle caps) that are smaller than 2 inches, the Contractor shall do so. For materials smaller than 2 inches that are not distinct, easily identifiable and sortable objects, the Contactor shall classify this material as “mixed residue.”

- For material that is difficult-to-sort due to adhesion, wetness, or partial decomposition, the Contractor shall make their best judgement to categorize the material. If it is practical to separate joined materials (such as a zip lock bag with metal screws in it), the Contractor shall do so.

- DIGITAL IMAGES: The Contractor shall provide a photography plan that will address the specifications described below:

  - When taking a digital image of each bin/sample, the Contractor shall place a placard on, adjacent, or near the bin/sample clearly identifying the unique sample ID number, location, and date. The Contractor shall name each digital image file so it correlates to the unique bin/sample ID. The Contractor shall provide images with a minimum resolution of 12-megapixels. If the digital image requirements are not met as previously described, such as, but not limited to, blurry images, the load is not clearly identified, and/or improper file naming, the digital images shall not be accepted as fulfilling the contract, and the Contract Manager shall have the discretion to withhold payment for each mishandled sample.

  - For each multi-family sample, the Contractor shall take:

    - Image(s) that clearly allow for visualization of the contents in the entire waste bin, before removal of waste sample.

    - At least 2 images of the waste sample that clearly shows the content of the waste sample. If needed, the Contractor shall break open garbage bags and/or spread out the sample to obtain adequate digital images. If digital images are submitted and garbage bags are not broken open and/or the sample is not spread out to adequately show the contents of the sample, the Contract Manager will have the discretion to withhold payment for each unsatisfactory digital image.

- Task 3 Fieldwork-Field Sampling and Sorting for PART 3- Moisture Analysis Study of Paper Types

- SAMPLE COLLECTION:  The Contractor shall collect the selected materials from the sorted materials after they have been weighed and recorded in Part 1. The Contractor shall create one composite sample for each selected material type set from all hand-sorted material on each specified sampling day as agreed upon by the Contract Manager and the Contractor.

- EQUIPMENT: The Contractor shall provide all equipment needed for fieldwork, including health and safety equipment.

- SAMPLING PERIODS: The Contractor shall use the same two sampling periods as in Part 1.

- SAMPLING DAYS: The Contractor shall gather the material needed for the Moisture Analysis Study on the number of sampling days discussed, selected and agreed upon by the Contract Manager and the Contractor.

- SELECTED MATERIALS: The Contractor shall gather the selected materials listed in Table 3 of the Appendix.

- SAMPLE WEIGHTS: The Contractor shall aggregate material by type until:

    - The composite sample for the material type weighs at least 20 pounds, or

    - The end of the sampling day is reached regardless of if the composite sample weighs less than 20 pounds. For example, the composite sample of corrugated cardboard is achieved by aggregating sorted corrugated cardboard from PART 1 of the study on a given sort day by either collecting up to 20 pounds of the material or by reaching the end of the day, whichever occurs first.

- SAMPLE HANDLING AND STORAGE: The Contractor shall start the Moisture Analysis Study within one week of the samples being collected to prevent further sample changes and degradation.

- SAMPLE TRACKING: The Contractor shall assign a new unique sample ID number to each composite sample and associate it with the corresponding unique original sample ID numbers and sectors that contributed to the composite sample, and composite sample weight.

- SAMPLE ANALYSIS AND STANDARDS:

  - Measure Moisture Absorption by Various Paper Types

    - The Contractor shall conduct this in the field at the corresponding sampling site or at another location proposed by the Contractor.

    - The Contractor shall, prior to analysis, record composite sample weight and corresponding composite sample ID number.

    - The Contractor shall remove moisture from the composite samples at an appropriate location.

    - The Contractor may air dry the composite samples using a drying method such as a desiccator containing a charged drying agent, an electronic dehumidifier, or a dry heat source. As part of its bid, the Contractor may propose other drying methods to meet the standards and objectives of this task.

    - The Contractor shall continue the drying process until samples reach equilibrium. Equilibrium has been reached when the weight of the sample does not decrease by more than 1 percent. The Contractor may propose their own sample measurement scheme. As an example, the Contractor could weigh the composite samples, dry for at least four hours and weigh the composite sample again. At that point the Contractor may use the last weight as the final sample weight.

    - The Contractor shall record composite sample weights and corresponding composite sample ID number.

- DIGITAL IMAGES:

- When taking a digital image of each composite sample, the Contractor shall place a placard on, adjacent, or near the sample clearly identifying the unique sample ID number, location, and date. The Contractor shall name each digital image file so it correlates to the unique composite sample ID. The Contractor shall provide images with a minimum resolution of 12-megapixels. If the digital image requirements are not met as previously described, such as, but not limited to, blurry images, the composite sample is not clearly identified, and/or improper file naming, the digital images shall not be accepted as fulfilling the contract, and the Contract Manager will have the discretion to withhold payment for each mishandled sample.

- For each composite sample, the Contractor shall take:

    - One image that will allow for clear visualization of the entire composite sample, for each sample, before processing.

    - One image that will allow for clear visualization of the entire composite sample, for each sample, after processing to remove moisture.

Task 4 - DATA COLLECTION

- TASK 4 - Data Collection for PART 1- Disposal Facility-Based Waste Characterization Study.

- The Contractor shall record all characterization data for each sample:

- For hand-sorts, the load weight (specifically the exact weight of the load as per the scale before entering the facility minus the unladen vehicle weight. In the absence of a scale, the Contractor shall use the methodology proposed in the RFP to estimate the load weight), the weight of each sorted material type and total sample weight shall be recorded. The Contractor shall use a scale that is accurate to within 0.01 pounds and is connected to a computer to record weights. The Contractor shall record weights in decimal pounds.

- For visual characterizations, the percentage of each material in the entire load and the tare weight of the entire load. The Contractor shall report percentages to the nearest percent. The Contractor shall record weights in decimal pounds and provide all volume-to-weight conversion factors used.

- Task 4 - Data Collection for PART 2- Multi-Family Generator-Based Waste Characterization Study

  - The Contractor shall collect the following information at each multi-family residence:

    - The sample weight and volume (cubic yards)

    - Confirmation of number and size (volume) of waste bins at the site,

    - Collection frequency for the bins,

    - Total volume of waste in disposal bin at sample collection,

    - Sample collection and bin observations on whether it was an appropriate day to obtain representative data on volumes,

    - Accurate accumulation time of waste or rate of accumulation (cubic yards/hours of bin accessibility) and raw data for accumulation time calculations,

    - Confirmation of number of occupied units and corresponding unit size (number of bedrooms/unit) and

    - Other pertinent information.

  - The Contractor shall assign a unique ID number to each sample, and record the date of collection, name and location of the multi-family residence including jurisdiction (city or unincorporated county) and county.

  - The Contractor shall record the weight of each sorted material type and total sample weight. The Contractor shall use a scale that is accurate to within 0.01 pounds and is connected to a computer to record weights. The Contractor shall record weights in decimal pounds.

- Task 4 - Data Collection for PART 3- Moisture Analysis Study

  - For before and after weights, the Contractor shall measure and record the weight of each composite sample (by material type) using a scale that is accurate to within 0.01 pounds and is connected to a computer to record weights. The Contractor shall record weights in decimal pounds.

Task 5 – Data Entry and Data QA/QC for ALL PARTS of the study

- At least 30 calendar days prior to the first sampling period, the Contractor shall submit sample printouts displaying database and/or spreadsheet format to the Contract Manager for approval.

- The Contractor shall implement QA/QC measures when providing field-sorting data for each sorted sample (weight of each material type in the sample) and total sample weight for the Disposal Facility-Based study, the Multi-Family Generator-Based study, and the Moisture Analysis Study.

- The Contractor shall perform all data entry and follow all quality control measures in their plan to ensure the accuracy of the data entered. The Contractor shall resolve any errors or discrepancies in data discovered during quality control activities and/or review by the Contract Manager.

- The Contractor shall enter all data collected into electronic spreadsheets (e.g. Microsoft Excel) compatible with CalRecycle’s computer system. The Contract Manager will approve the format and software. Upon contract approval, the Contract Manager shall provide the Contractor with a sample format for data submission. The Contractor shall submit all final data to CalRecycle in electronic form (e.g. via e-mail or uploaded to a secure shared drive).

- The Contractor shall present and submit the data as follows: sample IDs in rows and collected data in columns. The Contractor shall submit complete data for each sample, including, at a minimum: (1) unique sample ID number, (2) name of facility/site sample was collected from, (3) date of collection, (4) for PART 1, the load weight of truck to be sampled for a hand-sort, specifically the exact weight of the load as per the scale before entering the facility minus the unladen vehicle weight. In the absence of a scale, the Contractor shall use the methodology proposed in the RFP to estimate the load weight, (5) total disposal sample weight, (6) weight of each disposal component in the sample by material type, (7) data used to calculate waste amounts, (8) truck/vehicle type, (9) sector and subsector for self-haul, (10) jurisdiction of origin (city or unincorporated county area) or facility of origin (for transfer trucks), (11) county of origin, (12) weather conditions on the day of collection, (13) for commercial/multi-family route loads: estimated percentage of multi-family waste, (14) for transfer trucks: name of originating facility, (15) for transfer trucks: total weight of load delivered, (16) weight of material type #1, (17) weight of material type #2-etc., (18) any notes on special circumstance or other information, as applicable, and (19) all digital images. If visual characterizations are conducted, the data needs to clearly distinguish between hand-sorts and visual characterizations and provide justification for visual characterization by sample. Additional data to be submitted for the Multi-Family Generator-Based Study and Moisture Analysis Study is identified in Task 4.

- The Contractor shall submit final and correct data, after the Contractor has thoroughly reviewed and subjected the data to stringent QA/QC procedures.

- The Contractor shall submit all data required for the three parts of the study at least 45 days before the end of the contract. This will allow enough time for the Contract Manager to review the data and correspond with the Contractor regarding any issues.

- The Contract Manager will have 30 calendar days to review the submitted data to ensure it is complete, understandable, and usable for subsequent analyses. The Contractor shall respond to any questions and address any problems or discrepancies found by the Contract Manager within 15 calendar days.

Task - 6 Submit Field Data and Summary Reports to CalRecycle

- During the sample collection period, the Contractor shall provide weekly status reports in a format provided by CalRecycle (see Sample Report). The Contractor may propose an alternative format to the weekly report that meets the standards and objectives of the report and subject to the prior approval of the Contract Manager. The reports shall include project statuses including progress made, work done and work pending, any deviation from the plan and a detailed explanation for the deviation. When appropriate, these reports shall also include meeting minutes.

- Outside the sample collection periods, the Contractor shall provide monthly status reports, but may do so more frequently.

- During field sampling operations, the Contractor shall prepare and submit to the Contract Manager weekly reports containing the following:

  - Final schedule/sampling plan for the upcoming week for disposal sites, multi-family residences, and, as applicable, moisture analysis.

  - Summary of sampling completed during the previous week, including numbers of samples characterized and names of sites from which samples were collected for each sector and/or subsector.

  - Copies of all paper field sheets (if any) and digital images taken for the previous week’s work.

  - Reports of any problems, contingency measures taken, or significant findings encountered.

  - Recommendations for adjustments to field procedures, site selection, or general study parameters, if needed.

  - Electronic files that contain the data collected from the previous week.

- Not more than 20 calendar days after the completion of data collection for all parts, the Contractor shall notify the Contract Manager if there are any changes or corrections to the data.

- Not more than 25 calendar days after the end of the first and second field periods, the Contractor shall prepare and submit to the Contract Manager a report summarizing information on all samples completed including the following:

  - The total number of samples collected and characterized,

  - For each sample, corresponding site names from which the samples were obtained,

  - For each sample, the sector and/or subsector,

  - A description and explanation of any differences between the final sampling plan and the actual field sampling performed, and

  - A description of any unusual circumstances.

CalRecycle Responsibilities:

- CalRecycle Responsibilities regarding Part 1-Disposal Facility-Based Waste Characterization Study:

- At least 45 calendar days before each sampling period begins, the Contract Manager will provide the Contractor with the final list of sampling locations, the number of sampling days and samples to be hand-sorted at each site, and the proposed allocations to each source type at each site.

- CalRecycle will determine how the samples (total number to be proposed by the Contractor) shall be distributed between facilities, sources, and sampling periods. CalRecycle will use preliminary in-house data to suggest possible sample allocation. This will be discussed and finalized during the initial meetings between the Contract Manager and the Contractor.

- CalRecycle will set two distinct 4 months sampling periods in 2020 and mid-2021, separated by not less than two months. The specific dates of the sampling periods will be finalized based on the date of contract execution.

- CalRecycle will allocate approximately half of the samples to each sampling period. The number of samples and sampling days will be based on the total number of samples proposed by the Contractor.

- Subject to logistics and recruitment success, CalRecycle will recruit 35-45 sampling sites. CalRecycle will roughly allocate the number of samples to facilities based on their level of disposal.

- To gather data representative of California’s waste stream, CalRecycle will attempt to recruit the largest landfills in California (Table 1. Largest landfills in California) as sampling sites. CalRecycle will attempt to recruit sites that accept approximately 75 percent of statewide disposal.

- CalRecycle will attempt to select only landfills as sampling sites for the collection and sorting of waste. If a selected landfill does not participate, CalRecycle will attempt to recruit the next largest landfill(s) and/or large transfer station(s) that send waste to the original landfill. CalRecycle may substitute landfills or transfer stations as needed. CalRecycle will provide a preliminary list of potential sites to the Contractor prior to the meeting identified in Task 1. Additional information on potential facilities can be found at: https://www2.calrecycle.ca.gov/SWFacilities/Directory/

- To gather data representative of California’s waste stream, CalRecycle will recruit sites throughout the State. Most sites will likely be located near large urban areas, with very few sites in rural areas.

- To stratify by source, CalRecycle will allocate the samples proportionally to approximate the statewide contribution of each source to the overall waste stream. For each sampling site, CalRecycle will identify how many samples of waste destined for disposal will be taken from each source: vehicles delivering single-family residential route loads, commercial/multi-family route loads, transfer truck loads, and self-haul loads.

- CalRecycle will determine the material types for hand-sorting and visual characterizations. CalRecycle does not anticipate any alterations to the list of material types Table 2 of the Appendix.

- CalRecycle will conduct analyses of the data and prepare any final reports.

- CalRecycle Responsibilities regarding Part 2- Multi-Family Generator-Based Waste Characterization Study:

- At least 45 calendar days before each sampling period begins, the Contract Manager will provide the Contractor with the final list of recruited multi-family residences and the pertinent logistical information to facilitate sample collection from each multi-family residence.

- CalRecycle will recruit the multi-family residences to be sampled and provide logistical information needed for sample collection (e.g. contact person, number and location of bins, pick-up day). A multi-family residence is defined as a building or complex consisting of 5 or more dwelling units.

- CalRecycle will allocate approximately half of the multi-family samples (50 samples total) to each sampling period established in Part 1. At the minimum number of samples, this equates to 25 multi-family samples per sampling period.

- At a minimum, CalRecycle will recruit 50 multi-family residences distributed throughout the state based on proximity to the selected sampling sites (nodes) in Part 1. The Contractor shall transport the multi-family samples to these nodes where the sorting shall occur.

- CalRecycle will select disposal sampling sites in Part 1 and designate them as sampling nodes for the multi-family study. CalRecycle will attempt to recruit all multi-family residences from within 10 miles of each node and will not recruit a residence further than 30 miles from the node.

- CalRecycle will provide the material type list to be used (same as in Part 1).

- CalRecycle will conduct analyses of the data and prepare any final reports.

- CalRecycle Responsibilities regarding Part 3-- Moisture Analysis Study:

- At least 45 calendar days before each sampling period begins, the Contract Manager will provide the Contractor with the final number of samples to collect from each source/sector for the moisture analysis at each site. This will be based on total samples per material type proposed in the Contractors Moisture Analysis Study Plan

- Table 3 is the final list of material types for use in the moisture analysis. The materials are a subset of those identified in Table 2 of the Appendix. The Contractor shall already be sorting the material into the selected materials for PART 1 of the study.

- CalRecycle will allocate approximately half of the total (total sample number to be proposed by the Contractor) moisture analysis composite samples to each sampling period established in Part 1. A composite sample is the combined materials of each specific type identified in Table 3 of the Appendix from all samples sorted in PART 1 on a designated sampling day.

- The Contract Manager and the Contractor will agree upon which Part 1 sampling sites shall be used to collect the already sorted materials for the Moisture Analysis, and the sampling days on which materials are to be collected.

## Contract/Task Time Frame

| Task | Task Description | Start Date | End Date |
| --- | --- | --- | --- |
| 1 | Initial Meeting to Review Disposal Facility-Based Study Implementation Plan | Contract execution | 60 days post contract execution |
|  | Review Multi-Family Generator Study Implementation Plan |  |  |
|  | Review Moisture Analysis Implementation Plan |  |  |
| 2 | Coordinate with Disposal Facilities and Determine Field Schedule | Within 30 days of Contract Execution | 1st Sampling Period: 45 days before start of sampling period 2nd Sampling Period: 45 days before start of sampling period |
|  | Coordinate with Multi-family Residences and Determine Field Schedule |  |  |
|  | Determine Moisture Analysis Field Schedule |  |  |
| 3 | Perform Fieldwork-Field Sampling and Sorting at Disposal Facilities | Not to exceed 45 days post site coordination for each sampling period Composite sample processing must start with 1 week of initial sample collection and sorting for PART 1. | Not to exceed 4 months post fieldwork-field sampling and sorting start for each sampling period |
|  | Perform Fieldwork-Field Sampling and Sorting at Disposal Facilities |  |  |
|  | Conduct Moisture Analysis |  |  |
| 4 | Data Collection | ongoing | ongoing |
| 5 | Data Entry and Data QA/QC | As data is produced | 45 days before end of contract (12 months post contract execution) |
| 6 | Submit Field Data and Summary Reports to CalRecycle | As fieldwork begins | 45 days before end of contract (12 months post contract execution) |

## Location of Services

Services will be provided state-wide.  The location for meetings with the Contract Manager will be determined by the Contract Manager.  Meetings will be held via teleconference, at the Sacramento Environmental Protection Agency Headquarters (1001 I Street, Sacramento, CA 95814), or by other appropriate means such as webinar.

## Control of Work

- The Contract Manager has the authority to determine the quality and acceptability of the following:

- Work to be performed

- Rate and progress of the work

- Fulfillment of the services provided by the Contractor

- Compensation for services provided by the Contractor

These decisions will be deemed final and enforceable by the Contract Manager when the Contractor fails to complete orders required by this Contract.

The Contractor shall immediately bring any unanticipated issues to the attention of the Contract Manager.  The Contract Manager will confer with appropriate CalRecycle staff, if necessary, and the Contractor to resolve the issue.

- The Contractor will designate a Project Manager who holds the following authority:

  - Act as the Contractor’s Representative for work to be provided under this Contract

  - Act as the Contractor’s Representative regarding contractual matters relating to this Contract

If during the course of the Contract, it is deemed necessary to replace the Project Manager, Contract Manager approval is required.

|  | ## Appendix |  |
| --- | --- | --- |

| Table 1. Largest landfills in California in descending order of percentage waste disposed in 2018 |  |  |  |
| --- | --- | --- | --- |
| Name | SWIS | County | % of CA waste disposed in 2018 |
| El Sobrante Landfill | 33-AA-0217 | Riverside | 8.47% |
| Frank R. Bowerman Sanitary LF | 30-AB-0360 | Orange | 5.92% |
| Olinda Alpha Landfill | 30-AB-0035 | Orange | 5.35% |
| Sunshine Canyon City/County Landfill | 19-AA-2000 | Los Angeles | 5.28% |
| Chiquita Canyon Sanitary Landfill | 19-AA-0052 | Los Angeles | 3.83% |
| Otay Landfill | 37-AA-0010 | San Diego | 3.47% |
| Simi Valley Landfill & Recycling Center | 56-AA-0007 | Ventura | 3.19% |
| Mid-Valley Sanitary Landfill | 36-AA-0055 | San Bernardino | 2.82% |
| Altamont Landfill & Resource Recovery | 01-AA-0009 | Alameda | 2.46% |
| Sycamore Landfill | 37-AA-0023 | San Diego | 2.38% |
| Potrero Hills Landfill | 48-AA-0075 | Solano | 2.34% |
| West Miramar Sanitary Landfill | 37-AA-0020 | San Diego | 2.30% |
| Central Disposal Site | 49-AA-0001 | Sonoma | 2.27% |
| Badlands Sanitary Landfill | 33-AA-0006 | Riverside | 2.23% |
| Sacramento County Landfill (Kiefer) | 34-AA-0001 | Sacramento | 2.15% |
| Forward Landfill, Inc. | 39-AA-0015 | San Joaquin | 2.14% |
| Keller Canyon Landfill | 07-AA-0032 | Contra Costa | 2.03% |
| Recology Hay Road | 48-AA-0002 | Solano | 1.79% |
| Monterey Peninsula Landfill | 27-AA-0010 | Monterey | 1.63% |
| Toland Road Landfill | 56-AA-0005 | Ventura | 1.57% |
| American Avenue Disposal Site | 10-AA-0009 | Fresno | 1.51% |
| Lamb Canyon Sanitary Landfill | 33-AA-0007 | Riverside | 1.49% |
| Corinda Los Trancos Landfill (Ox Mtn) | 41-AA-0002 | San Mateo | 1.46% |
| Newby Island Sanitary Landfill | 43-AN-0003 | Santa Clara | 1.38% |
| Prima Deshecha Landfill | 30-AB-0019 | Orange | 1.36% |
| Anderson Landfill, Inc. | 45-AA-0020 | Shasta | 1.29% |
| Antelope Valley Public Landfill | 19-AA-5624 | Los Angeles | 1.29% |
| Bakersfield Metropolitan (Bena) SLF | 15-AA-0273 | Kern | 1.16% |
| Scholl Canyon Landfill | 19-AA-0012 | Los Angeles | 1.01% |
| Redwood Landfill | 21-AA-0001 | Marin | 0.90% |
| Azusa Land Reclamation Co. Landfill | 19-AA-0013 | Los Angeles | 0.90% |
| H.M. Holloway Inc. | 15-AA-0308 | Kern | 0.89% |
| Visalia Disposal Site | 54-AA-0009 | Tulare | 0.81% |
| Highway 59 Landfill | 24-AA-0001 | Merced | 0.80% |
| Calabasas Landfill | 19-AA-0056 | Los Angeles | 0.80% |

| Table 2. 2020 Material List and Definitions by Category |  |  |  |
| --- | --- | --- | --- |
| Running Total | Category Name and # | Material Type and Definition | Examples |
| 1 | P1 (Paper) | Corrugated Cardboard means a paper laminate usually composed of three layers. The center wavy layer is sandwiched between the two outer layers. It can be uncoated or have a (glossy) coating on the inside or outside. This type does not include paperboard boxes such as cereal and tissue boxes. Excludes waxed cardboard. | - cardboard packaging and containers - shipping and moving boxes - computer packaging cartons - sheets and pieces used as dividers in boxes - boxes used for primary packaging of various consumer goods |
| 2 | P2 (Paper) | Paper Grocery Bags means bags (usually brown) made from Kraft paper generally designed to carry out groceries from stores and that can be clearly identified as coming from a grocery store. | - paper grocery bags |
| 3 | P3 (Paper) | Other Paper Bags/Kraft Paper means bags made from Kraft paper that are not clearly identified as grocery bags, and sheets of Kraft paper. The paper may be brown (unbleached) or white (bleached). The paper may also be single layer or multi-layer (multiwall). | - single-layer bags that are not grocery bags (e.g. department store bags, paper lunch bag) - multiwall bags that do not have a plastic layer incorporated into the bags (e.g. used for shipping bulk products like pet food, rice, flour and sugar) - heavyweight sheets of Kraft packing paper |
| 4 | P4 (Paper) | Newspapers/Newspaper Inserts: means paper used in newspapers and all items made from newsprint. | - Newspapers - glossy inserts found in newspapers - free advertising guides - election guides - plain news packing paper - telephone books |
| 5 | P5 (Paper) | White Office-type Paper and Mail means white paper used in offices and mail. Does not include envelopes lined with plastic or bubble wrap. | - copy paper - computer printer paper - letter paper - bills/business forms - white envelopes with or without clear windows - white cardstock |
| 6 | P6 (Paper) | Magazines and Catalogs means multi-page bound items (glued or stapled) made of glossy coated paper. This paper is usually slick, smooth to the touch, and reflects light. | - glossy magazines - catalogs - brochures - pamphlets |
| 7 | P7 (Paper) | Folding Cartons and Other Paperboard Packaging means paperboard boxes, other than corrugated, which fold and are primarily made of paper with few other materials (e.g. boxes with plastic windows are excluded) These cartons and packaging are typically used as the primary packaging for various products such as breakfast cereals, frozen foods, candy/cookies, jewelry, tobacco, pharmaceuticals and cosmetics. This also includes non-box paperboard such as paper tubes for toilet paper. | - paperboard boxes - tissue boxes - shoe boxes - paper-based tubes and cores (e.g. for toilet paper or paper towels) - paper clothing tags. |
| 8 | P8 (Paper) | Aseptic Containers and Gable-top Cartons means bleached polycoated paperboard containers or paper containers with a foil liner of various sizes and shapes that contain shelf-stable food products (i.e. aseptic containers) and paper-based cartons with a triangular top used for refrigerated and non-refrigerated items (i.e. gable-top cartons) Containers may include a plastic pour spout as part of the container. | - containers for apple juice, soup, soy/rice milk. - cartons used for milk, egg substitutes, and juice - gable-top containers used for snacks |
| 9 | P9 (Paper) | Paper/Fiber Food Service Ware means items made mostly of paper that are used to consume, contain, or transport prepared food items. Includes paper and molded fiber, including compostable and non-compostable items. May be contaminated with food and/or moisture. Excludes packaging. | - plates - bowls - cups - utensils - straws - stirrers - take-out containers - pizza boxes - bakery/bread bags - condiment cups |
| 10 | P10 (Paper) | Other Recyclable Paper means items made of paper that do not fit into any of the other paper types, but that are generally recyclable or not generally composted. Paper may be combined with minor amounts of other materials such as wax or glues. | - colored paper - manila folders - manila envelopes - index cards - lined or colored notebook paper - carbonless forms - chipboard - self-adhesive notes - hardcover and paperback books - bagged shredded paper - greeting cards |
| 11 | P11 (Paper) | Remainder/Composite Paper means items made mostly of paper but combined with large amounts of other materials. These are items that do not fit into any other categories and are not generally compostable or recyclable. Excludes packaging and food service ware. | - Blueprints - Sepia - carbon paper - photographs - sheets of paper stick-on labels - lined butcher paper - envelopes lined with plastic or bubble wrap. |
| 12 | P12 (Paper) | Other Paper/Fiber - Packaging means items that are made mostly of paper or molded fiber that don’t fit into any other material types and that are used for packaging. They may be combined with other materials or contaminated with food and/or moisture. Excludes food service ware, including clamshells, cups, bowls, plates, and trays. | - pulp paper egg cartons - unused pulp plant pots - molded paper packaging (e.g. some berry trays) - food-soiled paper packaging - waxed corrugated cardboard bags and boxes with plastic component (e.g. window) - paper frozen juice cans with metal ends |
| 13 | P13 (Paper) | Other Compostable Paper means items that do not fit any other category, are made of paper, can be composted and are generally not recycled. May be contaminated with food, moisture, or wax. | - waxed paper - napkins - facial tissues - paper towels |
| 14 | PL1 (Plastic) | PETE Beverage Containers - CRV means containers for beverages that are marked with PET (1) and have the CRV symbol. | - beverage containers for soda, juice, etc |
| 15 | PL2 (Plastic) | PETE Bottles and Jars – Non-CRV means screw top bottles without the CRV symbol and jars that are marked with PET (1). | - beverage containers for soda, juice, water - jars and containers for food - containers for household products (e.g. shampoo, cleaning products) |
| 16 | PL3 (Plastic) | HDPE Beverage Containers - CRV means containers for beverages that are marked with HDPE (2) and have the CRV symbol. | - beverage containers for soda, juice, etc |
| 17 | PL4 (Plastic) | HDPE Bottles and Jars - Non-CRV means screw top bottles without the CRV symbol and jars that are marked HDPE (2). | - beverage containers for soda, juice, water - jars and containers for food - containers for household products (e.g. shampoo, cleaning products) |
| 18 | PL5 (Plastic) | Expanded Polystyrene Packaging means packaging items made of expanded polystyrene. Does not include non-packaging items such as insulation boards. | - egg cartons - foam ice chests - transport and other packaging |
| 19 | PL6 (Plastic) | Plastic Trash Bags means plastic bags sold for use as trash bags, for both residential and commercial use. This type does not include other plastic bags, like shopping bags, that might have been used to contain trash. | - garbage bags and can liners - compostable plastic bags - lawn and leaf bags |
| 20 | PL7 (Plastic) | Plastic Grocery and Other Merchandise Bags means plastic shopping bags used to contain merchandise to transport from the place of purchase, given out by the store with the purchase. Does not include produce bags. | - dry cleaning bags - grocery bags - merchandise bags |
| 21 | PL8 (Plastic) | Film Products- Non-Packaging means plastic film used for purposes other than packaging, including agricultural use. | - agricultural film - wrap for hay bales - plastic sheeting (e.g. drop cloths) - building wrap - x-ray film - metallized film (e.g. balloons) - plastic food wrap |
| 22 | PL9 (Plastic) | Flexible Plastic Pouches means plastic pouches made of thicker, multi-layer flexible material. Material is thicker than potato chip bags and frozen vegetable bags. May have a flat bottom so that package would stand up on its own, but not always. May have plastic screw tops. | - child resistant pouch bags - plastic coffee bags - juice pouches (e.g. Capri Sun) - baby food pouches - food pouches for soup, salad, wine, or backpacking meals - soap refill pouches |
| 23 | PL10 (Plastic) | Non-Bag Commercial and Industrial Packaging Film means film plastic used for large-scale packaging or transport packaging. | - shrink wrap - mattress bags - furniture wrap - film bubble wrap |
| 24 | PL11 (Plastic) | Film Bags means all other plastic film, in bag form, that does not fit into any other type, excluding flexible plastic pouches. Excludes packaging. | - sandwich bags and zipper bags - newspaper bags - produce bags - mailing pouches |
| 25 | PL12 (Plastic) | Plastic Food Service Ware means items made partially or entirely of plastic that are used to consume, contain, or transport prepared food items. Includes all plastic types including compostable plastics. Excludes packaging. | - plates - bowls - cups (and lids) - utensils - straws - stirrers - take-out containers (e.g. clamshells) - bakery bags - condiment cups |
| 26 | PL13 (Plastic) | Other Plastic Packaging means jars, containers (including lids), and other packaging that are made of plastic, including film plastics. Only includes bottles and containers not included in any other category. Only includes film plastics not included in other categories. They may bear the triangular recycling symbol or may bear no recycling symbol. Excludes foodservice ware, including clamshells, takeout containers, cups, bowls, plates, and trays. | - frozen vegetable bags - bread bags - potato chip bags - candy wrappers - yogurt cups - ketchup bottles - small storage containers for fresh produce - household cleaning bottles - microwave food trays - vitamin bottles - cookie trays - single-use plant containers - thermoform packaging (e.g. berry containers) |
| 27 | PL14 (Plastic) | Durable Plastic Items means plastic items that are made to last for more than one use. These items may bear the numbers 1 through 7 in the triangular recycling symbol. | - crates, totes, buckets, tubs - plastic garbage cans - flower pots larger than one gallon - lawn furniture - plastic toys and sporting goods - CDs and cases - Plastic housewares including durable plates, cups, utensils - Building materials such as house siding, housing for electronics, fan blades, plastic pipes and fittings |
| 28 | PL14 (Plastic) | Remainder/Composite Plastic means plastic that cannot be put in any other type. This type includes items made mostly of plastic but combined with other materials. | - window blinds - insulating foam - imitation ceramics - handles and knobs - plastic lumber - EPS not used for packaging or food service ware - rigid bubble/foil packaging (e.g. blister pack) - some toys - some kitchenware - some auto parts |
| 29 | G1 (Glass) | Clear Glass Bottles and Containers – CRV means clear glass containers that display the CRV notification. Includes whole and broken bottles. | - soda bottles - fruit juice bottles - wine cooler bottles |
| 30 | G2 (Glass) | Clear Glass Bottles and Containers - Non-CRV means clear glass containers that do not display the CRV notification. Includes whole and broken containers. | - wine bottles - food jars |
| 31 | G3 (Glass) | Green Glass Bottles and Containers – CRV means green-colored glass containers that display the CRV notification. Includes whole and broken bottles. | - soda bottles - beer bottles |
| 32 | G4 (Glass) | Brown Glass Bottles and Containers – CRV means brown-colored glass containers that display the CRV notification. Includes whole and broken bottles. | - beer bottles |
| 33 | G5 (Glass) | Green and Brown Glass Bottles and Containers - Non-CRV means brown-colored or green-colored glass containers that do not display the CRV notification. Includes whole and broken containers. | - wine bottles |
| 34 | G6 (Glass) | Other Colored Glass Bottles and Containers means other-colored glass containers, with or without the CRV notification. Includes whole and broken containers. | - blue soda and water bottles - wine bottles - liquor bottles |
| 35 | G7 (Glass) | Remainder/Composite Glass means glass that cannot be put in any other type. It includes flat and curved glass and items made mostly of glass but combined with other materials. Includes whole or broken items. | - window panes - doors and table tops - automotive glass - safety glass - Pyrex and kitchen glass - crystal and glass tableware - drinking glasses - mirrors - non-fluorescent light bulbs - laminated glass |
| 36 | M1 (Metal) | Tin/Steel Cans means rigid containers made mainly of steel, both CRV and non-CRV containers. These items will stick to a magnet and may be tin-coated. This subtype is used to store food, beverages, paint, and a variety of other household and consumer products. | - canned food and beverage containers - empty metal paint cans - empty spray paint cans and aerosol containers - bimetal containers with steel sides and aluminum ends |
| 37 | M2 (Metal) | Aluminum Cans - CRV means any food or beverage container that is made mainly of aluminum and that displays the CRV notification. This subtype does not include bimetal containers with steel sides and aluminum ends. | - soda or beer cans |
| 38 | M3 (Metal) | Aluminum Cans - Non-CRV means any food or beverage container that is made mainly of aluminum and that does not display the CRV notification. | - pet food cans - meat cans - wine cans |
| 39 | M4 (Metal) | Major Appliances means discarded major appliances encased in metal, of any color. These items are often enamel-coated. This type does not include electronics, such as televisions and stereos. | - washing machines - clothes dryer - hot water heater - stove - refrigerator |
| 40 | M5 (Metal) | Other Ferrous means any iron or steel that is magnetic or any stainless-steel item. This type does not include tin/steel cans. | - structural steel beams - metal clothes hangers - metal pipes - stainless steel cookware - security bars - scrap ferrous items - reusable stainless steel water bottle |
| 41 | M6 (Metal) | Other Non-Ferrous means any metal item, other than aluminum cans, that is not stainless steel and that is not magnetic. These items may be made of aluminum, copper, brass, bronze, lead, zinc, or other metals. | - aluminum window frames - aluminum siding - copper wire - shell casings - brass pipes - aluminum foil - some cookware |
| 42 | M7 (Metal) | Remainder/Composite Metal means metal that cannot be put in any other type. This type includes items made mostly of metal but combined with other materials and items made of both ferrous metal and non-ferrous metals combined. Includes products whose weight is derived significantly from the metal portion of its construction. | - small non-electronic appliances (e.g. toasters, hair dryers) - used oil filters - motors - insulated wire |
| 43 | E1 (Electronics) | Covered Video Display Devices means video display devices with a screen greater than four inches, measured diagonally. A video display device may use, but is not limited to, a cathode ray tube (CRT), liquid crystal display (LCD), gas plasma, digital light processing or other image projection technology | - computers with displays or computer monitors - televisions - portable DVD players or gaming console with screen - tablet computers (e.g. iPad or Kindle) - cathode ray tubes |
| 44 | E2 (Electronics) | Consumer Electronics and Small Equipment means small IT and telecommunication equipment, and other small items that usually need electric currents or electromagnetic fields to operate. | - mobile phones - GPS - calculators - printers - computer without screen - sewing machines - microwaves - irons - toasters - electric knives - shavers - toys - some sport equipment - some hair care appliances |
| 45 | E3 (Electronics) | Large Equipment means large items that usually need electric currents or electromagnetic fields to operate. | - musical equipment - slot machines - large printing machines - large exercise equipment |
| 46 | OR1 (Organics) | Food - Potentially Donatable – Vegetative (Perishable/Fresh) means uncooked or cooked fresh vegetables, fruits, and fungi that are in a whole state (i.e., not partially consumed) and are unmixed with non-vegetative food types. Items in their whole state are either in original, unopened packaging or unpackaged items from commercial sector that have clearly not been consumed (e.g. a whole apple or entire head of lettuce). Items that are excluded from this category include condiments, non-perishable packaged fruits and vegetables such as: packaged dried fruits and vegetables, canned fruits and vegetables, and nuts. Any unpackaged vegetables, fruits, and fungi found in a whole state in residential loads are excluded from this category and should be sorted as “not donatable – non-meat”. However, unpackaged vegetables fruits, and fungi found in a whole state in commercial loads are included in this category. | - unopened package of mushrooms - whole fruit or vegetable - unopened package of fruit salad or salad greens |
| 47 | OR2 (Organics) | Food - Potentially Donatable - Eggs, Dairy, and Dairy Alternatives means egg or dairy products and dairy alternatives that are in a whole state, unmixed with other food types, and in the original unopened package. Items may be refrigerated or shelf stable. | - milk - cheese (dairy and non-dairy) - eggs (whole or sliced) - yogurts - soy/nut/rice/oat milks |
| 48 | OR3 (Organics) | OR3 Food - Potentially Donatable – Meat means any uncooked or cooked meat (beef, poultry, pork, lamb) or fish product that is in a whole state, is unmixed with other food types, and is in the original unopened package. This includes meat alternatives. | - whole or cooked meat or fish in unopened package - deli meat in unopened package - unopened jerky - unopened frozen meats (e.g. chicken nuggets) canned meat and fish - meat alternatives |
| 49 | OR4 (Organics) | Food - Potentially Donatable - Cooked/Baked/Prepared Perishable Items means items that are in a whole state but could have multiple food types mixed together as a part of cooking or preparation and are still in their original unopened package. | - whole sandwich in original unopened package - whole tray of food (e.g. lasagna) that is untouched - whole frozen pizza in unopened package - whole loaves of bread - bag of tortillas - unopened perishable fresh fruit and vegetable juice |
| 50 | OR5 (Organics) | Food - Potentially Donatable - Packaged Non-perishable means shelf-stable foods that are in a whole state and are in the original unopened package. Includes foods contained in aseptic or retort packages and other products that do not require refrigeration until after opening. Also includes non-perishable beverages such as sodas. Excluded from this category are shelf-stable meats, shelf-stable dairy products, and shelf-stable dairy alternatives. | - canned and bottled foods - rice - pasta - condiments - nuts and nut butters - flour, sugar, spices - oils - non-perishable beverages |
| 51 | OR6 (Organics) | Food - Not Donatable – Meat means any food that is predominantly meat or fish, but the product is not in a whole state (i.e., partially consumed), or the product’s packaging has been opened, or the product was not contained in any packaging at all. | - partially consumed meat, meat alternatives, or fish - meat or fish in opened package - hamburger that is mostly meat by weight - meat and fish trimmings - deli meats |
| 52 | OR7 (Organics) | Food - Not Donatable – Non-meat means any food that is not predominantly meat or fish, not in a whole state, or not in its original unopened package. Includes any non-meat partially consumed foods, any non-meat foods in a package that has been opened – as best as can be determined, any non-meat foods that are not in their original packaging. Item may contain small amounts of meat or fish. This category also includes fruit and vegetable peels, skins, trimmings, and or any parts of fruits and vegetables not included in the inedible category. In addition, this category also includes any indistinguishable food. | - partially consumed burrito or lasagna - fruit and vegetable peels (e.g. potato skins, carrot peels) - fruit and vegetable trimmings (e.g. cucumber ends, carrot tops, beet greens, broccoli and cauliflower stalks) - apple and pear cores |
| 53 | OR8 (Organics) | Food - Inedible means items typically not consumed by people in the United States. Categories of inedible parts include bones, pits, shells, banana peels, coffee grounds and tea leaves, rinds, woody stems/tops and vines, and corn cobs/husks. Note that small amounts of edible material associated with the inedible material are permitted to be included as “inedible.” Excludes other fruit and vegetable peels, skins, trimmings, cores, and ends not included in the previous categories (e.g. potato peels, carrot tops, apple cores, broccoli stalks, cucumber ends). | - pits (peach, avocado) - shells (eggs, nuts) - rinds (citrus, melon) - woody stems/tops and vines (pumpkin stem, pineapple top, tomato vine) - banana peels - corn cobs and husks - bones - coffee grounds - tea leaves |
| 54 | OR9 (Organics) | Leaves and Grass means plant material, except woody material, from any public or private landscape. This type does not include woody material or material from agricultural sources. | - leaves - grass clippings - plants - seaweed |
| 55 | OR10 (Organics) | Prunings and Trimmings means woody plant material up to 4 inches in diameter from any public or private landscape. This type does not include stumps, tree trunks, or material from agricultural sources. | - pruning from shrubs - branches with diameters of less than 4 inches |
| 56 | OR11 (Organics) | Branches and Stumps means woody plant material, branches, and stumps that exceed 4 inches in diameter, from any public or private landscape. | - branches with diameters greater than 4 inches - stumps |
| 57 | OR12 (Organics) | Manures means manure and soiled bedding materials from large domestic, farm, or ranch animals. Does not include feces from small household pets such as dogs and cats. | - manure - soiled bedding from animal operations |
| 58 | OR13 (Organics) | Clean Dimensional Lumber means unpainted new or demolition dimensional lumber. May contain nails or other trace contaminants. | - 2 x 4s, 2 x 6s, 2 x 12s - residual materials from framing and related construction activities |
| 59 | OR14 (Organics) | Clean Engineered Wood means unpainted new or demolition scrap from sheeted goods. May contain nails or other trace contaminants. | - plywood - particle board - wafer board - oriented strand board - residual materials used for sheathing and related construction uses |
| 60 | OR15 (Organics) | Clean Pallets and Crates means unpainted wood pallets, crates, and packaging made of lumber/engineered wood. May contain nails or other trace contaminants. | - unpainted wood pallets - unpainted crates - packaging made of lumber/engineered wood |
| 61 | OR16 (Organics) | Treated/Painted/Stained Wood means wood that has been treated with a chemical preservative for purposes of protecting the wood against attacks from insects, microorganisms, fungi, and other environmental conditions that can lead to decay of the wood; and wood that has had an external coating such as paint, varnish, or other finish applied. | - handrails - finished furniture - other wood and wood products with paint, varnish, or other finish applied |
| 62 | OR17 (Organics) | Other Recyclable Wood means recyclable wood not included in any other category. This may include scrap from production of prefabricated wood products that have not been treated with paint, stain, or other chemical finish. Wood material should not be contaminated with another material (e.g.. tar). May contain nails or other trace contaminants. | - Untreated scrap from production of pre-fabricated wood products (e.g. from cabinets or furniture) - untreated/unpainted fencing - recyclable demolition wood - untreated/unpainted wood roofing and siding |
| 63 | OR18 (Organics) | Remainder/Composite Organic means organic material that cannot be put in any other type. | - natural cork - hemp rope - hair - small wood products (e.g. popsicle sticks, toothpicks) - sawdust - agriculture crop residues - animal carcasses - straw baskets - dryer sheets - non-textile leather - cosmetics |
| 64 | InOth1 (Inerts & Other) | Concrete means a hard material made from sand, aggregate, gravel, cement mix, and water. This category includes concrete with a steel internal structure composed of reinforcing bars (re-bar) or metal mesh. | - pieces of building foundations - concrete paving - concrete/cinder blocks |
| 65 | InOth2 (Inerts & Other) | Asphalt Roofing means composite shingles and other roofing material made with asphalt. | - asphalt roofing - asphalt shingles and attached roofing tar and tar paper |
| 66 | InOth3 (Inerts & Other) | Gypsum Board means interior wall covering made of a sheet of gypsum sandwiched between paper layers. Includes used and unused broken or whole sheets. Includes painted gypsum board. | - gypsum board - sheet rock - drywall - plasterboard - gypboard - Gyproc - wallboard |
| 67 | InOth4 (Inerts & Other) | Carpet means flooring applications consisting of various natural or synthetic fibers bonded to some type of backing material. This type does not include carpet padding or woven rugs with no backing. | - carpet |
| 68 | InOth5 (Inerts & Other) | Rock, Soil and Fines means rock pieces of any size and soil, dirt, and other matter. This type also includes nonhazardous contaminated soil. | - rock - stones - sand - clay - soil and other fines |
| 69 | InOth6 (Inerts & Other) | Remainder/Composite Inerts and Other means inerts and other material that cannot be put in any other type. This type may include items from different types combined, which would be very hard to separate. This type may also include demolition debris that is a mixture of items such as plate glass, wood, tiles, gypsum board, synthetic counter tops, fiber or composite acoustic ceiling tiles, and aluminum scrap. | - brick - ceramics - tiles - toilets - sinks - dried paint not attached to any materials - fiberglass - insulation - carpet padding - asphalt paving |
| 70 | HHW1 (Household Hazardous Waste) | Paint means containers with paint in them. This type does not include dried paint, empty paint cans, or empty aerosol containers. | - latex paint - oil-based paint - tubes of pigment - fine art paint |
| 71 | HHW2 (Household Hazardous Waste) | Used Oil means the same as defined in Health and Safety Code section 25250.1(a). | - spent lubricating oil (e.g. crankcase and transmission oil, gear oil, hydraulic oil) |
| 72 | HHW3 (Household Hazardous Waste) | Lead-acid (automotive) batteries means batteries consisting of lead-acid cells. | - auto batteries |
| 73 | HHW4 (Household Hazardous Waste) | Other batteries means any type of battery other than lead-acid (automotive) batteries. Examples include household batteries such as AA, AAA, D, button cell, 9 volt, and rechargeable batteries used for flashlights, small appliances, watches, and hearing aids. | - AA, AAA, D batteries - 9 volt batteries - rechargeable batteries - watch and hearing aid batteries |
| 74 | HHW5 (Household Hazardous Waste) | One-Pound or Less Propane Gas Cylinders means small, compact, and portable propane gas cylinders used to power devices such as camping stoves, tailgating grills, heaters, and more. Generally, these cylinders are not refillable. | - one pound or less propane gas cylinder |
| 75 | HHW6 (Household Hazardous Waste) | Pharmaceuticals means both prescription and over-the-counter medications and supplements in all forms, including pills, liquid medications, creams, and ointments. Does not include containers for these items, except for tubes for creams and ointments and other containers that cannot be easily separated from the product they contain. | - pills - liquid medications - creams and ointments |
| 76 | HHW7 (Household Hazardous Waste) | Remainder/Composite Household Hazardous means household hazardous material that cannot be put in any other type. Examples include household hazardous waste that, if improperly put in the solid waste stream, may present handling problems or other hazards. Also includes vehicle and equipment fluids other than used oil. | - pesticides - caustic cleaners - sharps - fluorescent lamps - LED lamps - mercury-containing items such as thermostats or thermometers - vehicle and equipment fluids such as used oil |
| 77 | SW1 (Special Waste) | Tires means vehicle tires. Tires may be pneumatic or solid. | - automobile tires - lawn mower tires - bicycle tires - motorcycle tires |
| 78 | SW2 (Special Waste) | Mattresses and Foundations means a resilient material or combination of materials that is enclosed by a ticking and is intended for or promoted for sleeping upon. Includes foundations, which means a ticking-covered structure used to support a mattress or sleep surface. The structure may include one or more of the following components: constructed frames, foam, box springs, or other materials. Excludes any unattached mattress pad or unattached mattress topper intended to be used with or on top of a mattress; sleeping bags and pillows; a car bed, crib, or bassinet mattress; juvenile products, including a carriage a product containing liquid- or gaseous-filled ticking, including a water bed or air mattress that does not contain upholstery material between the ticking and the mattress core; upholstered furniture that does not otherwise contain a detachable mattress or that is a fold out sofa bed or futon. | - mattresses - foundations used to support mattress |
| 79 | SW3 (Special Waste) | Bulky Items means large, hard-to-handle items that are not defined elsewhere in the material types list, including furniture and other large items. | - couches - furniture |
| 80 | SW4 (Special Waste) | Remainder/Composite Special Waste means special waste that cannot be put in any other type. Includes treated medical waste (medical waste that has been processed in order to change its physical, chemical, or biological character or composition, or to remove or reduce its harmful properties or characteristics, as defined in Section 25123.5 of the Health and Safety Code). | - ash - auto fluff - auto bodies - treated medical waste - untreated medical waste (e.g. tubes, oxygen masks) - asbestos-containing materials (e.g. certain pipes, insulation, and floor tiles) - artificial fireplace logs |
| 81 | MISC1 (Miscellaneous) | Textiles – Cloth and Clothing means cloth, clothing, sheets and towels, rope, and other textile items made of organic, synthetic, unknown, and mixed fibers. Textiles with zippers and buttons are included | - cloth and rags - clothing - towels - sheets - rope |
| 82 | MISC2 (Miscellaneous) | Textiles - Shoes, Purses, Belts means all shoes and boots, purses, and belts whether made of leather, rubber, other materials, or a combination thereof. | - shoes and sandals - purses - belts |
| 83 | MISC3 (Miscellaneous) | Solar Panels means panels used to convert sunlight into electricity. Solar panels consist of a semiconductor material such as silicon, encased in glass, with an aluminum frame. This category is specific to the panels, themselves, and does not include associated equipment such as junction boxes, wires, inverters, cables, energy storage batteries, or a photovoltaic cell that is part of a consumer electronic device for which it provides electricity needed to make the device function. | - solar panels |
| 84 | MISC4 (Miscellaneous) | Diapers & Sanitary Products means single-use items that are made from a combination of natural and/or synthetic fibers. | - diapers - feminine hygiene products - absorbent pads |
| 85 | MISC5 (Miscellaneous) | Miscellaneous Inorganics means inorganic items that cannot be put in any other type. | - kitchen ceramics - synthetic rubber products (e.g. kitchen gloves) - sports balls |
| 86 | MISC6 (Miscellaneous) | Mixed Residue means material (including 2-inch-minus materials) that cannot be put in any other type or category. This category includes mixed residue and materials smaller than two inches that cannot be further sorted. | - clumping kitty litter - feces from household pets - partially filled containers of non-food consumer products |

| Table 3. Moisture Analysis Material List Paper Categories |  |  |
| --- | --- | --- |
| Category Name and # | Material Type and Definition | Examples |
| P1 (Paper) | Corrugated Cardboard means a paper laminate usually composed of three layers. The center wavy layer is sandwiched between the two outer layers. It can be uncoated or have a (glossy) coating on the inside or outside. This type does not include paperboard boxes such as cereal and tissue boxes. Excludes waxed cardboard. | - cardboard packaging and containers - shipping and moving boxes - computer packaging cartons - sheets and pieces used as dividers in boxes - boxes used for primary packaging of various consumer goods |
| Combined P2 and P3 (Paper) | Paper Grocery Bags means bags (usually brown) made from Kraft paper generally designed to carry out groceries from stores and that can be clearly identified as coming from a grocery store. Other Paper Bags/Kraft Paper means bags made from Kraft paper that are not clearly identified as grocery bags, and sheets of Kraft paper. The paper may be brown (unbleached) or white (bleached). The paper may also be single layer or multi-layer (multiwall). | Paper Grocery Bags - paper grocery bags Other Paper Bags/Kraft Paper - single-layer bags that are not grocery bags (e.g. department store bags, paper lunch bag) - multiwall bags that do not have a plastic layer incorporated into the bags (e.g. used for shipping bulk products like pet food, rice, flour and sugar) heavyweight sheets of Kraft packing paper |
| P4 (Paper) | Newspapers/Newspaper Inserts: means paper used in newspapers and all items made from newsprint. | - Newspapers - glossy inserts found in newspapers - free advertising guides - election guides - plain news packing paper - telephone books |
| P5 (Paper) | White Office-type Paper and Mail means white paper used in offices and mail. Does not include envelopes lined with plastic or bubble wrap. | - copy paper - computer printer paper - letter paper - bills/business forms - white envelopes with or without clear windows - white cardstock |
| P6 (Paper) | Magazines and Catalogs means multi-page bound items (glued or stapled) made of glossy coated paper. This paper is usually slick, smooth to the touch, and reflects light. | - glossy magazines - catalogs - brochures - pamphlets |
| P7 (Paper) | Folding Cartons and Other Paperboard Packaging means paperboard boxes, other than corrugated, which fold and are primarily made of paper with few other materials (e.g. boxes with plastic windows are excluded) These cartons and packaging are typically used as the primary packaging for various products such as breakfast cereals, frozen foods, candy/cookies, jewelry, tobacco, pharmaceuticals and cosmetics. This also includes non-box paperboard such as paper tubes for toilet paper. | - paperboard boxes - tissue boxes - shoe boxes - paper-based tubes and cores (e.g. for toilet paper or paper towels) - paper clothing tags. |
| P9 (Paper) | Paper/Fiber Food Service Ware means items made mostly of paper that are used to consume, contain, or transport prepared food items. Includes paper and molded fiber, including compostable and non-compostable items. May be contaminated with food and/or moisture. Excludes packaging. | - plates - bowls - cups - utensils - straws - stirrers - take-out containers - pizza boxes - bakery/bread bags - condiment cups |
| P10 (Paper) | Other Recyclable Paper means items made of paper that do not fit into any of the other paper types, but that are generally recyclable or not generally composted. Paper may be combined with minor amounts of other materials such as wax or glues. | - colored paper - manila folders - manila envelopes - index cards - lined or colored notebook paper - carbonless forms - chipboard - self-adhesive notes - hardcover and paperback books - bagged shredded paper - greeting cards |
| P12 (Paper) | Other Paper/Fiber - Packaging means items that are made mostly of paper or molded fiber that don’t fit into any other material types and that are used for packaging. They may be combined with other materials or contaminated with food and/or moisture. Excludes food service ware, including clamshells, cups, bowls, plates, and trays. | - pulp paper egg cartons - unused pulp plant pots - molded paper packaging (e.g. some berry trays) - food-soiled paper packaging - waxed corrugated cardboard bags and boxes with plastic component (e.g. window) - paper frozen juice cans with metal ends |
| P13 (Paper) | Other Compostable Paper means items that do not fit any other category, are made of paper, can be composted and are generally not recycled. May be contaminated with food, moisture, or wax. | - waxed paper - napkins - facial tissues - paper towels |

SAMPLE REPORT

Project Name:

Project Status Reporting Period: From: To:

Project Manager:

Report Prepared By:

Weekly Project Summary: Enter a brief summary of the project status, noting any key issues for the week. Comment on major deliverables completed; milestones reached and percent complete.

Current Task Summary

| Task or Deliverable | Scheduled Completion Date | Actual Completion Date | Issues? If yes, explain |
| --- | --- | --- | --- |
| Example: Sample Task 1 | 31 March 2020 | 1 April 2020 | No issues for Sample Task 1 |

Accomplished this week

Sites and samples

Hand-Sorting: Indicate number of hand-sorts completed per sector (and subsector), at which sites and day(s) and provide required attachments such as photos or site details

Visual Characterization: Indicate number of visual characterizations completed per sector (and subsector), at which sites and day(s); also provide narrative description(s) per Task 3 and provide required attachments such as photos or site details.

Attachments provided? (Such as copies of paper field sheets (if any), digital images, electronic files that contain data from the previous week) Yes/No If no, provide a reasonable explanation and a date when the attachments will be submitted.

Other items such as problems, contingency measures taken, significant findings encountered, recommendations:

Weekly look ahead - Planned/Scheduled Completion in Next Two Weeks

What sites and how many days per site?

Sample Plan (Confirm the Plan Provided by CalRecycle)

Deliverables Due:

Other items, concerns, issues:

# Section VII 	Definition and Terms

General

Unless the context otherwise requires, wherever in this RFP or addenda, the following abbreviations and terms, or pronouns in place of them, are used, the intent and meaning shall be interpreted as provided in this Section.

Working titles having a masculine gender, such as “draftsman” and “journeyman” and the pronoun “he”, are utilized in these provisions for the sake of brevity and are intended to refer to persons of either sex.

Abbreviations

ADA	Americans with Disabilities Act

CAL EPA	California Environmental Protection Agency

CALRECYCLE	Department of Resources Recycling and Recovery

CCR	California Code of Regulations

DVBE	Disabled Veteran Business Enterprise

EPA	Environmental Protection Agency (Federal Government)

GC	Government Code

PCC	Public Contract Code

RFP	Request for Proposals

SB	Small Business

SOW	Scope of Work

OSDS	The Department of General Services (DGS), Procurement Division (PD), Office of Small Business and DVBE Services (OSDS)

Cal EPA

The California Environmental Protection Agency

CalRecycle Staff

Staff of the Department of Resources Recycling and Recovery involved in the implementation of this contract or representatives of Consultant to the Department of Resources Recycling and Recovery as designated in the Work Orders.

Consultant

The person or persons, firm, partnership, corporation, or combination thereof, which may enter into this Contract with CalRecycle to provide work pursuant to this RFP or his or their legal representatives

Contract

A legally binding Agreement between the state & another entity, public or private, for the provision of goods or services; the written Agreement covering performance of the work and furnishing of labor, materials, tools, and equipment in providing the work.  The Agreement shall include the RFP, Proposal, general and specific terms and conditions, Work Orders, and supplemental Agreements which may be required to complete the work in a substantial and acceptable manner.

Contract Manager

A person designated by the responsible state agency or department to manage performance under a contract.

Contractor

A party contracting with the awarding agency.  Vendor is often used synonymously with contractor.

Director

The Director of CalRecycle, or his/her designees.  Any references to Executive Officer shall mean the Director and/or designated officer.

Disabled Veteran Business Enterprise (DVBE Certified)

A business that meets all of the following criteria:  (1) at least 51% of the business is owned by one or more disabled veterans or, in a business whose stock is publicly held, at least 51% or more of the stockholders are disabled veterans (2) the management and control of the business are exercised by one or more disabled veterans; (3) the business is domestically owned and its home office is in the United States; and (4) the business has been certified as a DVBE by the State of California, Department of General Services (DGS), Procurement Division (PD), Office of Small Business and DVBE Services (OSDS).

Legal Holiday

Those days designated as State holidays in the Government Code.

Project Manager

Contractor’s representative for all work performed under this Contract.  All official correspondence, reports, submittals, billings, and other work done under this Contract shall be reviewed and signed by the Project Manager prior to submittal to CalRecycle.

Scope of Work

The description of work required of a contractor by the awarding agency.

Small Business (Certified)

A business that has been certified by the Department of General Services (DGS), Procurement Division (PD), Office of Small Business and DVBE Services (OSDS), as a small business as defined in GC 14837 and 2 CCR 1896.

State

The State of California.

State Contract Law

The Public Contract Code and other applicable laws that form and constitute a part of the provisions of this Contract to the same extent as if set forth herein in full.

Subcontractor

A person or entity which contracts with the Contractor to perform all or a portion of the work as specified in the Scope of Work.

|  | # Attachments |  |
| --- | --- | --- |

## Cost Proposal Sheet

2020 Statewide Disposal-based Waste Characterization Study, DRR19079

Complete this form and submit the original in accordance with the requirements of this RFP.

Any invoices submitted by contractor will identify line item costs and corresponding task number.

| Contractor/Company Name: |  |
| --- | --- |

| Task # | Personnel Services: (Do not include travel or overhead) estimated # of hrs needed for Contract services multiplied by the individual or position rates per hr. (Include name/position title and hours) |  |  |  | Fringe Benefits (Identify fringe benefit costs citing actual benefits or as a percentage of personal services costs) | Operating Expenses (operating expenses related to the services provided in this agreement, including rent and supplies, as applicable) | Equipment Costs (Include a description of equipment) | Travel Expenses (Include travel expenses and per diem. Rates are set at the rate specified by CalHR for excluded employees) | Overhead (This information must be provided) | Other (any other specific breakdown required to sufficiently explain the budget costs) | Total by Task |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Name/Position | $/Hr | Hrs | Total $ |  |  |  |  |  |  |  |
| Total by Line Item | (Sums of Total $) |  |  |  |  |  |  |  |  |  | GRAND TOTAL |

| Acknowledgement/Authorization |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| The undersigned acknowledges the submittal of this Proposal constitutes an irrevocable offer for a ninety (90) day period for the CalRecycle to award an Agreement. Additional acknowledgement is made of receipt of all competitive documents, including Addenda, relating to this Agreement. The undersigned acknowledges that the Proposer has read all of the requirements set forth in CalRecycle documents and will comply with said provisions. The undersigned hereby authorizes and requests any person, firm, agency, or corporation to furnish any information requested by the CalRecycle in verification of the recitals comprising this Proposal and also hereby authorizes the CalRecycle to contact such persons, firms, etc., in order to obtain information regarding the undersigned. The undersigned acknowledges that there are no potential conflicts of interest, as defined in Public Contract Code (PCC) 10410, 10411, and Government Code (GC) 87100, and this RFP by the submitting firm and/or any subcontractors listed in the Proposal. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| I declare under penalty of perjury that the foregoing is true and correct. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Contractor Name: |  |  |  |  |  |  |  |  | Address: |  |  |  |  |  |  |  |  |  |
| Telephone #: |  |  |  |  |  | City, State, Zip: |  |  |  |  |  |  |  |  |  |  |  |  |
| Name & Title of Authorized Representative: |  |  |  |  |  |  |  |  |  |  |  |  |  | Email: |  |  |  |  |
| Signature of Authorized Representative: |  |  |  |  |  |  |  |  |  |  |  |  | Date Signed: |  |  |  |  |

## RFP (S) Proposal Scoring Sheet

DRR19079 2020 Statewide Disposal-based Waste Characterization Study

| Contractor/Company Name: |  |
| --- | --- |

The Proposer must pass each section separately (Experience and Methodology) with the minimum points indicated for each section.

| EXPERIENCE (Minimum 25 of 36 points to qualify) | SCORE (0-3) | MULTIPLIER | POINTS EARNED (A * B) |
| --- | --- | --- | --- |
|  | A | B | C |
| (1) Project Manager demonstrates experience in and knowledge of implementing a pre-determined study design, leading large, complex, multi-site waste characterization studies, adaptability to unforeseen circumstances, and a proven ability to design and conduct a moisture analysis study. |  | 3 |  |
| (2) All members of the project team demonstrate appropriate background and professional experience in conducting waste characterization studies, including broad experience implementing a pre-determined study design, leading large, complex, multi-site waste characterization studies, and adaptability to unforeseen circumstances. |  | 3 |  |
| (3) All members of the project team demonstrate knowledge of California’s solid waste infrastructure, handling and processing systems, as relevant to the study objectives, including experience working in various parts of the state and with the suite of facilities types and operators found in California. |  | 2 |  |
| (4) All members of the project team demonstrate experience in conducting disposal facility-based and multi-family generator-based studies and designing and conducting moisture analyses, including demonstrated experience sampling from complex sites and facilities as it pertains to the previously mentioned studies. |  | 2 |  |
| (5) All field supervisors and the majority of sorters have field experience for sampling, sorting, health and safety protocols, and coordinating with solid waste facilities and generators for data collection. |  | 2 |  |
| If minimum points attained, move to next section |  |  |  |
| METHODOLOGY (Minimum 80 of 114 points to qualify) | SCORE (0-3) | MULTIPLIER | POINTS EARNED (A * B) |
|  | A | B | C |
| (6) Proposed number of hand-sort samples for PART 1 of the study that will result in representative data and will achieve the goals of the study. The table below shows how the proposed number of hand-sort samples will be scored. # of samples Score <800 0 801-900 1 901-1000 2 >1000 3 |  | 3 |  |
| (7) Proposed a clear justification (e.g. prior experience, literature review, statistical analyses) of how the proposed number of samples, for PART 1, will result in representative data and will achieve the goals of the study. |  | 3 |  |
| (8) Provides an implementation plan describing how the Project Manager will staff the project including roles, responsibilities, and numbers of staff and supervisors, how the Project Manager will train staff, along with a tentative timeline of work, including: start-up tasks, logistical arrangements, training, travel, set-up, sample collection/sorting/analysis (as applicable to each part), data entry, data quality control, and delivery of final data sets to CalRecycle. |  | 3 |  |
| (9) Provides a thorough discussion of all proposed approaches, methodologies, and/or alternatives to achieve the goals of each part including how representative samples for each part will be selected and collected, how adequate sample weights will be achieved, and how random samples will be collected from different trucks/vehicles/bins that are representative of the selected load and sector and does not introduce bias. |  | 3 |  |
| (10) Clearly describes approach and methodology for sampling and sorting, for PARTS 1,2 and 3 of the study, that is efficient, consistent, and will result in the most complete and robust data. |  | 2 |  |
| (11) Clearly describes contingency measures when adaptability for implementing PARTS 1,2 and 3 of the study is required. |  | 2 |  |
| (12) Describes how the project team will accomplish ALL objectives for disposal facilities site coordination and field schedule (PART 1), and how the members of the project team will coordinate logistics and field schedules with disposal facilities, and how the project fieldwork timeline will be maintained. |  | 2 |  |
| (13) Describes how the project team members will accomplish ALL objectives for disposal facilities (PART 1) fieldwork, including sampling and sorting, and discusses how random vehicle selection and how appropriate samples and sample weights will be collected, along with implementing data QA/QC. |  | 2 |  |
| (14) Clearly describes how the project team will accomplish ALL objectives for disposal facilities (PART 1) hand-sorting characterization of collected samples, and specifically address how all members of the project team will accurately characterize the material by hand based on the provided material list. |  | 2 |  |
| (15) A statement demonstrating the Contractors acknowledgment that visual characterization of samples (for PART 1) may be performed only when a sample meets special requirements specified in the Scope of Work provided, and that providing a pre-determined number is not possible. |  | 3 |  |
| (16) Describes how the project team will accomplish ALL objectives for multi-family residences (PART 2) site coordination and field schedule, how the project team will coordinate logistics and field schedules with multi-family residences, and how the project fieldwork timeline will be maintained. |  | 2 |  |
| (17) Describes how the project team will accomplish ALL objectives for multi-family residences (PART 2) fieldwork, including sampling and sorting, and discusses how appropriate samples will be collected, will accurately characterize the material by hand based on the provided material list, and how will data QA/QC be implemented. |  | 2 |  |
| (18) Describes how the project team will accomplish ALL objectives for the moisture analysis (PART 3) field schedule, how members of the project team will coordinate the field schedule for the identified site or off-site location(s) for the analyses and how the project fieldwork timeline will be maintained. |  | 2 |  |
| (19) Describes and specifies how the project team will accomplish the ALL the objectives of the moisture analysis (PART 3) using their proposed methodology and approach. This includes identifying the location(s) where this analysis will be conducted, the logistics of the fieldwork (sample collection, handling, travel and equipment), gathering the appropriate data, and how QA/QC will be implemented. |  | 3 |  |
| (20) Describes how the project team will accomplish ALL objectives for data entry and data QA/QC for PARTS 1, 2 and 3, and specify how all of the characterization data and images will be maintained and follow appropriate QA/QC parameters. |  | 2 |  |
| (21) Describes how the project team will accomplish ALL objectives for submitting field data and summary reports (for PARTS 1,2 and 3) to CalRecycle, and specifies how to ensure timely communication (e.g. weekly and monthly reports) with CalRecycle Contract Manager through the life of the contract. |  | 2 |  |
| SUBTOTAL of Methodology plus Experience Points |  |  |  |
| Cost Points (Max possible = | 66) |  |  |
| TOTAL POINTS (Max possible = | 216) |  |  |

| State of California—Department of General Services, Procurement Division GSPD–05–105 (EST 8/09) |  |  |  |  |  | Solicitation Number DRR19079 |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | BIDDER DECLARATION |  |  |  |  |  |  |  |
| - Prime bidder information (Review attached Bidder Declaration Instructions prior to completion of this form): |  |  |  |  |  |  |  |  |  |
| - Identify current California certification(s) (MB, SB, NVSA, DVBE): or None |  |  |  |  |  |  |  |  |  |
| - Will subcontractors be used for this contract? Yes No (If yes, indicate the distinct element of work your firm will perform in this contract e.g., list the proposed products produced by your firm, state if your firm owns the transportation vehicles that will deliver the products to the State, identify which solicited services your firm will perform, etc.). Use additional sheets, as necessary. |  |  |  |  |  |  |  |  |  |
| - If you are a California certified DVBE: |  |  | (1) Are you a broker or agent? Yes No |  |  |  |  |  |  |
|  |  |  | (2) If the contract includes equipment rental, does your company own at least 51% of the equipment provided in this contract (quantity and value)? Yes No N/A |  |  |  |  |  |  |
| - If no subcontractors will be used, skip to certification below. Otherwise, list all subcontractors for this contract. (Attach additional pages if necessary): |  |  |  |  |  |  |  |  |  |
| Subcontractor Name, Contact Person, Phone Number & Fax Number | Subcontractor Address & Email Address |  |  | CA Certification (MB, SB, DVBE or None) | Work performed or goods provided for this contract |  | Corresponding % of bid price | Good Standing? | 51% Rental? |
| CERTIFICATION: By signing the bid response, I certify under penalty of perjury that the information provided is true and correct |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  | Page _____ of _____ |  |  |

# Bidder Declaration

State of California—Department of General Services, Procurement

Division GSPD–05–105 (EST 8/09) Instructions

BIDDER DECLARATION Instructions

All prime bidders (the firm submitting the bid) must complete the Bidder Declaration.

  - Identify all current certifications issued by the State of California. If the prime bidder has no California certification(s), check the line labeled“None”and proceed to Item #2. If the prime bidder possesses one or more of the following certifications, enter the applicable certification(s) on the line:

    - Microbusiness  (MB)

    - Small Business (SB)

    - Small Business Nonprofit Veteran Service Agency (SB/NVSA)

    - Disabled Veteran Business Enterprise (DVBE)

  - Mark either“Yes”or“No” to identify whether subcontractors will be used for the contract. If the response is “No”, proceed to Item #1.c. If“Yes”, enter on the line the distinct element of work contained in the contract to be performed or the goods to be provided by the prime bidder. Do not include goods or services to be provided by subcontractors.

Bidders certified as MB, SB, SB/NVSA, and/or DVBE must provide a commercially useful function as defined in Military and Veterans Code Section 999(e)(2)(A) for DVBEs and Government Code Section 14837(d)(4)(A) for small/microbusinesses. For questions regarding commercially useful function determinations made in conjunction with certification approval, contact the Department of General Services, Procurement Division, Office of Small Business and DVBE Certification (OSDC), OSDC Certification and Compliance Unit via email at: osdchelp@dgs.ca.gov

Bids must propose that certified bidders provide a commercially useful function for the resulting contract or the bid will be deemed non-responsive and rejected by the State. For questions regarding the solicitation, contact the procurement official identified in the solicitation.

Note:A subcontractor is any person, firm, corporation, or organization contracting to perform part of the prime’s contract.

  - This item is only to be completed by businesses certified by California as a DVBE.

- Declare whether the prime bidder is a broker or agent by marking either“Yes”or“No”. The Military and Veterans Code Section 999.2 (b) defines“broker”or“agent”as a certified DVBE contractor or subcontractor that does not have title, possession, control, and risk of loss of materials, supplies, services, or equipment provided to an awarding department, unless one or more of the disabled veteran owners has at least 51-percent ownership of the quantity and value of the materials, supplies, services, and of each piece of equipment provided under the contract.

- If bidding rental equipment, mark either“Yes” or“No”to identify if the prime bidder owns at least 51% of the equipment provided (quantity and value). If not bidding rental equipment, mark“N/A”for“not applicable.”

- If no subcontractors are proposed, do not complete the table. Read the certification at the bottom of the form and complete“Page	of	”on the form.

If subcontractors will be used, complete the table listing all subcontractors. If necessary, attach additional pages and complete the“Page	of	”accordingly.

2. (continued) Column Labels

Subcontractor Name, Contact Person, Phone Number & Fax Number—List each element for all subcontractors.

Subcontractor Address & Email Address—Enter the address and if available, an Email address.

CA Certification (MB, SB, DVBE or None)—If the subcontractor possesses a current State of California certification(s), verify on the OSDC website (www.pd.dgs.ca.gov/smbus) that it is still valid and list all current certifications here. Otherwise, enter“None”. [Note: A SB/NVSA should not be participating as a subcontractor]

Work performed or goods provided for this contract—Identify the distinct element of work contained in the contract to be performed or the goods to be provided by each subcontractor. Certified subcontractors must provide a commercially useful function for the contract. (See paragraph 1.b above for code citations regarding the definition of commercially useful function.) If a certified subcontractor is further subcontracting a greater portion of the work or goods provided for the resulting contract than would be expected by normal industry practices, attach a separate sheet of paper explaining the situation.

Corresponding % of bid price—Enter the corresponding percentage of the total bid price for the goods and/or services to be provided by each subcontractor. Do not enter a dollar amount.

Good Standing?—Provide a response for each subcontractor listed. Enter either“Yes”or“No”to indicate that the prime bidder has verified that the subcontractor(s) is in good standing for all of the following:

  - Possesses valid license(s) for any license(s) or permits required by the solicitation or by law

  - If a corporation, the company is qualified to do business in California and designated by the State of California Secretary of State to be in good standing

  - Possesses valid State of California certification(s) if claiming MB, SB, and/or DVBE status

  - Is not listed on the OSDC website as ineligible to transact business with the State

51% Rental?—This pertains to the applicability of rental equipment. Based on the following parameters, enter either“N/A” (not applicable),“Yes”or“No”for each subcontractor listed.

Enter“N/A”if the:

  - Subcontractor is NOT a DVBE (regardless of whether or not rental equipment is provided by the subcontractor) or

  - Subcontractor is NOT providing rental equipment (regardless of whether or not subcontractor is a DVBE)

Enter“Yes”if the subcontractor is a California certified DVBE providing rental equipment and the subcontractor owns at least 51% of the rental equipment (quantity and value) it will be providing for the contract.

Enter“No”if the subcontractor is a California certified DVBE providing rental equipment but the subcontractor does NOT own at least 51% of the rental equipment (quantity and value) it will be providing.

Read the certification at the bottom of the page and complete the “Page	of	” accordingly.

## Small Business (SB) and Disabled Veteran Business Enterprise (DVBE) Subcontractor Payment Certification

As Contractor of record for the Department of Resources Recycling and Recovery, Contract number ___________________, I certify, in accordance with Government Code 14841 and Military and Veteran Code § 999.5, that pursuant to the terms and conditions of the contract, all payments have been made to the SB or DVBE firm(s) listed below for commodities or services rendered as the SB or DVBE subcontractor(s) of record.   I understand certification must be made to the Department of Resources Recycling and Recovery within 60 days of receiving final payment under this Agreement.   I further understand and acknowledge that falsification of this Certification may result in the imposition of civil or criminal penalties for not less than $2,500 or more than $25,000 for each violation.

Please copy this form to include as many SB or DVBE firms as necessary.  Authorized signatures and information are required on each separately submitted form. Return to: Department of Resources Recycling and Recovery, Contracts Unit- MS 19-A, Attn: SB/DVBE Advocate, P.O. Box 4025, Sacramento, CA 95812-4025

SB/MB/DVBE SUBCONTRACTOR INFORMATION

| Contract Firm Name |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Name of Firm Representative |  |  |  |  |  |  |  |  |  |  |  |  |
| Title |  |  |  |  |  |  |  |  |  |  |  |  |
| Phone: |  |  |  |  |  | Fax: |  |  |  |  |  |  |
| Firm Address |  |  | Street: |  |  |  |  |  |  |  |  |  |
| City: |  |  |  |  |  |  |  |  | State: |  | Zip: |  |
| Contract Number |  |  |  |  |  |  |  |  |  |  |  |  |
| Total Amount Received Under this Contract |  |  |  |  | $ Date Final Payment Received: / / |  |  |  |  |  |  |  |

SB/DVBE SUBCONTRACTOR INFORMATION

| SB/DVBE Subcontractor |  | Street Address City State Zip |  |  | Amount Paid | Participation Achieved |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  | % |
|  |  |  |  |  |  | % |
|  |  |  |  |  |  | % |
|  |  |  |  |  |  | % |
| Printed Name |  |  | Signature: |  |  |  |
| Title: |  |  | Report Date: |  |  |  |

THIS PAGE INTENTIONALLY LEFT BLANK

## Iran Contracting Act

Public Contract Code Sections 2202-2208

Prior to bidding on, submitting a proposal or executing a contract or renewal for a State of California contract for goods or services of $1,000,000 or more, a vendor must either:  a) certify it is not on the current list of persons engaged in investment activities in Iran created by the California Department of General Services (“DGS”) pursuant to Public Contract Code section 2203(b) and is not a financial institution extending twenty million dollars ($20,000,000) or more in credit to another person, for 45 days or more, if that other person will use the credit to provide goods or services in the energy sector in Iran and is identified on the current list of persons engaged in investment activities in Iran created by DGS; or b) demonstrate it has been exempted from the certification requirement for that solicitation or contract pursuant to Public Contract Code section 2203(c) or (d).

To comply with this requirement, please insert your vendor or financial institution name and Federal ID Number (if available) and complete one of the options below. Please note: California law establishes penalties for providing false certifications, including civil penalties equal to the greater of $250,000 or twice the amount of the contract for which the false certification was made; contract termination; and three-year ineligibility to bid on contracts. (Public Contract Code section 2205.)

OPTION #1 – CERTIFICATION

I, the official named below, certify I am duly authorized to execute this certification on behalf of the vendor/financial institution identified below, and the vendor/financial institution identified below is not on the current list of persons engaged in investment activities in Iran created by DGS and is not a financial institution extending twenty million dollars ($20,000,000) or more in credit to another person/vendor, for 45 days or more, if that other person/vendor will use the credit to provide goods or services in the energy sector in Iran and is identified on the current list of persons engaged in investment activities in Iran created by DGS.

| Vendor Name/Financial Institution (Printed) |  | Federal ID Number (or n/a) |
| --- | --- | --- |
| By (Authorized Signature) |  |  |
| Printed Name and Title of Person Signing |  |  |
| Date Executed | Executed in |  |

OPTION #2 – EXEMPTION

Pursuant to Public Contract Code sections 2203(c) and (d), a public entity may permit a vendor/financial institution engaged in investment activities in Iran, on a case-by-case basis, to be eligible for, or to bid on, submit a proposal for, or enters into or renews, a contract for goods and services.

If you have obtained an exemption from the certification requirement under the Iran Contracting Act, please fill out the information below, and attach documentation demonstrating the exemption approval.

| Vendor Name/Financial Institution (Printed) |  | Federal ID Number (or n/a) |
| --- | --- | --- |
| By (Authorized Signature) |  |  |
| Printed Name and Title of Person Signing | Date Executed |  |

## Darfur Contracting Act

Pursuant to Public Contract Code section 10478, if a bidder or Proposer currently or within the previous three years has had business activities or other operations outside of the United States, it must certify that it is not a “scrutinized” company as defined in Public Contract Code section 10476.

Therefore, to be eligible to submit a bid or Proposal, please complete only one of the following three paragraphs (via initials for Paragraph # 1 or Paragraph # 2, or via initials and certification for Paragraph # 3):

1.	_____		We do not currently have, or we have not had within the previous

Initials	three years, business activities or other operations outside of the United States.

OR

2.	_____		We are a scrutinized company as defined in Public Contract Code

Initials	section 10476, but we have received written permission from the Department of General Services (DGS) to submit a bid or Proposal pursuant to Public Contract Code section 10477(b).  A copy of the written permission from DGS is included with our bid or Proposal.

OR

3.	_____		We currently have, or we have had within the previous three years,

Initials	business activities or other operations outside of the United States,

+ certification	but we certify below that we are not a scrutinized company

below	as defined in Public Contract Code section 10476.

CERTIFICATION For # 3.

I, the official named below, CERTIFY UNDER PENALTY OF PERJURY that I am duly authorized to legally bind the prospective Proposer/bidder to the clause listed above in # 3.  This certification is made under the laws of the State of California.

| Proposer/Bidder Firm Name (Printed) |  | Federal ID Number |
| --- | --- | --- |
| By (Authorized Signature) |  |  |
| Printed Name and Title of Person Signing |  |  |
| Date Executed | Executed in the County and State of |  |

YOUR BID OR PROPOSAL WILL BE DISQUALIFIED UNLESS YOUR BID OR PROPOSAL INCLUDES THIS FORM WITH EITHER PARAGRAPH # 1 OR # 2 INITIALED OR PARAGRAPH # 3 INITIALED AND CERTIFIED.

## California Civil Rights Laws Certification

Pursuant to Public Contract Code section 2010, if a bidder or proposer executes or renews a contract over $100,000 on or after January 1, 2017, the bidder or proposer hereby certifies compliance with the following:

1.  CALIFORNIA CIVIL RIGHTS LAWS:  For contracts over $100,000 executed or renewed after January 1, 2017, the contractor certifies compliance with the Unruh Civil Rights Act (Section 51 of the Civil Code) and the Fair Employment and Housing Act (Section 12960 of the Government Code); and

2.  EMPLOYER DISCRIMINATORY POLICIES: For contracts over $100,000 executed or renewed after January 1, 2017, if a Contractor has an internal policy against a sovereign nation or peoples recognized by the United States government, the Contractor certifies that such policies are not used in violation of the Unruh Civil Rights Act (Section 51 of the Civil Code) or the Fair Employment and Housing Act (Section 12960 of the Government Code).

CERTIFICATION

| I, the official named below, certify under penalty of perjury under the laws of the State of California that the foregoing is true and correct. Proposer/Bidder Firm Name (Printed) |  | Federal ID Number |
| --- | --- | --- |
| By (Authorized Signature) |  |  |
| Printed Name and Title of Person Signing |  |  |
| Date Executed | Executed in the County and State of |  |

## Contractor Status Form

| Contractor’s Name: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | County: |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Address: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Phone Number: |  |  |  |  |  |  |  |  |  |  |  |  |  | Fax Number: |  |  |  |  |  |  |  |  |  |
| Federal Employer Identification Number: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| STATUS OF CONTRACTOR PROPOSING TO DO BUSINESS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Individual Limited Partnership General Partnership Corporation Other |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| If Individual or sole proprietorship, state the true name of sole proprietor: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| If a Limited or General Partnership, list each partner and state their true name and interest in the partnership: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| If a Corporation, state place and date of incorporation: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| President: |  |  |  |  |  |  |  |  |  |  |  |  | Vice President: |  |  |  |  |  |  |  |  |
| Secretary: |  |  |  |  |  |  |  |  |  |  |  | Treasurer: |  |  |  |  |  |  |  |  |
| Other Officer: |  |  |  |  |  |  |  |  |  |  | Other Officer: |  |  |  |  |  |  |  |  |  |  |
| Provide explanation if claiming Other: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| SMALL BUSINESS PREFERENCE |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Are you claiming preference for small business? |  |  |  |  |  |  | YES – Attach approval letter from Office of Small Business Certification and Resources NO |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Are you claiming preference for DVBE? |  |  |  |  |  |  | YES – Attach approval letter from Office of Small Business Certification and Resources NO |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| NOTE: THIS FORM MUST BE COMPLETED OR YOUR PROPOSAL WILL BE REJECTED |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

## Client References

List at least three (3) client references that can attest to the Bidder’s qualifications to fulfill the requirements of the Scope of Work.  List the most recent first.  Client references must also be provided for any subcontractors identified in the Bidder’s response.  Duplicate and attach additional pages as necessary.

| BIDDER / SUBCONTRACTOR’S NAME: |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| REFERENCE 1 |  |  |  |  |  |
| Name of Firm |  |  |  |  |  |
| Street Address | City |  |  | State | Zip Code |
| Contact Person |  | Telephone Number |  |  |  |
| Dates of Service |  |  | Cost of Service |  |  |
| Brief Description of Service Provided |  |  |  |  |  |
| REFERENCE 2 |  |  |  |  |  |
| Name of Firm |  |  |  |  |  |
| Street Address | City |  |  | State | Zip Code |
| Contact Person |  | Telephone Number |  |  |  |
| Dates of Service |  |  | Cost of Service |  |  |
| Brief Description of Service Provided |  |  |  |  |  |
| REFERENCE 3 |  |  |  |  |  |
| Name of Firm |  |  |  |  |  |
| Street Address | City |  |  | State | Zip Code |
| Contact Person |  | Telephone Number |  |  |  |
| Dates of Service |  |  | Cost of Service |  |  |
| Brief Description of Service Provided |  |  |  |  |  |
| If three references cannot be provided, explain why: |  |  |  |  |  |

## Sample Agreement

| STATE OF CALIFORNIA - DEPARTMENT OF GENERAL SERVICES |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| STANDARD AGREEMENT |  |  | AGREEMENT NUMBER |  | PURCHASING AUTHORITY NUMBER (If Applicable) |  |  |  |
| STD 213 (Rev. 03/2019) |  |  | DRR19079 |  |  |  |  |  |
| 1. This Agreement is entered into between the Contracting Agency and the Contractor named below: |  |  |  |  |  |  |  |  |
| CONTRACTING AGENCY NAME |  |  |  |  |  |  |  |  |
| Department of Resources Recycling and Recovery (CalRecycle) |  |  |  |  |  |  |  |  |
| CONTRACTOR NAME |  |  |  |  |  |  |  |  |
| TBD |  |  |  |  |  |  |  |  |
| 2. The term of this Agreement is: |  |  |  |  |  |  |  |  |
| START DATE |  |  |  |  |  |  |  |  |
| June 1, 2020 or Upon DGS Approval, whichever is later |  |  |  |  |  |  |  |  |
| THROUGH END DATE |  |  |  |  |  |  |  |  |
| September 1, 2021 |  |  |  |  |  |  |  |  |
| 3. The maximum amount of this Agreement is: |  |  |  |  |  |  |  |  |
| ( dollars and zero cents) |  |  |  |  |  |  |  |  |
| 4. The parties agree to comply with the terms and conditions of the following exhibits, which are by this reference made a part of the Agreement. |  |  |  |  |  |  |  |  |
| EXHIBITS |  | TITLE |  |  |  |  | PAGES |  |
|  | Exhibit A | Scope of Work |  |  |  |  |  |  |
|  | Exhibit B | Budget Detail and Payment Provisions |  |  |  |  |  |  |
|  | Exhibit C* | General Terms and Conditions GTC 04/2017 |  |  |  |  |  |  |
| Exhibit D |  | Special Terms and Conditions |  |  |  |  |  |  |
|  |  | Attachment 1 Recycled Content Certification |  |  |  |  |  |  |
| Exhibit E** |  | from company name in response to DRR19079 |  |  |  |  |  |  |
|  |  | Items shown with double Asterisks (**) are hereby incorporated by reference and made part of this agreement as if attached hereto. |  |  |  |  |  |  |
| Items shown with an asterisk (*), are hereby incorporated by reference and made part of this agreement as if attached hereto. These documents can be viewed at https://www.dgs.ca.gov/OLS/Resources |  |  |  |  |  |  |  |  |
| IN WITNESS WHEREOF, THIS AGREEMENT HAS BEEN EXECUTED BY THE PARTIES HERETO. |  |  |  |  |  |  |  |  |
| CONTRACTOR |  |  |  |  |  |  |  |  |
| CONTRACTOR NAME (if other than an individual, state whether a corporation, partnership, etc.) |  |  |  |  |  |  |  |  |
| CONTRACTOR BUSINESS ADDRESS |  |  |  | CITY |  | STATE |  | ZIP |  |
| PRINTED NAME OF PERSON SIGNING |  |  |  | TITLE |  |  |  |  |  |
| CONTRACTOR AUTHORIZED SIGNATURE |  |  |  | DATE SIGNED |  |  |  |  |  |
| STATE OF CALIFORNIA |  |  |  |  |  |  |  |  |  |
| CONTRACTING AGENCY NAME |  |  |  |  |  |  |  |  |  |
| Department of Resources Recycling and Recovery |  |  |  |  |  |  |  |  |  |
| CONTRACTING AGENCY ADDRESS |  |  |  | CITY |  | STATE |  | ZIP |  |
| 1001 “I” Street |  |  |  | Sacramento |  | CA |  | 95814 |  |
| PRINTED NAME OF PERSON SIGNING |  |  |  | TITLE |  |  |  |  |  |
| Noah Valadez |  |  |  | Adminstrative Services Branch Chief |  |  |  |  |  |
| CONTRACTING AGENCY AUTHORIZED SIGNATURE |  |  |  | DATE SIGNED |  |  |  |  |  |

| STATE OF CALIFORNIA - DEPARTMENT OF GENERAL SERVICES |  |  |  |
| --- | --- | --- | --- |
| STANDARD AGREEMENT | AGREEMENT NUMBER |  | PURCHASING AUTHORITY NUMBER (If Applicable) |
| STD 213 (Rev. 03/2019) | DRR19079 |  |  |
| CALIFORNIA DEPARTMENT OF GENERAL SERVICES APPROVAL |  | EXEMPTION (If Applicable) |  |

EXHIBIT A

SCOPE OF WORK

- TBD (Contractor) agrees to provide the Department of Resources Recycling and Recovery (CalRecycle), with Disposal based waste characterization services as described herein.

- The Project Coordinators during the term of this Agreement will be:

| CalRecycle Contract Manager |  |  | TBD |  |
| --- | --- | --- | --- | --- |
| Name: | Kamrun Zargar |  | Name: | TBD |
| Phone: | (916) 341-6548 |  | Phone: | ( ) - |
| Email: | Kamrun.zargar@calrecycle.ca.gov |  | Email: | @ |
| Direct all Agreement inquiries to: |  |  |  |  |
| CalRecycle Contract Analyst |  |  | TBD |  |
| Contracts Unit |  |  |  |  |
| Attention: |  | Melissa Mojonnier | Attention: | TBD |
| Address: |  | 1001 I St., MS 19-A | Address: |  |
|  |  | Sacramento, CA 95814 |  |  |
| Phone: |  | (916) 341-6048 | Phone: | ( ) - |
| Email: |  | melissa.mojonnier@calrecycle.ca.gov | Email: | @ |

- Work To Be Performed

The Contractor shall conduct waste characterization research, consisting of three parts to be conducted concurrently.  They are:

- Part 1. A Disposal Facility-Based Waste Characterization Study to determine the statewide waste disposal composition.  The Contractor shall propose and justify the quantity of samples to be taken to accurately represent California’s complex waste stream.

- Part 2. A Multi-Family Generator-Based Waste Characterization Study to determine the disposed waste composition and disposal rate for multi-family residences; and

- Part 3. A Moisture Analysis Study to analyze moisture absorbed by specific paper types collected for Part 1 of the study. The Contractor shall propose the methodology and quantity of samples and justify how the quantity of samples will be sufficient to meet the goals of the study, while remaining within the specified budget of $37,000.00.

- Tasks Identified

Task 1 – Initial Meeting to refine the Proposed Study Design (Work Plan)

- Within 10 calendar days after Contract approval, the Contractor shall meet in-person with CalRecycle’s Contract Manager (Contract Manager) at the CalRecycle office in Sacramento to identify logistical details and fine-tune the proposed methodologies, including:

  - The timeline and logistics for sampling collection and analysis.

  - The potential sampling sites (based on recruitment success) and sample distributions per site. The Contract Manager will provide an updated list of sampling sites and re-distribute the quantity of samples at each site if necessary.

- For PART 3-the Moisture Analysis Study, this includes the proposed method.

  - The specific materials to be used to characterize the waste samples.

- For PART 3-the Moisture Analysis Study, this refers to the specific material list to be included in this part of the study.

- Within 15 calendar days of meeting, the Contractor shall submit any proposed revisions to the plan based on the meeting.

- The Contract Manager will respond within 15 calendar days with any final edits to the proposed revisions.

- The Contractor shall make required changes, if any, and submit them to the Contract Manager within 15 calendar days of receiving the edits. Work shall not begin on Tasks 2 and 3 without the Contract Manager’s written approval confirming that any proposed revisions or required changes have been made and are satisfactory to the Contract Manager.

Task 2 – Coordinate with Facilities and Determine Field Schedule

- The Contractor shall promptly establish contact and confirm logistics (e.g. sample collection date(s), and health and safety requirements). For PART 1- Disposal Facility-Based Waste Characterization Study, the Contractor shall also confirm the availability of a loader/skid steer loader and an equipment operator/driver).

- The Contractor shall coordinate with the Contract Manager to minimize impacts to the field schedule and to request replacement sampling sites if needed.

- The Contractor shall, when scheduling sampling activities at sites, ensure accurate and representative sampling at each site by including information on variations in site operations, waste flows, on-site processing/handling and other relevant information as determined by the Contractor.  For PART 2- Multi-Family Generator-Based Waste Characterization Study, waste storage, on-site processing/handling, and other relevant information as determined by the Contractor.

- The Contractor shall provide a tentative schedule for sampling site order for Parts 1 and 2 at least 20 calendar days before each sampling period begins.

- The Contractor shall provide an overall schedule for fieldwork, travel, site set-up and sorting days. For PART 3- Moisture Analysis Study, the Contractor shall provide an overall schedule for sample collection, handling, transport and analysis at least 20 calendar days before each sampling period, including the sorting schedule for Part 1.

- The Contractor shall provide a description of start-up tasks, and confirmation of the number of samples at each site and from each source.

- For PART 2- Multi-Family Generator-Based Waste Characterization Study, the Contractor shall confirm the number of multi-family residences to be sampled and the nodes to be used for sorting (if applicable).

- For PART 3- Moisture Analysis Study, The Contractor shall be responsible for the adhering to the agreed upon coordination schedule and logistical arrangements with each site and/or off-site location used for the analyses.

Task 3 – Perform Fieldwork-Field Sampling and Sorting

- Task 3 Fieldwork-Field Sampling and Sorting for ALL THREE PARTS of the study

- SAMPLING PERIODS: The Contractor shall conduct sampling, for all three parts of the study, during two, 4-month sampling periods, no less than two months apart. CalRecycle anticipates that the two seasons will span calendar year 2020 and early 2021.

- HEALTH AND SAFETY: The Contractor shall have a health and safety plan, implement health and safety measures, conduct training and monitor effectiveness. The Contractor shall comply with all local, state, and federal health and safety codes, regulations, and laws.

- FIELD OBSERVATIONS: The Contractor shall accommodate observation by the Contract Manager, other CalRecycle staff, and possibly other interested parties, at the sampling sites.

- Task 3: For PART 1- Disposal Facility-Based Waste Characterization Study

- SAMPLE COLLECTION: The Contractor shall collect samples of waste from selected vehicles at sampling sites. If a transfer station is substituted for a landfill, the Contractor shall collect samples only of materials destined for disposal after any processing.

- EQUIPMENT: The Contractor shall provide all equipment needed for fieldwork, including health and safety equipment. During the initial site recruitment, CalRecycle will determine if a loader/skid steer loader and an equipment operator/driver are available on-site. If a loader/ skid steer loader or similar equipment and an equipment operator/driver are not available, the Contractor shall arrange to rent a loader/ skid steer loader or similar equipment and provide a certified/trained operator/driver.

- VEHICLE SELECTION: The Contractor shall select vehicles from which to collect samples to comply with the sample source sector allocations provided by the Contract Manager. The source sector allocations shall specify the number of samples to be taken from vehicles delivering single-family residential route loads, commercial/multi-family route loads, transfer truck loads, and self-haul loads. The Contractor shall select vehicles from which to sample in a manner that is representative of the loads delivered to the sampling site and does not introduce bias.

- VEHICLE DATA COLLECTION: For each load sampled at a facility, the Contractor shall obtain and record:

- A unique identification (ID) number for each sample taken.

- The date of collection.

- The name of the sampling site.

- Local weather conditions.

- Any notes or unusual circumstances.

- The jurisdiction (city or unincorporated county area) and county of origin.

- Vehicle type and the source sector including (1) single-family residential route load, (2) commercial/multi-family route load, (3) transfer truck loads, and (4) self-haul loads.

- For each commercial/multi-family load, the estimated percentage of multi-family waste.

- For each self-haul load, the subsector of origin: (1) residential, (2) general commercial/industrial, (3) construction and demolition, (4) roofing, (5) landscaper, (6) disaster debris, (7) designated waste, or (8) other (specify subsector).

- For each transfer truck, the total weight delivered, the name of the originating facility, the number of samples collected from the load, and any other pertinent information.

- For each route-truck and self-haul vehicle, load weight, specifically the exact weight of the load as per the scale before entering the facility minus the unladen vehicle weight. In the absence of a scale, the Contractor shall use the methodology proposed in the RFP to estimate the load weight.

- SAMPLE WEIGHT: The Contractor shall collect samples that weigh at least 200 pounds for each load sampled from all vehicle types. The Contract Manager shall reject each underweight sample and the Contractor shall substitute underweight samples with additional samples that meet the weight requirement. If a self-haul load weighs less than 200 pounds (as do many passenger carloads), the Contractor shall collect additional loads from the same class of vehicle and subsector of origin until the total weight exceeds 200 pounds. After combining these subsamples, the Contractor shall handle and count the aggregate as one sample. If submitted sample data is below the agreed upon weight, the samples shall not be accepted as fulfilling the terms of the contract, and the Contract Manager will have the discretion to withhold the payment for each underweight sample.

- NUMBER OF SAMPLES PER LOAD: The Contractor shall collect samples in a manner that is representative of the selected load and does not introduce bias.

- The Contractor shall collect only one sample from each selected route truck or self-haul vehicle.

- For each selected transfer truck, the Contractor shall collect two samples, each composed of three subsamples from distinct locations in the load.

- If a transfer/processor is substituted for a landfill as a sampling site, the Contractor shall collect samples from route trucks and self-haul vehicles, and distinct samples from the tipping floor representative of waste outflows destined for disposal.

- CHARACTERIZING THE MATERIAL:  After a load is selected, the Contractor shall determine if hand-sorting is impractical and/or unsafe.

- HAND-SORTING:

- If hand-sorting is acceptable:

- the Contractor shall hand-sort samples of solid waste into individual material types listed in Table 2 of the Appendix.

- The Contractor shall sort all materials with a particle size of 2 inches or larger. If it is practical to sort distinct, easily identifiable and sortable objects (such as plastic bottle caps) that are smaller than 2 inches, the Contractor shall do so. For materials smaller than 2 inches that are not distinct, easily identifiable and sortable objects, the Contactor shall classify this material as “mixed residue.”

- For material that is difficult to sort due to adhesion, wetness, or partial decomposition, the Contractor shall make their best judgement to categorize the material. If it is practical to separate joined materials (such as a zip lock bag with metal screws in it), the Contractor shall do so.

- If hand-sorting has been determined to be impractical and/or unsafe:

- The Contractor shall document the reasons that hand-sorting is not safe or practical.

- The Contractor shall be permitted to conduct visual characterization only on loads that:

- Are composed of no more than ten different, clearly distinct material types,

- Do not contain bagged materials, and

- Do not contain heterogeneous mixtures of materials.

- The Contractor shall visually characterize the entire load, not just a 200-pound sample.

- The Contractor shall characterize the material into the individual material types listen in Table 2 of the Appendix.

- The Contractor shall have two staff independently conduct the visual characterization. These staff shall then discuss and agree on a final characterization result that gives the percentage of each material in the entire load.

- The Contractor shall use volume-to-weight conversion factors to estimate the individual weights of each material type identified in the visual characterization. The Contractor shall provide the conversion factors to the Contract Manager for review and approval prior to conducting visual characterizations.

- The Contractor shall clearly identify each sample that is visually characterized to distinguish it from hand-sort data.

- The Contractor shall provide a narrative description for why a visual characterization was appropriate for each specific load.

- The Contract Manager will reject samples that do not meet the criteria for visual characterization as identified above and the Contractor shall substitute the rejected samples with additional samples that do meet the criteria. If the substituted samples do not meet the above criteria, the Contract Manager will have the discretion to withhold payment for each rejected sample, not to exceed the marginal sample cost for this task.

- IMPACT OF VISUAL CHARACTERIZATIONS ON OVERALL SAMPLE NUMBERS:

- When used as described above, a visual characterization may substitute for a hand-sort. However, visual characterizations are substantially faster and cheaper than hand-sorts. The Contractor shall substitute a hand-sort sample with visual characterizations, but there shall be five visual characterizations assessed for each hand-sort that is substituted/removed. The Contractor shall evaluate each sample-by-sample case whether a load is appropriate for hand-sort or visual characterization.

- If the Contractor does not conform to the requirements for visual characterizations, the Contract Manager may place a cap on the number of visual characterizations or prohibit additional visual characterization.

- DIGITAL IMAGES: The Contractor shall provide a photography plan that will address the specifications described below:

- When taking digital images of each load/sample, the Contractor shall place a placard on, adjacent, or near the load/sample clearly identifying the unique load/sample ID number, location, and date.

- The Contractor shall name each digital image file so it correlates to the unique load/sample ID.

- The Contractor shall provide images with a minimum resolution of 12-megapixels. If the digital image requirements are not met as previously described, such as, but not limited to, blurry images, the load is not clearly identified, and/or improper file naming, the digital images shall not be accepted as fulfilling the contract, and the Contract Manager will have the discretion to withhold payment for each mishandled sample.

- SAMPLE SELECTION IMAGES:

- For each selected route truck, self-haul vehicle and transfer truck, the Contractor shall take image(s) that clearly allow for visualization of the entire waste load, after being dumped by the truck/vehicle and before removal of waste sample.

- CHARACTERIZATION IMAGES:

- For hand-sorts, the Contractor shall meet the following specific photography requirements in their plan:

- At least 2 images taken from different angles of the waste sample that clearly shows the entire content of the waste sample. If needed, the Contractor shall break open garbage bags and/or spread out the sample to obtain adequate digital images. If digital images are submitted and garbage bags are not broken open and/or the sample is not spread out to adequately show the contents of the sample, the Contract Manager will have the discretion to withhold payment for each unsatisfactory digital image.

- For visual characterizations, the Contractor shall take the following digital images of the waste load to demonstrate the visual characterization criteria are met:

          - The Contractor shall take image(s) that clearly allow for visualization of the entire waste load, after being dumped by the truck/vehicle and before removal of waste sample. This is critical for allowing the Contract Manager to assess if the selected load qualified for visual characterization.

          - At least 2 images of the waste load that clearly shows the entire content of the load. If needed, the Contractor shall break open garbage bags and/or spread out the load to obtain adequate digital images. If digital images are submitted and garbage bags are not broken open and/or the load is not spread out to adequately show the contents of the load, the Contract Manager will have the discretion to withhold payment for each unsatisfactory digital image. If an image is not in focus/clear or lacks to show the entire content of the load, then it cannot be confirmed if the load has qualified for a visual characterization. In this case, the sample cannot be counted, and the Contractor must re-sample accordingly. The Contract Manager will have 7 calendar days to review the previous weeks visual characterization pictures, if any, and determine if any samples need to be re-collected. If the Contractor has left the area and re-sampling at the same site is no longer logistically feasible, the Contract Manager, in consultation with the Contractor, will decide how to re-allocate that sample.

- SORTED MATERIAL TYPES IMAGES: For each remainder composite category and mixed residue (a total of 10 material types), the Contractor shall take a digital image showing the individual items in sorted material types (i.e., a picture of the contents spread out on the ground) from 10 distinct samples each. The Contractor shall take digital images on different sample days.

- Task 3 Fieldwork-Field Sampling and Sorting for PART 2- Multi-Family Generator-Based Waste Characterization Study

- SAMPLE COLLECTION: The Contractor shall collect multi-family samples at the site of generation (e.g. apartment buildings) from waste destined for disposal.

- EQUIPMENT: The Contractor shall provide all equipment needed for fieldwork, including health and safety equipment

- MULTIPLE BINS: If there are multiple bins, the Contractor shall take subsamples from the bins to be representative of waste on-site and combine the subsamples into one representative sample.

- SAMPLE WEIGHT: The Contractor shall collect samples that weigh at least 200 pounds. If a multi-family residence has less than 200 pounds of waste to sample, the Contractor shall collect additional waste on subsequent days until the total weight exceeds 200 pounds. After combining these subsamples, the Contractor shall handle and count the aggregate as one sample. The Contract Manager shall reject each underweight sample and the Contractor shall substitute additional samples that meet the weight requirement. If submitted sample data is below the agreed upon weight, the samples shall not be accepted as fulfilling the contract, and the Contract Manager shall have the discretion to withhold payment for each underweight sample.

- SAMPLE VOLUME: The Contractor shall determine the combined bin volume of the waste bins on-site and estimate total volume of all on-site waste at the time of collection. The Contractor shall estimate the in-place sample volume at the time of collection.

- CHARACTERIZING THE MATERIAL: The Contractor shall hand-sort all multi-family samples.

- The Contractor shall hand-sort samples of solid waste into individual material types listen in Table 2 of the Appendix.

- The Contractor shall sort all materials with a particle size of 2 inches or larger. If it is practical to sort distinct, easily identifiable objects (such as plastic bottle caps) that are smaller than 2 inches, the Contractor shall do so. For materials smaller than 2 inches that are not distinct, easily identifiable and sortable objects, the Contactor shall classify this material as “mixed residue.”

- For material that is difficult-to-sort due to adhesion, wetness, or partial decomposition, the Contractor shall make their best judgement to categorize the material. If it is practical to separate joined materials (such as a zip lock bag with metal screws in it), the Contractor shall do so.

- DIGITAL IMAGES: The Contractor shall provide a photography plan that will address the specifications described below:

  - When taking a digital image of each bin/sample, the Contractor shall place a placard on, adjacent, or near the bin/sample clearly identifying the unique sample ID number, location, and date. The Contractor shall name each digital image file so it correlates to the unique bin/sample ID. The Contractor shall provide images with a minimum resolution of 12-megapixels. If the digital image requirements are not met as previously described, such as, but not limited to, blurry images, the load is not clearly identified, and/or improper file naming, the digital images shall not be accepted as fulfilling the contract, and the Contract Manager shall have the discretion to withhold payment for each mishandled sample.

  - For each multi-family sample, the Contractor shall take:

    - Image(s) that clearly allow for visualization of the contents in the entire waste bin, before removal of waste sample.

    - At least 2 images of the waste sample that clearly shows the content of the waste sample. If needed, the Contractor shall break open garbage bags and/or spread out the sample to obtain adequate digital images. If digital images are submitted and garbage bags are not broken open and/or the sample is not spread out to adequately show the contents of the sample, the Contract Manager will have the discretion to withhold payment for each unsatisfactory digital image.

- Task 3 Fieldwork-Field Sampling and Sorting for PART 3- Moisture Analysis Study of Paper Types

- SAMPLE COLLECTION: The Contractor shall collect the selected materials from the sorted materials after they have been weighed and recorded in Part 1. The Contractor shall create one composite sample for each selected material type set from all hand-sorted material on each specified sampling day as agreed upon by the Contract Manager and the Contractor.

- EQUIPMENT: The Contractor shall provide all equipment needed for fieldwork, including health and safety equipment.

- SAMPLING PERIODS: The Contractor shall use the same two sampling periods as in Part 1.

- SAMPLING DAYS: The Contractor shall gather the material needed for the Moisture Analysis Study on the number of sampling days discussed, selected and agreed upon by the Contract Manager and the Contractor.

- SELECTED MATERIALS: The Contractor shall gather the selected materials listed in Table 3 of the Appendix.

- SAMPLE WEIGHTS: The Contractor shall aggregate material by type until:

    - The composite sample for the material type weighs at least 20 pounds, or

    - The end of the sampling day is reached regardless of if the composite sample weighs less than 20 pounds. For example, the composite sample of corrugated cardboard is achieved by aggregating sorted corrugated cardboard from PART 1 of the study on a given sort day by either collecting up to 20 pounds of the material or by reaching the end of the day, whichever occurs first.

- SAMPLE HANDLING AND STORAGE: The Contractor shall start the Moisture Analysis Study within one week of the samples being collected to prevent further sample changes and degradation.

- SAMPLE TRACKING: The Contractor shall assign a new unique sample ID number to each composite sample and associate it with the corresponding unique original sample ID numbers and sectors that contributed to the composite sample, and composite sample weight.

- SAMPLE ANALYSIS AND STANDARDS:

  - Measure Moisture Absorption by Various Paper Types

    - The Contractor shall conduct this in the field at the corresponding sampling site or at another location proposed by the Contractor.

    - The Contractor shall, prior to analysis, record composite sample weight and corresponding composite sample ID number.

    - The Contractor shall remove moisture from the composite samples at an appropriate location.

    - The Contractor may air dry the composite samples using a drying method such as a desiccator containing a charged drying agent, an electronic dehumidifier, or a dry heat source. As part of its bid, the Contractor may propose other drying methods to meet the standards and objectives of this task.

    - The Contractor shall continue the drying process until samples reach equilibrium. Equilibrium has been reached when the weight of the sample does not decrease by more than 1 percent. The Contractor may propose their own sample measurement scheme. As an example, the Contractor could weigh the composite samples, dry for at least four hours and weigh the composite sample again. At that point the Contractor may use the last weight as the final sample weight.

    - The Contractor shall record composite sample weights and corresponding composite sample ID number.

- DIGITAL IMAGES:

- When taking a digital image of each composite sample, the Contractor shall place a placard on, adjacent, or near the sample clearly identifying the unique sample ID number, location, and date. The Contractor shall name each digital image file so it correlates to the unique composite sample ID. The Contractor shall provide images with a minimum resolution of 12-megapixels. If the digital image requirements are not met as previously described, such as, but not limited to, blurry images, the composite sample is not clearly identified, and/or improper file naming, the digital images shall not be accepted as fulfilling the contract, and the Contract Manager will have the discretion to withhold payment for each mishandled sample.

- For each composite sample, the Contractor shall take:

    - One image that will allow for clear visualization of the entire composite sample, for each sample, before processing.

    - One image that will allow for clear visualization of the entire composite sample, for each sample, after processing to remove moisture.

Task 4 - DATA COLLECTION

- TASK 4 - Data Collection for PART 1- Disposal Facility-Based Waste Characterization Study.

- The Contractor shall record all characterization data for each sample:

- For hand-sorts, the load weight (specifically the exact weight of the load as per the scale before entering the facility minus the unladen vehicle weight. In the absence of a scale, the Contractor shall use the methodology proposed in the RFP to estimate the load weight), the weight of each sorted material type and total sample weight shall be recorded. The Contractor shall use a scale that is accurate to within 0.01 pounds and is connected to a computer to record weights. The Contractor shall record weights in decimal pounds.

- For visual characterizations, the percentage of each material in the entire load and the tare weight of the entire load. The Contractor shall report percentages to the nearest percent. The Contractor shall record weights in decimal pounds and provide all volume-to-weight conversion factors used.

- Task 4 - Data Collection for PART 2- Multi-Family Generator-Based Waste Characterization Study

  - The Contractor shall collect the following information at each multi-family residence:

    - The sample weight and volume (cubic yards)

    - Confirmation of number and size (volume) of waste bins at the site,

    - Collection frequency for the bins,

    - Total volume of waste in disposal bin at sample collection,

    - Sample collection and bin observations on whether it was an appropriate day to obtain representative data on volumes,

    - Accurate accumulation time of waste or rate of accumulation (cubic yards/hours of bin accessibility) and raw data for accumulation time calculations,

    - Confirmation of number of occupied units and corresponding unit size (number of bedrooms/unit) and

    - Other pertinent information.

  - The Contractor shall assign a unique ID number to each sample, and record the date of collection, name and location of the multi-family residence including jurisdiction (city or unincorporated county) and county.

  - The Contractor shall record the weight of each sorted material type and total sample weight. The Contractor shall use a scale that is accurate to within 0.01 pounds and is connected to a computer to record weights. The Contractor shall record weights in decimal pounds.

- Task 4 - Data Collection for PART 3- Moisture Analysis Study

  - For before and after weights, the Contractor shall measure and record the weight of each composite sample (by material type) using a scale that is accurate to within 0.01 pounds and is connected to a computer to record weights. The Contractor shall record weights in decimal pounds.

Task 5 – Data Entry and Data QA/QC for ALL PARTS of the study

- At least 30 calendar days prior to the first sampling period, the Contractor shall submit sample printouts displaying database and/or spreadsheet format to the Contract Manager for approval.

- The Contractor shall implement QA/QC measures when providing field-sorting data for each sorted sample (weight of each material type in the sample) and total sample weight for the Disposal Facility-Based study, the Multi-Family Generator-Based study, and the Moisture Analysis Study.

- The Contractor shall perform all data entry and follow all quality control measures in their plan to ensure the accuracy of the data entered. The Contractor shall resolve any errors or discrepancies in data discovered during quality control activities and/or review by the Contract Manager.

- The Contractor shall enter all data collected into electronic spreadsheets (e.g. Microsoft Excel) compatible with CalRecycle’s computer system. The Contract Manager will approve the format and software. Upon contract approval, the Contract Manager shall provide the Contractor with a sample format for data submission. The Contractor shall submit all final data to CalRecycle in electronic form (e.g. via e-mail or uploaded to a secure shared drive).

- The Contractor shall present and submit the data as follows: sample IDs in rows and collected data in columns. The Contractor shall submit complete data for each sample, including, at a minimum: (1) unique sample ID number, (2) name of facility/site sample was collected from, (3) date of collection, (4) for PART 1, the load weight of truck to be sampled for a hand-sort, specifically the exact weight of the load as per the scale before entering the facility minus the unladen vehicle weight. In the absence of a scale, the Contractor shall use the methodology proposed in the RFP to estimate the load weight, (5) total disposal sample weight, (6) weight of each disposal component in the sample by material type, (7) data used to calculate waste amounts, (8) truck/vehicle type, (9) sector and subsector for self-haul, (10) jurisdiction of origin (city or unincorporated county area) or facility of origin (for transfer trucks), (11) county of origin, (12) weather conditions on the day of collection, (13) for commercial/multi-family route loads: estimated percentage of multi-family waste, (14) for transfer trucks: name of originating facility, (15) for transfer trucks: total weight of load delivered, (16) weight of material type #1, (17) weight of material type #2-etc., (18) any notes on special circumstance or other information, as applicable, and (19) all digital images. If visual characterizations are conducted, the data needs to clearly distinguish between hand-sorts and visual characterizations and provide justification for visual characterization by sample. Additional data to be submitted for the Multi-Family Generator-Based Study and Moisture Analysis Study is identified in Task 4.

- The Contractor shall submit final and correct data, after the Contractor has thoroughly reviewed and subjected the data to stringent QA/QC procedures.

- The Contractor shall submit all data required for the three parts of the study at least 45 days before the end of the contract. This will allow enough time for the Contract Manager to review the data and correspond with the Contractor regarding any issues.

- The Contract Manager will have 30 calendar days to review the submitted data to ensure it is complete, understandable, and usable for subsequent analyses. The Contractor shall respond to any questions and address any problems or discrepancies found by the Contract Manager within 15 calendar days.

Task - 6 Submit Field Data and Summary Reports to CalRecycle

- During the sample collection period, the Contractor shall provide weekly status reports in a format provided by CalRecycle (see Sample Report). The Contractor may propose an alternative format to the weekly report that meets the standards and objectives of the report and subject to the prior approval of the Contract Manager. The reports shall include project statuses including progress made, work done and work pending, any deviation from the plan and a detailed explanation for the deviation. When appropriate, these reports shall also include meeting minutes.

- Outside the sample collection periods, the Contractor shall provide monthly status reports, but may do so more frequently.

- During field sampling operations, the Contractor shall prepare and submit to the Contract Manager weekly reports containing the following:

  - Final schedule/sampling plan for the upcoming week for disposal sites, multi-family residences, and, as applicable, moisture analysis.

  - Summary of sampling completed during the previous week, including numbers of samples characterized and names of sites from which samples were collected for each sector and/or subsector.

  - Copies of all paper field sheets (if any) and digital images taken for the previous week’s work.

  - Reports of any problems, contingency measures taken, or significant findings encountered.

  - Recommendations for adjustments to field procedures, site selection, or general study parameters, if needed.

  - Electronic files that contain the data collected from the previous week.

- Not more than 20 calendar days after the completion of data collection for all parts, the Contractor shall notify the Contract Manager if there are any changes or corrections to the data.

- Not more than 25 calendar days after the end of the first and second field periods, the Contractor shall prepare and submit to the Contract Manager a report summarizing information on all samples completed including the following:

  - The total number of samples collected and characterized,

  - For each sample, corresponding site names from which the samples were obtained,

  - For each sample, the sector and/or subsector,

  - A description and explanation of any differences between the final sampling plan and the actual field sampling performed, and

  - A description of any unusual circumstances.

- CalRecycle Responsibilities:

- CalRecycle Responsibilities regarding Part 1-Disposal Facility-Based Waste Characterization Study:

- At least 45 calendar days before each sampling period begins, the Contract Manager will provide the Contractor with the final list of sampling locations, the number of sampling days and samples to be hand-sorted at each site, and the proposed allocations to each source type at each site.

- CalRecycle will determine how the samples (total number to be proposed by the Contractor) shall be distributed between facilities, sources, and sampling periods. CalRecycle will use preliminary in-house data to suggest possible sample allocation. This will be discussed and finalized during the initial meetings between the Contract Manager and the Contractor.

- CalRecycle will set two distinct 4 months sampling periods in 2020 and mid-2021, separated by not less than two months. The specific dates of the sampling periods will be finalized based on the date of contract execution.

- CalRecycle will allocate approximately half of the samples to each sampling period. The number of samples and sampling days will be based on the total number of samples proposed by the Contractor.

- Subject to logistics and recruitment success, CalRecycle will recruit 35-45 sampling sites. CalRecycle will roughly allocate the number of samples to facilities based on their level of disposal.

- To gather data representative of California’s waste stream, CalRecycle will attempt to recruit the largest landfills in California (Table 1. Largest landfills in California) as sampling sites. CalRecycle will attempt to recruit sites that accept approximately 75 percent of statewide disposal.

- CalRecycle will attempt to select only landfills as sampling sites for the collection and sorting of waste. If a selected landfill does not participate, CalRecycle will attempt to recruit the next largest landfill(s) and/or large transfer station(s) that send waste to the original landfill. CalRecycle may substitute landfills or transfer stations as needed. CalRecycle will provide a preliminary list of potential sites to the Contractor prior to the meeting identified in Task 1. Additional information on potential facilities can be found at: https://www2.calrecycle.ca.gov/SWFacilities/Directory/

- To gather data representative of California’s waste stream, CalRecycle will recruit sites throughout the State. Most sites will likely be located near large urban areas, with very few sites in rural areas.

- To stratify by source, CalRecycle will allocate the samples proportionally to approximate the statewide contribution of each source to the overall waste stream. For each sampling site, CalRecycle will identify how many samples of waste destined for disposal will be taken from each source: vehicles delivering single-family residential route loads, commercial/multi-family route loads, transfer truck loads, and self-haul loads.

- CalRecycle will determine the material types for hand-sorting and visual characterizations. CalRecycle does not anticipate any alterations to the list of material types Table 2 of the Appendix.

- CalRecycle will conduct analyses of the data and prepare any final reports.

- CalRecycle Responsibilities regarding Part 2- Multi-Family Generator-Based Waste Characterization Study:

- At least 45 calendar days before each sampling period begins, the Contract Manager will provide the Contractor with the final list of recruited multi-family residences and the pertinent logistical information to facilitate sample collection from each multi-family residence.

- CalRecycle will recruit the multi-family residences to be sampled and provide logistical information needed for sample collection (e.g. contact person, number and location of bins, pick-up day). A multi-family residence is defined as a building or complex consisting of 5 or more dwelling units.

- CalRecycle will allocate approximately half of the multi-family samples (50 samples total) to each sampling period established in Part 1. At the minimum number of samples, this equates to 25 multi-family samples per sampling period.

- At a minimum, CalRecycle will recruit 50 multi-family residences distributed throughout the state based on proximity to the selected sampling sites (nodes) in Part 1. The Contractor shall transport the multi-family samples to these nodes where the sorting shall occur.

- CalRecycle will select disposal sampling sites in Part 1 and designate them as sampling nodes for the multi-family study. CalRecycle will attempt to recruit all multi-family residences from within 10 miles of each node and will not recruit a residence further than 30 miles from the node.

- CalRecycle will provide the material type list to be used (same as in Part 1).

- CalRecycle will conduct analyses of the data and prepare any final reports.

- CalRecycle Responsibilities regarding Part 3-- Moisture Analysis Study:

- At least 45 calendar days before each sampling period begins, the Contract Manager will provide the Contractor with the final number of samples to collect from each source/sector for the moisture analysis at each site. This will be based on total samples per material type proposed in the Contractors Moisture Analysis Study Plan

- Table 3 is the final list of material types for use in the moisture analysis. The materials are a subset of those identified in Table 2 of the Appendix. The Contractor shall already be sorting the material into the selected materials for PART 1 of the study.

- CalRecycle will allocate approximately half of the total (total sample number to be proposed by the Contractor) moisture analysis composite samples to each sampling period established in Part 1. A composite sample is the combined materials of each specific type identified in Table 3 of the Appendix from all samples sorted in PART 1 on a designated sampling day.

- The Contract Manager and the Contractor will agree upon which Part 1 sampling sites shall be used to collect the already sorted materials for the Moisture Analysis, and the sampling days on which materials are to be collected.

- Contract/Task Time Frame

| Task | Task Description | Start Date | End Date |
| --- | --- | --- | --- |
| 1 | Initial Meeting to Review Disposal Facility-Based Study Implementation Plan | Contract execution | 60 days post contract execution |
|  | Review Multi-Family Generator Study Implementation Plan |  |  |
|  | Review Moisture Analysis Implementation Plan |  |  |
| 2 | Coordinate with Disposal Facilities and Determine Field Schedule | Within 30 days of Contract Execution | 1st Sampling Period: 45 days before start of sampling period 2nd Sampling Period: 45 days before start of sampling period |
|  | Coordinate with Multi-family Residences and Determine Field Schedule |  |  |
|  | Determine Moisture Analysis Field Schedule |  |  |
| 3 | Perform Fieldwork-Field Sampling and Sorting at Disposal Facilities | Not to exceed 45 days post site coordination for each sampling period Composite sample processing must start with 1 week of initial sample collection and sorting for PART 1. | Not to exceed 4 months post fieldwork-field sampling and sorting start for each sampling period |
|  | Perform Fieldwork-Field Sampling and Sorting at Disposal Facilities |  |  |
|  | Conduct Moisture Analysis |  |  |
| 4 | Data Collection | ongoing | ongoing |
| 5 | Data Entry and Data QA/QC | As data is produced | 45 days before end of contract (12 months post contract execution) |
| 6 | Submit Field Data and Summary Reports to CalRecycle | As fieldwork begins | 45 days before end of contract (12 months post contract execution) |

Appendix

| Table 1. Largest landfills in California in descending order of percentage waste disposed in 2018 |  |  |  |
| --- | --- | --- | --- |
| Name | SWIS | County | % of CA waste disposed in 2018 |
| El Sobrante Landfill | 33-AA-0217 | Riverside | 8.47% |
| Frank R. Bowerman Sanitary LF | 30-AB-0360 | Orange | 5.92% |
| Olinda Alpha Landfill | 30-AB-0035 | Orange | 5.35% |
| Sunshine Canyon City/County Landfill | 19-AA-2000 | Los Angeles | 5.28% |
| Chiquita Canyon Sanitary Landfill | 19-AA-0052 | Los Angeles | 3.83% |
| Otay Landfill | 37-AA-0010 | San Diego | 3.47% |
| Simi Valley Landfill & Recycling Center | 56-AA-0007 | Ventura | 3.19% |
| Mid-Valley Sanitary Landfill | 36-AA-0055 | San Bernardino | 2.82% |
| Altamont Landfill & Resource Recovery | 01-AA-0009 | Alameda | 2.46% |
| Sycamore Landfill | 37-AA-0023 | San Diego | 2.38% |
| Potrero Hills Landfill | 48-AA-0075 | Solano | 2.34% |
| West Miramar Sanitary Landfill | 37-AA-0020 | San Diego | 2.30% |
| Central Disposal Site | 49-AA-0001 | Sonoma | 2.27% |
| Badlands Sanitary Landfill | 33-AA-0006 | Riverside | 2.23% |
| Sacramento County Landfill (Kiefer) | 34-AA-0001 | Sacramento | 2.15% |
| Forward Landfill, Inc. | 39-AA-0015 | San Joaquin | 2.14% |
| Keller Canyon Landfill | 07-AA-0032 | Contra Costa | 2.03% |
| Recology Hay Road | 48-AA-0002 | Solano | 1.79% |
| Monterey Peninsula Landfill | 27-AA-0010 | Monterey | 1.63% |
| Toland Road Landfill | 56-AA-0005 | Ventura | 1.57% |
| American Avenue Disposal Site | 10-AA-0009 | Fresno | 1.51% |
| Lamb Canyon Sanitary Landfill | 33-AA-0007 | Riverside | 1.49% |
| Corinda Los Trancos Landfill (Ox Mtn) | 41-AA-0002 | San Mateo | 1.46% |
| Newby Island Sanitary Landfill | 43-AN-0003 | Santa Clara | 1.38% |
| Prima Deshecha Landfill | 30-AB-0019 | Orange | 1.36% |
| Anderson Landfill, Inc. | 45-AA-0020 | Shasta | 1.29% |
| Antelope Valley Public Landfill | 19-AA-5624 | Los Angeles | 1.29% |
| Bakersfield Metropolitan (Bena) SLF | 15-AA-0273 | Kern | 1.16% |
| Scholl Canyon Landfill | 19-AA-0012 | Los Angeles | 1.01% |
| Redwood Landfill | 21-AA-0001 | Marin | 0.90% |
| Azusa Land Reclamation Co. Landfill | 19-AA-0013 | Los Angeles | 0.90% |
| H.M. Holloway Inc. | 15-AA-0308 | Kern | 0.89% |
| Visalia Disposal Site | 54-AA-0009 | Tulare | 0.81% |
| Highway 59 Landfill | 24-AA-0001 | Merced | 0.80% |
| Calabasas Landfill | 19-AA-0056 | Los Angeles | 0.80% |

| Table 2. 2020 Material List and Definitions by Category |  |  |  |
| --- | --- | --- | --- |
| Running Total | Category Name and # | Material Type and Definition | Examples |
| 1 | P1 (Paper) | Corrugated Cardboard means a paper laminate usually composed of three layers. The center wavy layer is sandwiched between the two outer layers. It can be uncoated or have a (glossy) coating on the inside or outside. This type does not include paperboard boxes such as cereal and tissue boxes. Excludes waxed cardboard. | - cardboard packaging and containers - shipping and moving boxes - computer packaging cartons - sheets and pieces used as dividers in boxes - boxes used for primary packaging of various consumer goods |
| 2 | P2 (Paper) | Paper Grocery Bags means bags (usually brown) made from Kraft paper generally designed to carry out groceries from stores and that can be clearly identified as coming from a grocery store. | - paper grocery bags |
| 3 | P3 (Paper) | Other Paper Bags/Kraft Paper means bags made from Kraft paper that are not clearly identified as grocery bags, and sheets of Kraft paper. The paper may be brown (unbleached) or white (bleached). The paper may also be single layer or multi-layer (multiwall). | - single-layer bags that are not grocery bags (e.g. department store bags, paper lunch bag) - multiwall bags that do not have a plastic layer incorporated into the bags (e.g. used for shipping bulk products like pet food, rice, flour and sugar) - heavyweight sheets of Kraft packing paper |
| 4 | P4 (Paper) | Newspapers/Newspaper Inserts: means paper used in newspapers and all items made from newsprint. | - newspapers - glossy inserts found in newspapers - free advertising guides - election guides - plain news packing paper - telephone books |
| 5 | P5 (Paper) | White Office-type Paper and Mail means white paper used in offices and mail. Does not include envelopes lined with plastic or bubble wrap. | - copy paper - computer printer paper - letter paper - bills/business forms - white envelopes with or without clear windows - white cardstock |
| 6 | P6 (Paper) | Magazines and Catalogs means multi-page bound items (glued or stapled) made of glossy coated paper. This paper is usually slick, smooth to the touch, and reflects light. | - glossy magazines - catalogs - brochures - pamphlets |
| 7 | P7 (Paper) | Folding Cartons and Other Paperboard Packaging means paperboard boxes, other than corrugated, which fold and are primarily made of paper with few other materials (e.g. boxes with plastic windows are excluded) These cartons and packaging are typically used as the primary packaging for various products such as breakfast cereals, frozen foods, candy/cookies, jewelry, tobacco, pharmaceuticals and cosmetics. This also includes non-box paperboard such as paper tubes for toilet paper. | - paperboard boxes - tissue boxes - shoe boxes - paper-based tubes and cores (e.g. for toilet paper or paper towels) - paper clothing tags. |
| 8 | P8 (Paper) | Aseptic Containers and Gable-top Cartons means bleached polycoated paperboard containers or paper containers with a foil liner of various sizes and shapes that contain shelf-stable food products (i.e. aseptic containers) and paper-based cartons with a triangular top used for refrigerated and non-refrigerated items (i.e. gable-top cartons) Containers may include a plastic pour spout as part of the container. | - containers for apple juice, soup, soy/rice milk. - cartons used for milk, egg substitutes, and juice - gable-top containers used for snacks |
| 9 | P9 (Paper) | Paper/Fiber Food Service Ware means items made mostly of paper that are used to consume, contain, or transport prepared food items. Includes paper and molded fiber, including compostable and non-compostable items. May be contaminated with food and/or moisture. Excludes packaging. | - plates - bowls - cups - utensils - straws - stirrers - take-out containers - pizza boxes - bakery/bread bags - condiment cups |
| 10 | P10 (Paper) | Other Recyclable Paper means items made of paper that do not fit into any of the other paper types, but that are generally recyclable or not generally composted. Paper may be combined with minor amounts of other materials such as wax or glues. | - colored paper - manila folders - manila envelopes - index cards - lined or colored notebook paper - carbonless forms - chipboard - self-adhesive notes - hardcover and paperback books - bagged shredded paper - greeting cards |
| 11 | P11 (Paper) | Remainder/Composite Paper means items made mostly of paper but combined with large amounts of other materials. These are items that do not fit into any other categories and are not generally compostable or recyclable. Excludes packaging and food service ware. | - blueprints - sepia - carbon paper - photographs - sheets of paper stick-on labels - lined butcher paper - envelopes lined with plastic or bubble wrap. |
| 12 | P12 (Paper) | Other Paper/Fiber - Packaging means items that are made mostly of paper or molded fiber that don’t fit into any other material types and that are used for packaging. They may be combined with other materials or contaminated with food and/or moisture. Excludes food service ware, including clamshells, cups, bowls, plates, and trays. | - pulp paper egg cartons - unused pulp plant pots - molded paper packaging (e.g. some berry trays) - food-soiled paper packaging - waxed corrugated cardboard bags and boxes with plastic component (e.g. window) - paper frozen juice cans with metal ends |
| 13 | P13 (Paper) | Other Compostable Paper means items that do not fit any other category, are made of paper, can be composted and are generally not recycled. May be contaminated with food, moisture, or wax. | - waxed paper - napkins - facial tissues - paper towels |
| 14 | PL1 (Plastic) | PETE Beverage Containers - CRV means containers for beverages that are marked with PET (1) and have the CRV symbol. | - beverage containers for soda, juice, etc |
| 15 | PL2 (Plastic) | PETE Bottles and Jars – Non-CRV means screw top bottles without the CRV symbol and jars that are marked with PET (1). | - beverage containers for soda, juice, water - jars and containers for food - containers for household products (e.g. shampoo, cleaning products) |
| 16 | PL3 (Plastic) | HDPE Beverage Containers - CRV means containers for beverages that are marked with HDPE (2) and have the CRV symbol. | - beverage containers for soda, juice, etc |
| 17 | PL4 (Plastic) | HDPE Bottles and Jars - Non-CRV means screw top bottles without the CRV symbol and jars that are marked HDPE (2). | - beverage containers for soda, juice, water - jars and containers for food - containers for household products (e.g. shampoo, cleaning products) |
| 18 | PL5 (Plastic) | Expanded Polystyrene Packaging means packaging items made of expanded polystyrene. Does not include non-packaging items such as insulation boards. | - egg cartons - foam ice chests - transport and other packaging |
| 19 | PL6 (Plastic) | Plastic Trash Bags means plastic bags sold for use as trash bags, for both residential and commercial use. This type does not include other plastic bags, like shopping bags, that might have been used to contain trash. | - garbage bags and can liners - compostable plastic bags - lawn and leaf bags |
| 20 | PL7 (Plastic) | Plastic Grocery and Other Merchandise Bags means plastic shopping bags used to contain merchandise to transport from the place of purchase, given out by the store with the purchase. Does not include produce bags. | - dry cleaning bags - grocery bags - merchandise bags |
| 21 | PL8 (Plastic) | Film Products- Non-Packaging means plastic film used for purposes other than packaging, including agricultural use. | - agricultural film - wrap for hay bales - plastic sheeting (e.g. drop cloths) - building wrap - x-ray film - metallized film (e.g. balloons) - plastic food wrap |
| 22 | PL9 (Plastic) | Flexible Plastic Pouches means plastic pouches made of thicker, multi-layer flexible material. Material is thicker than potato chip bags and frozen vegetable bags. May have a flat bottom so that package would stand up on its own, but not always. May have plastic screw tops. | - child resistant pouch bags - plastic coffee bags - juice pouches (e.g. Capri Sun) - baby food pouches - food pouches for soup, salad, wine, or backpacking meals - soap refill pouches |
| 23 | PL10 (Plastic) | Non-Bag Commercial and Industrial Packaging Film means film plastic used for large-scale packaging or transport packaging. | - shrink wrap - mattress bags - furniture wrap - film bubble wrap |
| 24 | PL11 (Plastic) | Film Bags means all other plastic film, in bag form, that does not fit into any other type, excluding flexible plastic pouches. Excludes packaging. | - sandwich bags and zipper bags - newspaper bags - produce bags - mailing pouches |
| 25 | PL12 (Plastic) | Plastic Food Service Ware means items made partially or entirely of plastic that are used to consume, contain, or transport prepared food items. Includes all plastic types including compostable plastics. Excludes packaging. | - plates - bowls - cups (and lids) - utensils - straws - stirrers - take-out containers (e.g. clamshells) - bakery bags - condiment cups |
| 26 | PL13 (Plastic) | Other Plastic Packaging means jars, containers (including lids), and other packaging that are made of plastic, including film plastics. Only includes bottles and containers not included in any other category. Only includes film plastics not included in other categories. They may bear the triangular recycling symbol or may bear no recycling symbol. Excludes foodservice ware, including clamshells, takeout containers, cups, bowls, plates, and trays. | - frozen vegetable bags - bread bags - potato chip bags - candy wrappers - yogurt cups - ketchup bottles - small storage containers for fresh produce - household cleaning bottles - microwave food trays - vitamin bottles - cookie trays - single-use plant containers - thermoform packaging (e.g. berry containers) |
| 27 | PL14 (Plastic) | Durable Plastic Items means plastic items that are made to last for more than one use. These items may bear the numbers 1 through 7 in the triangular recycling symbol. | - crates, totes, buckets, tubs - plastic garbage cans - flower pots larger than one gallon - lawn furniture - plastic toys and sporting goods - CDs and cases - Plastic housewares including durable plates, cups, utensils - Building materials such as house siding, housing for electronics, fan blades, plastic pipes and fittings |
| 28 | PL14 (Plastic) | Remainder/Composite Plastic means plastic that cannot be put in any other type. This type includes items made mostly of plastic but combined with other materials. | - window blinds - insulating foam - imitation ceramics - handles and knobs - plastic lumber - EPS not used for packaging or food service ware - rigid bubble/foil packaging (e.g. blister pack) - some toys - some kitchenware - some auto parts |
| 29 | G1 (Glass) | Clear Glass Bottles and Containers – CRV means clear glass containers that display the CRV notification. Includes whole and broken bottles. | - soda bottles - fruit juice bottles - wine cooler bottles |
| 30 | G2 (Glass) | Clear Glass Bottles and Containers - Non-CRV means clear glass containers that do not display the CRV notification. Includes whole and broken containers. | - wine bottles - food jars |
| 31 | G3 (Glass) | Green Glass Bottles and Containers – CRV means green-colored glass containers that display the CRV notification. Includes whole and broken bottles. | - soda bottles - beer bottles |
| 32 | G4 (Glass) | Brown Glass Bottles and Containers – CRV means brown-colored glass containers that display the CRV notification. Includes whole and broken bottles. | - beer bottles |
| 33 | G5 (Glass) | Green and Brown Glass Bottles and Containers - Non-CRV means brown-colored or green-colored glass containers that do not display the CRV notification. Includes whole and broken containers. | - wine bottles |
| 34 | G6 (Glass) | Other Colored Glass Bottles and Containers means other-colored glass containers, with or without the CRV notification. Includes whole and broken containers. | - blue soda and water bottles - wine bottles - liquor bottles |
| 35 | G7 (Glass) | Remainder/Composite Glass means glass that cannot be put in any other type. It includes flat and curved glass and items made mostly of glass but combined with other materials. Includes whole or broken items. | - window panes - doors and table tops - automotive glass - safety glass - Pyrex and kitchen glass - crystal and glass tableware - drinking glasses - mirrors - non-fluorescent light bulbs - laminated glass |
| 36 | M1 (Metal) | Tin/Steel Cans means rigid containers made mainly of steel, both CRV and non-CRV containers. These items will stick to a magnet and may be tin-coated. This subtype is used to store food, beverages, paint, and a variety of other household and consumer products. | - canned food and beverage containers - empty metal paint cans - empty spray paint cans and aerosol containers - bimetal containers with steel sides and aluminum ends |
| 37 | M2 (Metal) | Aluminum Cans - CRV means any food or beverage container that is made mainly of aluminum and that displays the CRV notification. This subtype does not include bimetal containers with steel sides and aluminum ends. | - soda or beer cans |
| 38 | M3 (Metal) | Aluminum Cans - Non-CRV means any food or beverage container that is made mainly of aluminum and that does not display the CRV notification. | - pet food cans - meat cans - wine cans |
| 39 | M4 (Metal) | Major Appliances means discarded major appliances encased in metal, of any color. These items are often enamel-coated. This type does not include electronics, such as televisions and stereos. | - washing machines - clothes dryer - hot water heater - stove - refrigerator |
| 40 | M5 (Metal) | Other Ferrous means any iron or steel that is magnetic or any stainless-steel item. This type does not include tin/steel cans. | - structural steel beams - metal clothes hangers - metal pipes - stainless steel cookware - security bars - scrap ferrous items - reusable stainless steel water bottle |
| 41 | M6 (Metal) | Other Non-Ferrous means any metal item, other than aluminum cans, that is not stainless steel and that is not magnetic. These items may be made of aluminum, copper, brass, bronze, lead, zinc, or other metals. | - aluminum window frames - aluminum siding - copper wire - shell casings - brass pipes - aluminum foil - some cookware |
| 42 | M7 (Metal) | Remainder/Composite Metal means metal that cannot be put in any other type. This type includes items made mostly of metal but combined with other materials and items made of both ferrous metal and non-ferrous metals combined. Includes products whose weight is derived significantly from the metal portion of its construction. | - small non-electronic appliances (e.g. toasters, hair dryers) - used oil filters - motors - insulated wire |
| 43 | E1 (Electronics) | Covered Video Display Devices means video display devices with a screen greater than four inches, measured diagonally. A video display device may use, but is not limited to, a cathode ray tube (CRT), liquid crystal display (LCD), gas plasma, digital light processing or other image projection technology | - computers with displays or computer monitors - televisions - portable DVD players or gaming console with screen - tablet computers (e.g. iPad or Kindle) - cathode ray tubes |
| 44 | E2 (Electronics) | Consumer Electronics and Small Equipment means small IT and telecommunication equipment, and other small items that usually need electric currents or electromagnetic fields to operate. | - mobile phones - GPS - calculators - printers - computer without screen - sewing machines - microwaves - irons - toasters - electric knives - shavers - toys - some sport equipment - some hair care appliances |
| 45 | E3 (Electronics) | Large Equipment means large items that usually need electric currents or electromagnetic fields to operate. | - musical equipment - slot machines - large printing machines - large exercise equipment |
| 46 | OR1 (Organics) | Food - Potentially Donatable – Vegetative (Perishable/Fresh) means uncooked or cooked fresh vegetables, fruits, and fungi that are in a whole state (i.e., not partially consumed) and are unmixed with non-vegetative food types. Items in their whole state are either in original, unopened packaging or unpackaged items from commercial sector that have clearly not been consumed (e.g. a whole apple or entire head of lettuce). Items that are excluded from this category include condiments, non-perishable packaged fruits and vegetables such as: packaged dried fruits and vegetables, canned fruits and vegetables, and nuts. Any unpackaged vegetables, fruits, and fungi found in a whole state in residential loads are excluded from this category and should be sorted as “not donatable – non-meat”. However, unpackaged vegetables fruits, and fungi found in a whole state in commercial loads are included in this category. | - unopened package of mushrooms - whole fruit or vegetable - unopened package of fruit salad or salad greens |
| 47 | OR2 (Organics) | Food - Potentially Donatable - Eggs, Dairy, and Dairy Alternatives means egg or dairy products and dairy alternatives that are in a whole state, unmixed with other food types, and in the original unopened package. Items may be refrigerated or shelf stable. | - milk - cheese (dairy and non-dairy( - eggs (whole or sliced) - yogurts - soy/nut/rice/oat milks |
| 48 | OR3 (Organics) | OR3 Food - Potentially Donatable – Meat means any uncooked or cooked meat (beef, poultry, pork, lamb) or fish product that is in a whole state, is unmixed with other food types, and is in the original unopened package. This includes meat alternatives. | - whole or cooked meat or fish in unopened package - deli meat in unopened package - unopened jerky - unopened frozen meats (e.g. chicken nuggets) canned meat and fish - meat alternatives |
| 49 | OR4 (Organics) | Food - Potentially Donatable - Cooked/Baked/Prepared Perishable Items means items that are in a whole state but could have multiple food types mixed together as a part of cooking or preparation and are still in their original unopened package. | - whole sandwich in original unopened package - whole tray of food (e.g. lasagna) that is untouched - whole frozen pizza in unopened package - whole loaves of bread - bag of tortillas - unopened perishable fresh fruit and vegetable juice |
| 50 | OR5 (Organics) | Food - Potentially Donatable - Packaged Non-perishable means shelf-stable foods that are in a whole state and are in the original unopened package. Includes foods contained in aseptic or retort packages and other products that do not require refrigeration until after opening. Also includes non-perishable beverages such as sodas. Excluded from this category are shelf-stable meats, shelf-stable dairy products, and shelf-stable dairy alternatives. | - canned and bottled foods - rice - pasta - condiments - nuts and nut butters - flour, sugar, spices - oils - non-perishable beverages |
| 51 | OR6 (Organics) | Food - Not Donatable – Meat means any food that is predominantly meat or fish, but the product is not in a whole state (i.e., partially consumed), or the product’s packaging has been opened, or the product was not contained in any packaging at all. | - partially consumed meat, meat alternatives, or fish - meat or fish in opened package - hamburger that is mostly meat by weight - meat and fish trimmings - deli meats |
| 52 | OR7 (Organics) | Food - Not Donatable – Non-meat means any food that is not predominantly meat or fish, not in a whole state, or not in its original unopened package. Includes any non-meat partially consumed foods, any non-meat foods in a package that has been opened – as best as can be determined, any non-meat foods that are not in their original packaging. Item may contain small amounts of meat or fish. This category also includes fruit and vegetable peels, skins, trimmings, and or any parts of fruits and vegetables not included in the inedible category. In addition, this category also includes any indistinguishable food. | - partially consumed burrito or lasagna - fruit and vegetable peels (e.g. potato skins, carrot peels) - fruit and vegetable trimmings (e.g. cucumber ends, carrot tops, beet greens, broccoli and cauliflower stalks) - apple and pear cores |
| 53 | OR8 (Organics) | Food - Inedible means items typically not consumed by people in the United States. Categories of inedible parts include bones, pits, shells, banana peels, coffee grounds and tea leaves, rinds, woody stems/tops and vines, and corn cobs/husks. Note that small amounts of edible material associated with the inedible material are permitted to be included as “inedible.” Excludes other fruit and vegetable peels, skins, trimmings, cores, and ends not included in the previous categories (e.g. potato peels, carrot tops, apple cores, broccoli stalks, cucumber ends). | - pits (peach, avocado) - shells (eggs, nuts) - rinds (citrus, melon) - woody stems/tops and vines (pumpkin stem, pineapple top, tomato vine) - banana peels - corn cobs and husks - bones - coffee grounds - tea leaves |
| 54 | OR9 (Organics) | Leaves and Grass means plant material, except woody material, from any public or private landscape. This type does not include woody material or material from agricultural sources. | - leaves - grass clippings - plants - seaweed |
| 55 | OR10 (Organics) | Prunings and Trimmings means woody plant material up to 4 inches in diameter from any public or private landscape. This type does not include stumps, tree trunks, or material from agricultural sources. | - pruning from shrubs - branches with diameters of less than 4 inches |
| 56 | OR11 (Organics) | Branches and Stumps means woody plant material, branches, and stumps that exceed 4 inches in diameter, from any public or private landscape. | - branches with diameters greater than 4 inches - stumps |
| 57 | OR12 (Organics) | Manures means manure and soiled bedding materials from large domestic, farm, or ranch animals. Does not include feces from small household pets such as dogs and cats. | - manure - soiled bedding from animal operations |
| 58 | OR13 (Organics) | Clean Dimensional Lumber means unpainted new or demolition dimensional lumber. May contain nails or other trace contaminants. | - 2 x 4s, 2 x 6s, 2 x 12s - residual materials from framing and related construction activities |
| 59 | OR14 (Organics) | Clean Engineered Wood means unpainted new or demolition scrap from sheeted goods. May contain nails or other trace contaminants. | - plywood - particle board - wafer board - oriented strand board - residual materials used for sheathing and related construction uses |
| 60 | OR15 (Organics) | Clean Pallets and Crates means unpainted wood pallets, crates, and packaging made of lumber/engineered wood. May contain nails or other trace contaminants. | - unpainted wood pallets - unpainted crates - packaging made of lumber/engineered wood |
| 61 | OR16 (Organics) | Treated/Painted/Stained Wood means wood that has been treated with a chemical preservative for purposes of protecting the wood against attacks from insects, microorganisms, fungi, and other environmental conditions that can lead to decay of the wood; and wood that has had an external coating such as paint, varnish, or other finish applied. | - handrails - finished furniture - other wood and wood products with paint, varnish, or other finish applied |
| 62 | OR17 (Organics) | Other Recyclable Wood means recyclable wood not included in any other category. This may include scrap from production of prefabricated wood products that have not been treated with paint, stain, or other chemical finish. Wood material should not be contaminated with another material (e.g.. tar). May contain nails or other trace contaminants. | - Untreated scrap from production of pre-fabricated wood products (e.g. from cabinets or furniture) - untreated/unpainted fencing - recyclable demolition wood - untreated/unpainted wood roofing and siding |
| 63 | OR18 (Organics) | Remainder/Composite Organic means organic material that cannot be put in any other type. | - natural cork - hemp rope - hair - small wood products (e.g. popsicle sticks, toothpicks) - sawdust - agriculture crop residues - animal carcasses - straw baskets - dryer sheets - non-textile leather - cosmetics |
| 64 | InOth1 (Inerts & Other) | Concrete means a hard material made from sand, aggregate, gravel, cement mix, and water. This category includes concrete with a steel internal structure composed of reinforcing bars (re-bar) or metal mesh. | - pieces of building foundations - concrete paving - concrete/cinder blocks |
| 65 | InOth2 (Inerts & Other) | Asphalt Roofing means composite shingles and other roofing material made with asphalt. | - asphalt roofing - asphalt shingles and attached roofing tar and tar paper |
| 66 | InOth3 (Inerts & Other) | Gypsum Board means interior wall covering made of a sheet of gypsum sandwiched between paper layers. Includes used and unused broken or whole sheets. Includes painted gypsum board. | - gypsum board - sheet rock - drywall - plasterboard - gypboard - Gyproc - wallboard |
| 67 | InOth4 (Inerts & Other) | Carpet means flooring applications consisting of various natural or synthetic fibers bonded to some type of backing material. This type does not include carpet padding or woven rugs with no backing. | - carpet |
| 68 | InOth5 (Inerts & Other) | Rock, Soil and Fines means rock pieces of any size and soil, dirt, and other matter. This type also includes nonhazardous contaminated soil. | - rock - stones - sand - clay - soil and other fines |
| 69 | InOth6 (Inerts & Other) | Remainder/Composite Inerts and Other means inerts and other material that cannot be put in any other type. This type may include items from different types combined, which would be very hard to separate. This type may also include demolition debris that is a mixture of items such as plate glass, wood, tiles, gypsum board, synthetic counter tops, fiber or composite acoustic ceiling tiles, and aluminum scrap. | - brick - ceramics - tiles - toilets - sinks - dried paint not attached to any materials - fiberglass - insulation - carpet padding - asphalt paving |
| 70 | HHW1 (Household Hazardous Waste) | Paint means containers with paint in them. This type does not include dried paint, empty paint cans, or empty aerosol containers. | - latex paint - oil-based paint - tubes of pigment - fine art paint |
| 71 | HHW2 (Household Hazardous Waste) | Used Oil means the same as defined in Health and Safety Code section 25250.1(a). | - spent lubricating oil (e.g. crankcase and transmission oil, gear oil, hydraulic oil) |
| 72 | HHW3 (Household Hazardous Waste) | Lead-acid (automotive) batteries means batteries consisting of lead-acid cells. | - auto batteries |
| 73 | HHW4 (Household Hazardous Waste) | Other batteries means any type of battery other than lead-acid (automotive) batteries. Examples include household batteries such as AA, AAA, D, button cell, 9 volt, and rechargeable batteries used for flashlights, small appliances, watches, and hearing aids. | - AA, AAA, D batteries - 9 volt batteries - rechargeable batteries - watch and hearing aid batteries |
| 74 | HHW5 (Household Hazardous Waste) | One-Pound or Less Propane Gas Cylinders means small, compact, and portable propane gas cylinders used to power devices such as camping stoves, tailgating grills, heaters, and more. Generally, these cylinders are not refillable. | - one pound or less propane gas cylinder |
| 75 | HHW6 (Household Hazardous Waste) | Pharmaceuticals means both prescription and over-the-counter medications and supplements in all forms, including pills, liquid medications, creams, and ointments. Does not include containers for these items, except for tubes for creams and ointments and other containers that cannot be easily separated from the product they contain. | - pills - liquid medications - creams and ointments |
| 76 | HHW7 (Household Hazardous Waste) | Remainder/Composite Household Hazardous means household hazardous material that cannot be put in any other type. Examples include household hazardous waste that, if improperly put in the solid waste stream, may present handling problems or other hazards. Also includes vehicle and equipment fluids other than used oil. | - pesticides - caustic cleaners - sharps - fluorescent lamps - LED lamps - mercury-containing items such as thermostats or thermometers - vehicle and equipment fluids such as used oil |
| 77 | SW1 (Special Waste) | Tires means vehicle tires. Tires may be pneumatic or solid. | - automobile tires - lawn mower tires - bicycle tires - motorcycle tires |
| 78 | SW2 (Special Waste) | Mattresses and Foundations means a resilient material or combination of materials that is enclosed by a ticking and is intended for or promoted for sleeping upon. Includes foundations, which means a ticking-covered structure used to support a mattress or sleep surface. The structure may include one or more of the following components: constructed frames, foam, box springs, or other materials. Excludes any unattached mattress pad or unattached mattress topper intended to be used with or on top of a mattress; sleeping bags and pillows; a car bed, crib, or bassinet mattress; juvenile products, including a carriage a product containing liquid- or gaseous-filled ticking, including a water bed or air mattress that does not contain upholstery material between the ticking and the mattress core; upholstered furniture that does not otherwise contain a detachable mattress or that is a fold out sofa bed or futon. | - mattresses - foundations used to support mattress |
| 79 | SW3 (Special Waste) | Bulky Items means large, hard-to-handle items that are not defined elsewhere in the material types list, including furniture and other large items. | - couches - furniture |
| 80 | SW4 (Special Waste) | Remainder/Composite Special Waste means special waste that cannot be put in any other type. Includes treated medical waste (medical waste that has been processed in order to change its physical, chemical, or biological character or composition, or to remove or reduce its harmful properties or characteristics, as defined in Section 25123.5 of the Health and Safety Code). | - ash - auto fluff - auto bodies - treated medical waste - untreated medical waste (e.g. tubes, oxygen masks) - asbestos-containing materials (e.g. certain pipes, insulation, and floor tiles) - artificial fireplace logs |
| 81 | MISC1 (Miscellaneous) | Textiles – Cloth and Clothing means cloth, clothing, sheets and towels, rope, and other textile items made of organic, synthetic, unknown, and mixed fibers. Textiles with zippers and buttons are included | - cloth and rags - clothing - towels - sheets - rope |
| 82 | MISC2 (Miscellaneous) | Textiles - Shoes, Purses, Belts means all shoes and boots, purses, and belts whether made of leather, rubber, other materials, or a combination thereof. | - shoes and sandals - purses - belts |
| 83 | MISC3 (Miscellaneous) | Solar Panels means panels used to convert sunlight into electricity. Solar panels consist of a semiconductor material such as silicon, encased in glass, with an aluminum frame. This category is specific to the panels, themselves, and does not include associated equipment such as junction boxes, wires, inverters, cables, energy storage batteries, or a photovoltaic cell that is part of a consumer electronic device for which it provides electricity needed to make the device function. | - solar panels |
| 84 | MISC4 (Miscellaneous) | Diapers & Sanitary Products means single-use items that are made from a combination of natural and/or synthetic fibers. | - diapers - feminine hygiene products - absorbent pads |
| 85 | MISC5 (Miscellaneous) | Miscellaneous Inorganics means inorganic items that cannot be put in any other type. | - kitchen ceramics - synthetic rubber products (e.g. kitchen gloves) - sports balls |
| 86 | MISC6 (Miscellaneous) | Mixed Residue means material (including 2-inch-minus materials) that cannot be put in any other type or category. This category includes mixed residue and materials smaller than two inches that cannot be further sorted. | - clumping kitty litter - feces from household pets - partially filled containers of non-food consumer products |

| Table 3. Moisture Analysis Material List Paper Categories |  |  |
| --- | --- | --- |
| Category Name and # | Material Type and Definition | Examples |
| P1 (Paper) | Corrugated Cardboard means a paper laminate usually composed of three layers. The center wavy layer is sandwiched between the two outer layers. It can be uncoated or have a (glossy) coating on the inside or outside. This type does not include paperboard boxes such as cereal and tissue boxes. Excludes waxed cardboard. | - cardboard packaging and containers - shipping and moving boxes - computer packaging cartons - sheets and pieces used as dividers in boxes - boxes used for primary packaging of various consumer goods |
| Combined P2 and P3 (Paper) | Paper Grocery Bags means bags (usually brown) made from Kraft paper generally designed to carry out groceries from stores and that can be clearly identified as coming from a grocery store. Other Paper Bags/Kraft Paper means bags made from Kraft paper that are not clearly identified as grocery bags, and sheets of Kraft paper. The paper may be brown (unbleached) or white (bleached). The paper may also be single layer or multi-layer (multiwall). | Paper Grocery Bags - paper grocery bags Other Paper Bags/Kraft Paper - single-layer bags that are not grocery bags (e.g. department store bags, paper lunch bag) - multiwall bags that do not have a plastic layer incorporated into the bags (e.g. used for shipping bulk products like pet food, rice, flour and sugar) heavyweight sheets of Kraft packing paper |
| P4 (Paper) | Newspapers/Newspaper Inserts: means paper used in newspapers and all items made from newsprint. | - Newspapers - glossy inserts found in newspapers - free advertising guides - election guides - plain news packing paper - telephone books |
| P5 (Paper) | White Office-type Paper and Mail means white paper used in offices and mail. Does not include envelopes lined with plastic or bubble wrap. | - copy paper - computer printer paper - letter paper - bills/business forms - white envelopes with or without clear windows - white cardstock |
| P6 (Paper) | Magazines and Catalogs means multi-page bound items (glued or stapled) made of glossy coated paper. This paper is usually slick, smooth to the touch, and reflects light. | - glossy magazines - catalogs - brochures - pamphlets |
| P7 (Paper) | Folding Cartons and Other Paperboard Packaging means paperboard boxes, other than corrugated, which fold and are primarily made of paper with few other materials (e.g. boxes with plastic windows are excluded) These cartons and packaging are typically used as the primary packaging for various products such as breakfast cereals, frozen foods, candy/cookies, jewelry, tobacco, pharmaceuticals and cosmetics. This also includes non-box paperboard such as paper tubes for toilet paper. | - paperboard boxes - tissue boxes - shoe boxes - paper-based tubes and cores (e.g. for toilet paper or paper towels) - paper clothing tags. |
| P9 (Paper) | Paper/Fiber Food Service Ware means items made mostly of paper that are used to consume, contain, or transport prepared food items. Includes paper and molded fiber, including compostable and non-compostable items. May be contaminated with food and/or moisture. Excludes packaging. | - plates - bowls - cups - utensils - straws - stirrers - take-out containers - pizza boxes - bakery/bread bags - condiment cups |
| P10 (Paper) | Other Recyclable Paper means items made of paper that do not fit into any of the other paper types, but that are generally recyclable or not generally composted. Paper may be combined with minor amounts of other materials such as wax or glues. | - colored paper - manila folders - manila envelopes - index cards - lined or colored notebook paper - carbonless forms - chipboard - self-adhesive notes - hardcover and paperback books - bagged shredded paper - greeting cards |
| P12 (Paper) | Other Paper/Fiber - Packaging means items that are made mostly of paper or molded fiber that don’t fit into any other material types and that are used for packaging. They may be combined with other materials or contaminated with food and/or moisture. Excludes food service ware, including clamshells, cups, bowls, plates, and trays. | - pulp paper egg cartons - unused pulp plant pots - molded paper packaging (e.g. some berry trays) - food-soiled paper packaging - waxed corrugated cardboard bags and boxes with plastic component (e.g. window) - paper frozen juice cans with metal ends |
| P13 (Paper) | Other Compostable Paper means items that do not fit any other category, are made of paper, can be composted and are generally not recycled. May be contaminated with food, moisture, or wax. | - waxed paper - napkins - facial tissues - paper towels |

SAMPLE REPORT

Project Name:

Project Status Reporting Period: From: To:

Project Manager:

Report Prepared By:

Weekly Project Summary: Enter a brief summary of the project status, noting any key issues for the week. Comment on major deliverables completed; milestones reached and percent complete.

Current Task Summary

| Task or Deliverable | Scheduled Completion Date | Actual Completion Date | Issues? If yes, explain |
| --- | --- | --- | --- |
| Example: Sample Task 1 | 31 March 2020 | 1 April 2020 | No issues for Sample Task 1 |

Accomplished this week

Sites and samples

Hand-Sorting: Indicate number of hand-sorts completed per sector (and subsector), at which sites and day(s) and provide required attachments such as photos or site details

Visual Characterization: Indicate number of visual characterizations completed per sector (and subsector), at which sites and day(s); also provide narrative description(s) per Task 3 and provide required attachments such as photos or site details.

Attachments provided? (Such as copies of paper field sheets (if any), digital images, electronic files that contain data from the previous week) Yes/No If no, provide a reasonable explanation and a date when the attachments will be submitted.

Other items such as problems, contingency measures taken, significant findings encountered, recommendations:

Weekly look ahead - Planned/Scheduled Completion in Next Two Weeks

What sites and how many days per site?

Sample Plan (Confirm the Plan Provided by CalRecycle)

Deliverables Due:

Other items, concerns, issues:

EXHIBIT B

BUDGET DETAIL AND PAYMENT PROVISIONS

- INVOICING AND PAYMENT:

For services satisfactorily rendered and upon receipt and approval of the invoices, the State agrees to compensate the Contractor for work performed in accordance with the Scope of Work and the approved Work Plan at the rates specified herein, not to exceed the per Task totals in the Cost Breakdown.

- Itemized invoices shall be submitted in triplicate, with two sets of supporting documentation (i.e., receipts, timesheets, etc), not more frequently than monthly in arrears to:

Accounts Payable

Department of Resources Recycling and Recovery

Fiscal Services Branch

U.S. Postal Correspondence:

P.O. Box 4025, MS-19A

Sacramento, CA 95812-4025

Federal Express Correspondence:

1001 I Street, MS-19A

Sacramento, CA 95814

- Each invoice submitted to CalRecycle must include the following information:

  - Invoice Number

  - Contract Number

  - Description of Rendered Activities/Services

  - Submitting Contractor’s Address

  - Invoice Period

- BUDGET CONTINGENCY CLAUSE:

- It is mutually agreed that if the Budget Act of the current year and/or any subsequent years covered under this Agreement does not appropriate sufficient funds for the program, this Agreement shall be of no further force and effect.  In this event, the State shall have no liability to pay any funds whatsoever to the Contractor or to furnish any other considerations under this Agreement and the Contractor shall not be obligated to perform any provisions of this Agreement.

- If funding for any fiscal year is reduced or deleted by the Budget Act for purposes of this program, the State shall have the option to either: cancel this Agreement with no liability occurring to the State, or offer an Agreement Amendment to the Contractor to reflect the reduced amount.

- PROMPT PAYMENT CLAUSE: Payment will be made in accordance with and within the time specified in Government Code, Chapter 4.5 (commencing with Section 927).

- TAXES:  The State of California is exempt from Federal Excise Taxes, and no payment will be made for any taxes levied on employees' wages.  The State will pay for any applicable State of California or local sales or use taxes on the services rendered or equipment or parts supplied pursuant to this Agreement.  California may pay any applicable sales or use tax imposed by another state.

- COST BREAKDOWN:

<<INSERT BUDGET SPREADSHEET OR OTHER BUDGET DETAIL HERE>>

- TRAVEL CLAUSE: All travel will be reimbursed at the excluded employee travel rates in accordance with the California Code of Regulations Title 2, Division 1, Chapter 3, Subchapter 1, Article 2, Section 599.615.1 et seq.  The Contractor will be held to the State per diem rates in effect at the time of travel.  For specific per diem (lodging, meals and incidentals) reimbursement rates, see California Code of Regulations Title 2, Division 1, Chapter 3, Subchapter 1, Article 2, Section 599.619.  For this agreement, the Contractor’s headquarters are located at <Contractor’s Address>.  Per diem will not be reimbursed for travel within 50 miles of Contractor’s headquarters.

- PROGRESS PAYMENT AND PAYMENT WITHHOLD: If progress payments are allowed for services performed under this agreement, not less than ten (10) percent of the agreement amount shall be withheld pending final completion of the agreement, and receipt and acceptance by the State of any final reports required under the agreement.  However, for those agreements that consist entirely of separate and distinct tasks, any funds withheld with regard to a particular task may be paid upon completion of that particular task. The Contractor agrees to comply with the requirements of Public Contract Code (PCC), Section 10346.

EXHIBIT D

SPECIAL TERMS AND CONDITIONS

    - AGENCY LIABILITY: The Contractor warrants by execution of this Agreement, that no person or selling agency has been employed or retained to solicit or secure this Agreement upon agreement or understanding for a commission, percentage, brokerage, or contingent fee, excepting bona fide employees or bona fide established commercial or selling agencies maintained by the Contractor for the purpose of securing business. For breach or violation of this warranty, CalRecycle shall, in addition to other remedies provided by law, have the right to annul this Agreement without liability, paying only for the value of the work actually performed, or otherwise recover the full amount of such commission, percentage, brokerage, or contingent fee.

    - AMENDMENT: No amendment or variation of the terms of this Agreement shall be valid unless made in writing, signed by the parties and approved as required.  No oral understanding or agreement not incorporated in this Agreement is binding on any of the parties.  CalRecycle reserves the right to amend this Agreement through a formal written amendment signed by both parties, for additional time and/or funding.

    - CALIFORNIA WASTE TIRES: Unless otherwise provided for in this contract, in the event the Contractor and/or Subcontractor(s) purchases waste tires or waste-tire derived products for the performance of this Agreement, only California waste tires and California waste tire-derived products shall be used. As a condition of payment under this Agreement, the Contractor must provide documentation substantiating the source of the tire materials used during the performance of this Agreement to the Contract Manager.

All formal notices required by this Agreement must be given in writing and sent by prepaid certified mail, fax, personal delivery or telex.

    - CONTRACT MANAGEMENT: The Contractor and the agents and employees of the Contractor, in the performance of this Agreement, shall act in an independent capacity and not as officers or employees or agents of the State of California. The Contractor may change the designated Project Director, but CalRecycle reserves the right to approve any substitution of the Project Director. Contractor’s key personnel may not be substituted without CalRecycle’s Contract Manager’s prior written approval. CalRecycle may change the Contract Manager by notice given to the Contractor at any time. CalRecycle staff will be permitted to work side by side with the Contractor’s staff to the extent and under conditions that may be directed by the Contract Manager. In this connection, CalRecycle’s staff will be given access to all required data, working papers, etc. The Contractor will not be permitted to utilize the CalRecycle’s staff for the performance of services, which are the responsibility of the Contractor unless the Contract Manager previously agreed to such utilization in writing, and any appropriate adjustment in price is made. No charge will be made to the Contractor for the services of CalRecycle’s staff for coordination or monitoring functions.

    - CONTRACTOR EVALUATIONS: If this Agreement is for consulting services, CalRecycle will evaluate the Contractor’s performance within sixty days of the completion of this Agreement and shall remain on file by CalRecycle for a period of thirty-six months. If the Contractor does not satisfactorily perform the work or service specified in this Agreement, CalRecycle will submit a copy of the negative evaluation to the Department of General Services (DGS), Office of Legal Services, within five (5) working days of the completion of the evaluation. Upon filing an unsatisfactory evaluation with the DGS, CalRecycle shall notify and send a copy of the evaluation to the Contractor within fifteen days. The Contractor shall have thirty days to prepare and send a written response to CalRecycle and the DGS. CalRecycle and the DGS shall file the Contractor's statement with the evaluation. (PCC §10369).

    - CONFIDENTIALITY/PUBLIC RECORDS: The Contractor and CalRecycle understand that each party may come into possession of information and/or data, which may be deemed confidential or proprietary by the person or organization furnishing the information or data. Such information or data may be subject to disclosure under the California Public Records Act, commencing with GC § 6250, or the PCC. CalRecycle agrees not to disclose such information or data furnished by Contractor and to maintain such information or data as confidential when so designated by Contractor in writing at the time it is furnished to CalRecycle, only to the extent that such information or data is exempt from disclosure under the California Public Records Act and the PCC.

    - CONFLICT-FUTURE BIDDING LIMITATION: Pursuant to Public Contracts Code Section 10365.5:

      - No person, firm, or subsidiary therefore who has been awarded a consulting services contract may submit a bid for, nor be awarded a contract for, the provision of services, procurement of goods or supplies, or any other related action that is required, suggested, or otherwise deemed appropriate in the end product of the consulting services contract.

      - Subdivision (a) does not apply to any person, firm, or subsidiary thereof who is awarded a subcontract of a consulting services contract that amounts to no more than ten (10) percent of the total monetary value of the consulting services contract.

      - Subdivisions (a) and (b) do not apply to consulting services contracts subject to Chapter 10 (commencing with Section 4525) of Division 5 of Title 1 of the Government Code.

    - CONSULTING SERVICES: If this Agreement is for consulting services, the Contractor is hereby advised of its duties, obligations and rights under PCC §§10335 through 10381.

    - COPYRIGHTS AND TRADEMARKS: The Contractor shall assign to CalRecycle any and all rights, title and interests to any copyrightable material or trademarkable material created or developed in whole or in any part as a result of this Agreement, including the right to register for copyright or trademark of such materials. The Contractor shall require that its subcontractors agree that all such materials shall be the property of CalRecycle. Such title will include exclusive copyrights and trademarks in the name of CalRecycle.

For contracts of $5,000 or more, any document or written report prepared for or under the direction of CalRecycle, shall include a notation on the inside cover as follows:

"Prepared as part of CalRecycle contract number DRR17079, Total Contract Amount ($TBD), pursuant to Government Code Section 7550."

    - DELIVERABLES: All documents and/or reports drafted for publication by or for CalRecycle in accordance with this contract shall adhere to CalRecycle’s Contractor Publications Guide at https://www.calrecycle.ca.gov/Contracts/PubGuide/ and shall be reviewed by CalRecycle’s Contract Manager in consultation with CalRecycle editor.

    - ENTIRE AGREEMENT: This Agreement supersedes all prior agreements, oral or written, made with respect to the subject hereof and, together with the Attachments and/or Exhibits hereto, contains the entire Agreement of the parties.

    - ENVIRONMENTAL JUSTICE: In the performance of this Agreement, the Contractor shall conduct its programs, policies, and activities that substantially affect human health or the environment in a manner that ensures the fair treatment of people of all races, cultures, and income levels, including minority populations and low income populations of the State. (Government Code Section 65040.12(e)).

    - FORCE MAJEURE: Neither CalRecycle nor the Contractor, including the Contractor's subcontractor(s), if any, will be responsible hereunder for any delay, default or nonperformance of this Agreement, to the extent that such delay, default or nonperformance is caused by an act of God, weather, accident, labor strike, fire, explosion, riot, war, rebellion, sabotage, or flood, or any other cause beyond the reasonable control of such party.

    - GRATUITIES: CalRecycle may terminate this Agreement if gratuities were offered or given by the Contractor, or any agent or representative of the Contractor, to any employee of CalRecycle, with a view toward securing a contract or securing favorable treatment with respect to awarding or amending or making a determination with respect to performance of this Agreement.

    - IMPRACTICABILITY OF PERFORMANCE: This Agreement may be suspended or cancelled, without notice at the option of the Contractor, if the Contractor’s or CalRecycle premises or equipment is destroyed by fire or other catastrophe, or so substantially damaged that it is impractical to continue service or in the event the Contractor is unable to render service as a result of any action by any governmental authority.

    - INSURANCE: When required, the Contractor must provide: 1) a Certificate of Insurance insuring CalRecycle, and/or 2) verification of Worker’s Compensation insurance. The Contractor must provide said Certificate of Insurance and/or verification to CalRecycle within ten (10) days after notification of CalRecycle’s intent to award the Agreement. The Agreement will not be executed nor can work begin unless said Certificate of Insurance and/or verification is provided to CalRecycle.

The Certificate of Insurance must be in effect and shall include the following terms and conditions:

      - CalRecycle, its officers, agents, employees, and servants shall be included as additional insured.

      - The dates of inception and expiration of coverage shall be specified.

      - A minimum liability coverage of not less than $1,000,000 per occurrence for bodily injury and property damage liability combined shall be specified. The coverage shall not include a deductible feature.

      - The insurer will not cancel the insured’s coverage without thirty days prior written notice to CalRecycle.

      - CalRecycle is not liable for the payment of premiums or assessments on said policy.

      - The insurance coverage shall be on an occurrence basis only.

In the event the Certificate of Insurance should expire or be cancelled during the term of this Agreement, the Contractor agrees to provide, at least thirty days prior to said expiration or cancellation, a new Certificate of Insurance evidencing coverage, as provided for herein, for not less than one (1) year or for the remainder of the contractual agreement, whichever is greater. In the event the Contractor fails to keep in effect at all times insurance coverage as herein provided, CalRecycle may, in addition to any other remedies it may have, terminate this Agreement upon occurrence of such event.

    - LIABILITY FOR NONCONFORMING WORK: The Contractor will be fully responsible for ensuring the completed work conforms to the agreed upon terms. If nonconformity is discovered prior to the Contractor’s deadline, the Contractor will be given a reasonable opportunity to cure the nonconformity. If the nonconformity is discovered after the deadline for the completion of the project, CalRecycle, in its sole discretion, may use any reasonable means to cure the nonconformity. The Contractor shall be responsible for reimbursing CalRecycle for any additional expenses incurred to cure such defects.

    - LICENSE OR PERMITS: The Contractor shall be an individual or firm licensed to do business in California and shall obtain at his/her expense all license(s) and permit(s) required by law for accomplishing any work required in connection with this Agreement.

In the event the Contractor fails to keep in effect at all times all required license(s) and permit(s), CalRecycle may, in addition to other remedies it may have, terminate this Agreement upon occurrence of such event.

    - ORDER OF PRECEDENCE: In the event of conflict or inconsistency between the articles, exhibits, attachments, specifications or provisions that constitute this Agreement, the following order of precedence shall apply: STD 213; GTC 04/2017 - General Terms and Conditions (incorporated by reference); Exhibit A – Scope of Work; Exhibit B – Budget Detail and Payment Provisions; Exhibit D – Special Terms and Conditions; Other exhibits in alphabetical order, beginning with E; Attachments in numerical order, beginning with 1.

    - OWNERSHIP OF DRAWINGS, PLANS AND SPECIFICATIONS: CalRecycle will have separate and independent ownership of all drawings, design plans, specifications, notebooks, tracings, photographs, negatives, reports, findings, recommendations, data and memoranda of every description or any part thereof, prepared under this Agreement. The originals and all copies thereof will be delivered to CalRecycle upon request. CalRecycle will have the full right to use said originals and copies in any manner when and where it may determine without any claim on the part of the Contractor, its vendors or subcontractors to additional compensation.

    - PATENTS: The Contractor assigns to CalRecycle all rights, title, and interest in and to each invention or discovery that may be capable of being patented, that is conceived of or first actually reduced to practice in the course of or under this Agreement.

    - PUBLICITY AND ACKNOWLEDGEMENT: The Contractor agrees that it will acknowledge CalRecycle’s support whenever projects funded, in whole or in part, by this Agreement are publicized in any news media, brochures, or other type of promotional material.

    - RECYCLED-CONTENT PRODUCT PURCHASING: In the performance of this Agreement, the Contractor shall purchase used and/or recycled-content products as set forth on the back of the Recycled-Content Certification Form (Exhibit D,  Attachment 1). For assistance in locating recycled-content products, please search the recycled-content product database available at: https://www2.calrecycle.ca.gov/buyrecycled/manufacturers/directory/. If after searching the database, contractors are unable to find the recycled-content products they are looking for, please notify CalRecycle’s Contract Manager. All recycled content products purchased or charged/billed to CalRecycle that are printed upon such as promotional items, publications, written materials, and other educational brochures shall have both the total recycled content (TRC) and the post-consumer (PC) content clearly printed on them.

In addition, any written documents such as, publications, letters, brochures, and/or reports shall be printed double-sided on 100% post-consumer (PC) paper. Specific pages containing full-color photographs or other ink-intensive graphics may be printed on photographic paper. The paper should identify the post-consumer recycled content of the paper (i.e., “printed on 100% post-consumer paper”). When applicable, the Contractor shall provide the Contract Manager with an electronic copy of the document and/or report for CalRecycle’s uses. When appropriate, only an electronic copy of the document and/or report shall be submitted and no hard copy shall be provided.

    - REMEDIES: Unless otherwise expressly provided herein, the rights and remedies hereunder are in addition to, and not in limitation of, other rights and remedies under the Agreement, at law or in equity, and exercise of one right or remedy will not be deemed a waiver of any other right or remedy.

    - SETTLEMENT OF DISPUTES: In the event of a dispute, the Contractor shall file a “Notice of Dispute” with CalRecycle’s Director or his/her designee with ten (10) days of discovery of the problem. Within ten (10) days, the Director or his/her designee shall meet with the Contractor and CalRecycle Project Manager for the purpose of solving the dispute.

    - STOP WORK NOTICE: Immediately, upon receiving a written notice to stop work, the Contractor shall cease all work under this Agreement.

    - SUBCONTRACTORS: All Subcontractors previously identified in the bid/proposal submitted are considered to be acceptable to CalRecycle. Any change or addition of Subcontractors will be subject to the prior written approval of the Contract Manager or the Director or his/her designee. Upon termination of any Subcontract, the Contractor shall notify the Contract Manager or the Executive Director immediately. If CalRecycle or the Contractor determines that the level of expertise or the services required are beyond that provided by the Contractor or its routine Subcontractors, The Contractor will be required to employ additional Subcontractors. Nothing contained in this Agreement or otherwise, shall create any contractual relation between CalRecycle and any Subcontractors, and no Subcontract shall relieve the Contractor of its responsibilities and obligations hereunder. The Contractor agrees to be as fully responsible to CalRecycle for the acts and omissions of its Subcontractors and of persons either directly or indirectly employed by any of them as it is for the acts and omissions of persons directly employed by the Contractor. The Contractor's obligation to pay its Subcontractors is an independent obligation from CalRecycle obligation to make payments to the Contractor. As a result, CalRecycle shall have no obligation to pay or to enforce the payment of any moneys to any Subcontractor.

    - SUCCESSORS: The provisions of this Agreement will be binding upon and inure to the benefit of CalRecycle, the Contractor, and their respective successors.

    - TERMINATION: CalRecycle shall have the right to terminate this Agreement at its sole discretion at any time upon thirty days written notice given to the Contractor. In the case of early termination, a final payment will be made to the Contractor upon approval by the Contract Manager of a financial report, invoices for costs incurred to date of termination and a written report describing all work performed by the Contractor to date of termination.

    - UNRELIABLE LIST: Prior to authorizing a Subcontractor(s) to commence work under this Agreement, the Contractor shall submit to CalRecycle a declaration from the Subcontractor(s), signed under penalty of perjury, stating that within the preceding three years, none of the events listed in Section 17050 of Title 14, California Code of Regulations, Natural Resources, Division 7, have occurred with respect to the subcontractor(s).

Placement of Contractor on CalRecycle Unreliable List anytime after award of this Agreement may be grounds for termination of Agreement. If a Subcontractor is placed on CalRecycle Unreliable List after award of this Agreement, the Contractor may be required to terminate the Subcontract.

    - WASTE REDUCTION: In the performance of this Agreement, the Contractor shall take all reasonable steps to ensure that materials purchased or consumed in the course of the project are utilized both effectively and efficiently to minimize the generation of waste. The steps should include, but not necessarily be limited to, the use of reusable products, the use of recyclable and compostable products, discretion in the amount of materials used, the provision of alternatives to disposal for materials consumed, and the practice of other waste reduction measures where feasible and appropriate.

THIS PAGE INTENTIONALLY LEFT BLANK

| STATE OF CALIFORNIA | To be completed by Contractor |  |
| --- | --- | --- |
| Department of Resources Recycling and Recovery (CalRecycle) | Name of Contractor: |  |
| CalRecycle 74C (Rev. 06/10 for Contracts) | Contract #: | Work Order #: |

Recycled Content Certification

Check this box if no products, materials, goods, or supplies were purchased with contract dollars and submit to the CalRecycle Contract Manager.

This form to be completed by contractor. The form must be completed and returned to CalRecycle with a row completed for each product purchased with contract dollars. Attach additional sheets if necessary. Information must be included, even if the product does not contain recycled-content material. Product labels, catalog/website descriptions, or bid specifications may be attached to this form as a method of providing that information.  Add additional rows as needed.

Contractor’s Name     	Date

Address     	Phone

Fax     	E-mail     	Web site

| Product Manufacturer | Product Description / Brand | Purchase Amount ($) | 1Percent Postconsumer Material | 2SABRC Product Category Code | Meets SABRC |
| --- | --- | --- | --- | --- | --- |

Public Contract Code sections 12205 (a) (1) (2) (3) (b) (1) (2) (3).

I certify that the above information is true. I further certify that these environmental claims for recycled content regarding these products are consistent with the Federal Trade Commission’s Environmental Marketing Guidelines in accordance with PCC Section 12205.

______________________________________________________________________________

Print name	Signature 	Company	 Date

(See footnotes on the back of this page.) 
Postconsumer material comes from products that were bought by consumers, used, then recycled. For example: a newspaper that has been purchased and read, next recycled, and then used to make another product would be postconsumer material.

If the product does not fit into any of the product categories, enter “N/A.”  Common N/A products include wood products, natural textiles, aggregate, concrete, electronics such as computers, TV, software on a disk or CD, telephone

- Product category refers to one of the product categories listed below, into which the reportable purchase falls. For products made from multiple materials, choose the category that comprises most of the product by weight, or volume.

Note: For reused or refurbished products, there is no minimum content requirement.

For additional information visit www.CalRecycle.ca.gov/BuyRecycled/.

| Code | Description | Minimum content requirement |
| --- | --- | --- |
|  | Product Categories (11) |  |
| 1 | Paper Products - Recycled | 30 percent postconsumer fiber, by fiber weight |
| 2 | Printing and Writing - Recycled | 30 percent postconsumer fiber, by fiber weight |
| 3 | Compost, Co-compost, and Mulch – Recycled | 80 percent recovered materials. i.e., material that would otherwise be normally disposed of in a landfill |
| 4 | Glass – Recycled | 10 percent postconsumer, by weight |
| 5 | Rerefined Lubricating Oil - Recycled | 70 percent re-refined base oil |
| 6a | Plastic – Recycled | 10 percent postconsumer, by weight |
| 6b | Printer or duplication cartridges | - Have 10 percent postconsumer material, or - Are purchased as remanufactured, or - Are backed by a vendor-offered program that will take back the printer cartridges after their useful life and ensure that the cartridges are recycled and comply with the definition of recycled as set forth in Section 12156 of the Public Contract Code. |
| 7 | Paint – Recycled | 50 percent postconsumer paint (exceptions when 50% postconsumer content is not available or is restricted by a local air quality management district, then 10% postconsumer content may be substituted) |
| 8 | Antifreeze – Recycled | 70 percent postconsumer material |
| 9 | Retreated Tires - Recycled | Use existing casing that has undergone retreading or recapping process in accordance with Public Resource Code (commencing with section 42400). |
| 10 | Tire- Derived - Recycled | 50 percent postconsumer tires |
| 11 | Metals – Recycled | 10 percent postconsumer, by weight |

## Proposal Completion Checklist

Please use this checklist to assist in the preparation of your Proposal package to ensure that all required items are included.

|  | Cover Letter with contact information and statements as required in the RFP. |
| --- | --- |
|  | Organizational information and Personnel Information (Resumes) |
|  | Proposal (detailed Work Plan) |
|  | Samples of Written Work |
|  | Copy of Required License(s) (Secretary of State) |
|  | Cost Proposal Sheet (Attachment A) |
|  | Bidder Declaration (Attachment C) (Form must be submitted. Even if participation levels are zero, (write zero participation on form) |
|  | Iran Contracting Act Certification (Attachment E) |
|  | Darfur Contracting Act Certification (Attachment F) |
|  | California Civil Rights Laws Certification (Attachment G) |
|  | Contractor Status Form (Attachment H) |
|  | Client References (Attachment I) |

The following number of PROPOSAL packages must be submitted as the Contractor’s response to this RFP:

|  | One (1) unbound reproducible original Proposal package marked “Original” |
| --- | --- |
|  | Three (3) bound copies of the Proposal package marked “Copy”. |
|  | One (1) Electronic copy of Proposal Package in Adobe Acrobat format with all documents in a single file, including all attachments. |

The following form is only required upon submittal as applicable pursuant to the provisions outlined in Section III, Submittal Requirements:

|  | Certification of Target Area Contract Preference Act (The form may be downloaded at https://www.calrecycle.ca.gov/contracts/forms.) |
| --- | --- |

The following forms are not required at the time of the Proposal submission but are part of the draft Standard Agreement (Attachment I) and will be required by the successful Contractor during the contract period:

|  | Recycled Content Certification (end of Attachment J) |  |
| --- | --- | --- |
|  | Payee Data Record (Standard Form 204 viewable at https://www.calrecycle.ca.gov/Contracts/Forms/default.htm) |  |
|  | Small Business (SB) and Disabled Veteran Business Enterprise (DVBE) Subcontractor Payment Certification (Attachment D) |  |

Please note that if any of the items are missing from the Proposal package, the package will be considered incomplete and will be disqualified from the process.